## Summary (hidden)
Overall Summary of NHIDCL Road Works as on date
| State/UT | Total Entrusted Length (in KM) | Total Sanctioned (A+B+C+D+E+F) |  |  | A) Sanctioned but Balance For Award |  |  | B) Completed (inc. CC Under Issue) |  |  | C) Awarded Not Appointed |  |  | D) Terminated |  |  | E) Under Termination |  |  | F) Under Construction |  |  | Length Constructed against sanctioned length (in KM)
|  |  | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.)
NER | Arunachal Pradesh | 1221 | 46 | 1096.118 | 16577.707 |  |  |  | 34 | 662.626 | 8036.387 | 2 | 55.14 | 1200.29 | [6 empty] | 10 | 378.352 | 7341.03 | 748.708
| Assam | 1596 | 77 | 1396.445 | 67941.39 | 1 | 33.7 | 18662.02 | 36 | 655.73 | 16150.07 | 2 | 33.622 | 1829.62 | 5 | 52.565 | 2015.28 |  |  |  | 33 | 620.828 | 29284.4 | 1046.477
| Manipur | 1481.3 | 52 | 1124.539 | 16218.21 | 1 | 51.985 | 228.4 | 23 | 404.353 | 6564.84 | 2 | 21.201 | 446.98 |  |  |  | 1 | 22.34 | 226.32 | 25 | 624.66 | 8751.67 | 838.867
| Meghalaya | 428 | 23 | 594.149 | 31598.12 | 4 | 164.355 | 22863.93 | 8 | 191.168 | 2227.89 | 2 | 36.79 | 1515.34 | [6 empty] | 9 | 201.836 | 4990.96 | 305.015
| Mizoram | 921 | 33 | 818.51 | 19712.26 |  |  |  | 20 | 560.296 | 10515.34 | 1 | 10.6 | 329.7 | [6 empty] | 12 | 247.614 | 8867.22 | 651.213
| Nagaland | 667 | 40 | 792.464 | 13415.91 |  |  |  | 21 | 439.529 | 7168.17 | 1 | 17 | 207.33 | 2 | 41.184 | 850.04 |  |  |  | 16 | 294.751 | 5190.37 | 705.0675
| Sikkim | 279 | 17 | 213.429 | 5247.6065 | 1 | 5.3 | 161.2365 | 7 | 63.2 | 1320.35 |  |  |  | 1 | 7.322 | 348.92 | 2 | 31.37 | 853.76 | 6 | 106.237 | 2563.34 | 180.571
| Tripura | 793 | 31 | 744.675 | 11911.2708 |  |  |  | 17 | 412.063 | 4763.9168 | 1 | 72.472 | 198.51 |  |  |  | 2 | 31.872 | 2380.84 | 11 | 228.268 | 4568.004 | 498.988
| TOTAL (NER) | 7386.3 | 319 | 6780.329 | 182622.4743 | 7 | 255.34 | 41915.5865 | 166 | 3388.965 | 56746.9638 | 11 | 246.825 | 5727.77 | 8 | 101.071 | 3214.24 | 5 | 85.582 | 3460.92 | 122 | 2702.546 | 71556.994 | 4974.9065
Non-NER | Andaman & Nicobar | 331 | 12 | 321.651 | 2505.86 |  |  |  | 7 | 175.443 | 780.265 | [6 empty] | 2 | 88.865 | 644.12 | 3 | 57.343 | 1081.475 | 313.138
| Jammu & Kashmir (RO-Jammu) | 270 | 17 | 191.976 | 5790.4131 |  |  |  | 9 | 119.18 | 3089.22 | 1 | 4.037 | 132.99 | 1 | 1.269 | 91.29 |  |  |  | 6 | 67.49 | 2476.9131 | 170.0365
| Jammu & Kashmir (RO-Srinagar) | 37 | 6 | 131.972 | 10360.12 | 1 | 9.866 | 157.25 | 4 | 91.213 | 3394.18 | [9 empty] | 1 | 30.893 | 6808.69 | 106.3
| Ladakh | 234 | 11 | 225.225 | 3075.71 |  |  |  | 6 | 98.935 | 1292.99 |  |  |  | 1 | 24.04 | 384.24 |  |  |  | 4 | 102.25 | 1398.48 | 202.004
| Uttarakhand | 100 | 14 | 110.1105 | 3554.26 |  |  |  | 10 | 100.11 | 1443.83 | [9 empty] | 4 | 10.0005 | 2110.43 | 99.417
| West Bengal | 228 | 19 | 111.764 | 3015.3 | 3 | 20.47 | 658.23 | 5 | 48.317 | 1333.64 | 2 | 2.2 | 133.06 | [6 empty] | 9 | 40.777 | 890.37 | 79.867
| TOTAL (Non-NER) | 1200 | 79 | 1092.6985 | 28301.6631 | 4 | 30.336 | 815.48 | 41 | 633.198 | 11334.125 | 3 | 6.237 | 266.05 | 2 | 25.309 | 475.53 | 2 | 88.865 | 644.12 | 27 | 308.7535 | 14766.3581 | 970.7625
| Total Civil Road Works | 8586.3 | 398 | 7873.0275 | 210924.1374 | 11 | 285.676 | 42731.0665 | 207 | 4022.163 | 68081.0888 | 14 | 253.062 | 5993.82 | 10 | 126.38 | 3689.77 | 7 | 174.447 | 4105.04 | 149 | 3011.2995 | 86323.3521 | 5945.669
| Assam (MMLP) |  | 4 | 8.01 | 764.89 | 0 | 0 | 0 | 4 | 8.01 | 764.89
| Grand Total (overall) | 8586.3 | 402 | 7881.0375 | 211689.0274 | 11 | 285.676 | 42731.0665 | 211 | 4030.173 | 68845.9788 | 14 | 253.062 | 5993.82 | 10 | 126.38 | 3689.77 | 7 | 174.447 | 4105.04 | 149 | 3011.2995 | 86323.3521 | 5945.669
NH-Road Works as on date
| State/UT | Total Entrusted Length (in KM) | Total Sanctioned (A+B+C+D+E) |  |  | A) Sanctioned but Balance For Award |  |  | B) Completed (inc. CC Under Issue) |  |  | C) Awarded Not Appointed |  |  | D) Terminated |  |  | Under Termination |  |  | E) Under Construction |  |  | Length Constructed against sanctioned length (in KM)
|  |  | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.)
NER | Arunachal Pradesh | 1221 | 43 | 1016.19 | 15780.32 | 0 | 0 | 0 | 31 | 582.698 | 7239 | 2 | 55.14 | 1200.29 |  |  |  | 0 | 0 | 0 | 10 | 378.352 | 7341.03 | 668.78
| Assam | 1596 | 77 | 1396.445 | 67941.39 | 1 | 33.7 | 18662.02 | 36 | 655.73 | 16150.07 | 2 | 33.622 | 1829.62 | 5 | 52.565 | 2015.28 | 0 | 0 | 0 | 33 | 620.828 | 29284.4 | 1046.477
| Manipur | 1481.3 | 52 | 1124.539 | 16218.21 | 1 | 51.985 | 228.4 | 23 | 404.353 | 6564.84 | 2 | 21.201 | 446.98 |  |  |  | 1 | 22.34 | 226.32 | 25 | 624.66 | 8751.67 | 838.867
| Meghalaya | 428 | 13 | 394.071 | 28102.77 | 4 | 164.355 | 22863.93 | 2 | 63.136 | 961.21 | 2 | 36.79 | 1515.34 |  |  |  | 0 | 0 | 0 | 5 | 129.79 | 2762.29 | 124.5
| Mizoram | 921 | 33 | 818.51 | 19712.26 |  |  |  | 20 | 560.296 | 10515.34 | 1 | 10.6 | 329.7 |  |  |  | 0 | 0 | 0 | 12 | 247.614 | 8867.22 | 651.213
| Nagaland | 667 | 25 | 530.729 | 8554.26 |  |  |  | 12 | 257.989 | 3965.2 | 1 | 17 | 207.33 | 2 | 41.184 | 850.04 | 0 | 0 | 0 | 10 | 214.556 | 3531.69 | 467.0055
| Sikkim | 279 | 17 | 213.429 | 5247.6065 | 1 | 5.3 | 161.2365 | 7 | 63.2 | 1320.35 |  |  |  | 1 | 7.322 | 348.92 | 2 | 31.37 | 853.76 | 6 | 106.237 | 2563.34 | 180.571
| Tripura | 793 | 31 | 744.675 | 11911.2708 |  |  |  | 17 | 412.063 | 4763.9168 | 1 | 72.472 | 198.51 |  |  |  | 2 | 31.872 | 2380.84 | 11 | 228.268 | 4568.004 | 498.988
Non-NER | Andaman & Nicobar | 331 | 12 | 321.651 | 2505.86 |  |  |  | 7 | 175.443 | 780.265 | [6 empty] | 2 | 88.865 | 644.12 | 3 | 57.343 | 1081.475 | 313.138
| Jammu & Kashmir (RO-Jammu) | 270 | 17 | 191.976 | 5790.4131 |  |  |  | 9 | 119.18 | 3089.22 | 1 | 4.037 | 132.99 |  |  |  | 0 | 0 | 0 | 6 | 67.49 | 2476.9131 | 170.0365
| Jammu & Kashmir (RO-Srinagar) | 37 | 6 | 131.972 | 10360.12 | 1 | 9.866 | 157.25 | 4 | 91.213 | 3394.18 | [6 empty] | 0 | 0 | 0 | 1 | 30.893 | 6808.69 | 106.3
| Ladakh | 234 | 11 | 225.225 | 3075.71 |  |  |  | 6 | 98.935 | 1292.99 |  |  |  | 1 | 24.04 | 384.24 | 0 | 0 | 0 | 4 | 102.25 | 1398.48 | 202.004
| Uttarakhand | 100 | 14 | 110.1105 | 3554.26 |  |  |  | 10 | 100.11 | 1443.83 | [6 empty] | 0 | 0 | 0 | 4 | 10.0005 | 2110.43 | 99.417
| West Bengal | 228 | 19 | 111.764 | 3015.3 | 3 | 20.47 | 658.23 | 5 | 48.317 | 1333.64 | 2 | 2.2 | 133.06 |  |  |  | 0 | 0 | 0 | 9 | 40.777 | 890.37 | 79.867
| Grand Total | 8586.3 | 370 | 7331.2865 | 201769.7504 | 11 | 285.676 | 42731.0665 | 189 | 3632.663 | 62814.0518 | 14 | 253.062 | 5993.82 | 9 | 125.111 | 3598.48 | 7 | 174.447 | 4105.04 | 139 | 2859.0585 | 82436.0021 | 5447.164
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The length as per existing road is 921 Kms and upon realignment and Geometric improvement, the existing length of 921 Kms is reduced to 819.20 Kms in proportion.
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The length as per existing road is 921 Kms and upon realignment and Geometric improvement, the existing length of 921 Kms is reduced to 819.20 Kms in proportion.

## Summary-Comp. & Ong.
Overall Summary of NHIDCL Road Works as on 30-06-2026
State/UT | Completed Projects (inc. CC Under Issue) |  |  | Awarded Not Appointed |  |  | Ongoing Projects (excl. Under Termination)
| Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.) | Nos. | Length (Km) | TPC (Cr.)
Arunachal Pradesh | 34 | 662.626 | 8036.387 | 3 | 79.959 | 1641.7 | 10 | 378.352 | 7341.03
Assam | 36 | 655.73 | 16150.07 | 2 | 33.622 | 1829.62 | 33 | 620.828 | 29284.4
Manipur | 23 | 404.353 | 6564.84 | 2 | 21.201 | 446.98 | 25 | 624.66 | 8751.67
Meghalaya | 8 | 191.168 | 2227.89 | 2 | 36.79 | 1515.34 | 9 | 201.836 | 4990.96
Mizoram | 20 | 560.296 | 10515.34 | 1 | 10.6 | 329.7 | 12 | 247.614 | 8867.22
Nagaland | 21 | 439.529 | 7168.17 | 1 | 17 | 207.33 | 16 | 294.751 | 5190.37
Sikkim | 7 | 63.2 | 1320.35 |  |  |  | 6 | 106.237 | 2563.34
Tripura | 17 | 412.063 | 4763.9168 | 1 | 72.472 | 198.51 | 11 | 228.268 | 4568.004
Andaman & Nicobar | 7 | 175.443 | 780.265 |  |  |  | 3 | 57.343 | 1081.475
Jammu & Kashmir (RO-Jammu) | 9 | 119.18 | 3089.22 | 1 | 4.037 | 132.99 | 6 | 67.49 | 2476.9131
Jammu & Kashmir (RO-Srinagar) | 4 | 91.213 | 3394.18 |  |  |  | 1 | 30.893 | 6808.69
Ladakh | 6 | 98.935 | 1292.99 |  |  |  | 4 | 102.25 | 1398.48
Uttarakhand | 10 | 100.11 | 1443.83 |  |  |  | 4 | 10.0005 | 2110.43
West Bengal | 5 | 48.317 | 1333.64 | 2 | 2.2 | 133.06 | 9 | 40.777 | 890.37
Total Civil Road Works | 207 | 4022.163 | 68081.0888 | 15 | 277.881 | 6435.23 | 149 | 3011.2995 | 86323.3521
Assam (MMLP) | 4 | 8.01 | 764.89
Grand Total (overall) | 211 | 4030.173 | 68845.9788 | 15 | 277.881 | 6435.23 | 149 | 3011.2995 | 86323.3521

## Project list
NHIDCL -Completed and Ongoing Projects details as per PMP Data Lake Portal (30-06-2026)
Sl. No. | Dir.(T)s | NER/Non-NER | State/UT | PMU Name | PMIS ID | PMP (UPN- ID) | Project Stage | Project Status | Short Project Name | Name of Project | Scheme /Funding | NH/ NON-NH | NH No. (Old/ New) | Project Length (Km) | F.Y (26-27) | Total Length Constructed (KM) | TPC (in Crore) | Awarded Cost (in Cr.) | Date of Sanction | Date of Award | Appointed Date | Physical Progress (%) | Financial Progress (%) | Scheduled Completion Date | Likely Completion date as per PMP | Actual Date of Completion | Name of the Contractor | Contractor Email id | Name of the AE/IE | Project Type (Bridge/ Tunnel/ Bypass/ MJB/ Road)
1 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 123230 | DN/09009/01019/AN | Completed | Completed | Andaman Trunk Road Pkg-5 | Rehabilitation of Km 0.00 to Km 12.00 section in Andaman Trunk Road of NH-4 to Intermediate lane with hard shoulder in UT of A&N islands on EPC mode under NH(O) (Package-V) | NH(O) | NH | 223/ 4 | 12 | - | 12.001 | 32.54 | 22.6 | 2018-10-22 | 2019-02-14 | 2019-04-02 | 100 | 99.19 | 2020-03-31 | - | 2021-06-11 | Mohan Mutha Exports Pvt Ltd | 1) dkmutha@mmexport.com 2) pkmutha@mmexports.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
2 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 60004 | DN/09009/01020/AN | Completed | Completed | Beodnabad- Ferrargunj section Pkg-1 | Rehabilitation and up-gradation to 2-Lane with hard shoulder of section from Beodnabad- Ferrargunj section of NH-223 (New NH-04) from Km 12.000 to 45.000 (excluding Km 21.0 to 28.0) in UT of A&N islands on EPC mode (Package-I) | NH(O) | NH | 223/ 4 | 25.931 | - | 25.93 | 176.76 | 124.74 | 2017-01-19 | 2017-03-01 | 2017-11-01 | 100 | 100 | 2018-10-31 | - | 2019-05-03 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | prabaharan@sreeinfratech.com | Eptisa Servicios De Ingenieria S.L. | Normal Highway/Road Project
3 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 123227 | DN/09009/01021/AN | Completed | Completed | Andaman Trunk Road (Package-VI) | Rehabilitation of section from Km 45.00 to Km 59.20 of NH-4 to Intermediate lane with hard shoulder in UT of A&N islands on EPC mode under NH(O) (Package-VI) | NH(O) | NH | 223/ 4 | 14.1 | - | 14.1 | 59.08 | 37.67 | 2018-10-22 | 2019-02-14 | 2019-04-02 | 100 | 98.8 | 2020-03-31 | - | 2021-09-22 | Mohan Mutha Exports Pvt Ltd | 1) dkmutha@mmexport.com 2) pkmutha@mmexports.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
4 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 80782 | DN/09009/01022/AN | Completed | Completed | Strengthening and Upgradation of Jarwa area | Rehabilitation and Up-gradation of Jarwa area of NH-223 (New NH-4) from Km 59.40 to Km 107.00 (Jarwa-I) and Km 138.30 to Km 155.00 (Jarwa-II) in UT of A&N islands on Item Rate basis | NH(O) | NH | 223/ 4 | 64.3 | - | 64.3 | 59.56 | 53.73 | 2018-01-05 | 2018-03-05 | 2018-04-09 | 100 | 97.38 | 2019-04-09 | - | 2021-03-31 | J Infratech Limited (JIL) | 1) hoplanningjcipl@gmail.com 2)janduconstco@yahoo.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
5 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 157635 | DN/09009/01029/AN | Ongoing | Under Construction (AD issued) | Middle Strait Creek Bridge | Construction of Major Bridge over Middle Strait Creek between Km. 106.590 to Km 108.553 of NH-223 (New NH-04) connecting South Andaman and Baratang Islands in UT of A&N islands on EPC mode-Balance work | NH(O) | NH | 223/ 4 | 1.963 | - | 0 | 371.88 | 207.99 | 2015-03-31 | 2024-03-16 | 2024-05-07 | 12.98 | 9.27 | 2026-02-25 | 2026-12-31 | - | RKEC Projects Ltd.-YFC Projects Pvt. Ltd. (JV) | msbridge@rkecprojects.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Standalone Bridge Project
6 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 157583 | DN/09009/01018/AN | Ongoing | Under Construction (AD issued) | Andaman Trunk Road (Package-3A) | Rehabilitation and up-gradation of section to Intermediate/2-Lane with hard shoulder from Km 107.760 to Km 129.445 (After Middle strait to Humphrey), Km 130.600 to Km 138.00 (After Humphrey to Kadamtala) of NH-04 in the Union Territory of Andaman & Nicobar Islands on EPC (Package-IIIA)-Balance work | NH(O) | NH | 223/ 4 | 29.38 | - | 25.3 | 376.48 | 154.01 | 2018-02-27 | 2024-01-25 | 2024-03-14 | 81.32 | 54.38 | 2025-09-13 | 2026-12-31 | - | SMC Infrastructures | andaman3a.smcipl@gmail.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
7 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Mayabunder | 157584 | DN/09009/01027/AN | Ongoing | Under Construction (AD issued) | Andaman Trunk Road (Package-3B) | Rehabilitation and up-gradation and completion of balance work of section from Km 155.00 to Km 181.00 (End of Jarwa to Rangat) of NH -4 (Total length 26 Km) to Intermediate Lane/2-lane with hard shoulders in the UT of A&N Islands on EPC basis - (Package-III)-B Balance work | NH(O) | NH | 223/ 4 | 26 | - | 24.7 | 333.115 | 198.59 | 2018-02-27 | 2024-03-16 | 2024-05-07 | 50.15 | 45.59 | 2025-10-05 | 2027-03-31 | - | RKEC Projects Ltd. | roadpkg3@rkecprojects.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
8 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Baratang | 60003 | DN/09009/01023/AN | Completed | Completed | Humphrey Strait Creek Bridge (Azad Hind Fauz Setu) | Construction of Major Bridge (Bridge Length- 1020m) over Humphrey Strait Creek between Km.129.420 to Km. 130.600 of NH-223 (New NH-04) connecting Middle & North Andaman Island in the UT of Andaman and Nicobar Islands on EPC Basis "Azad Hind Fauz Setu" | NH(O) | NH | 223/ 4 | 1.45 | - | 0.28 | 271.065 | 202.91 | 2015-03-31 | 2017-02-15 | 2017-04-26 | 100 | 97.42 | 2020-04-25 | - | 2022-03-15 | MostoBudivelnyl Zahin(MBZ)-RDS Projects Ltd.(JV) [MBZ -RDS (JV)] | mayank.goyal@rdsproject.com | Eptisa Servicios De Ingenieria S.L. | Standalone Bridge Project
9 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Mayabunder | 123231 | DN/09009/01028/AN | Completed | Completed | Andaman Trunk Road Pkg-7 | Rehabilitation of Km 181.00 to Km 206.00 section in Andaman Trunk Road of NH-4 to Intermediate lane with hard shoulder in UT of A&N islands on EPC mode under NH(O) (Package-VII) | NH(O) | NH | 223/ 4 | 25 | - | 25 | 71.93 | 53.96 | 2018-10-22 | 2018-11-28 | 2019-01-01 | 100 | 100 | 2019-12-31 | - | 2021-03-31 | Garg & Sons Estate Promoters Pvt Ltd | 1) racgrag@yahoo.com 2) racgarg260@gmail.com | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
9 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Mayabunder | 102028 | DN/09009/01024/AN | Under Termination | Under Termination | Andaman Trunk Road (from Nimbutala to Austin Creek) (Package-IV) | Rehabilitation and up-gradation to 2-Lane with hard shoulder of section from Km 206.00 to Km 242.00(Design Ch. 239.425) (Nimbutala to Austin Creek) of NH-223 (New NH-4) in UT of A&N islands on EPC mode (Package-IV) | NH(O) | NH | 223/ 4 | 33.405 | - | 33.41 | 234.27 | 148.6 | 2018-03-14 | 2018-03-27 | 2018-09-04 | 83.09 | 79.69 | 2020-09-03 | Under Termination | - | Vasishta Constructions Pvt. Ltd. | aditya.k@vasishta.in | Yongma Engineering Co. Ltd. In association with Techniko Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
9 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Mayabunder | 63704 | DN/09009/01026/AN | Under Termination | Under Termination | Andaman Trunk Road (Package-II) | Rehabilitation and up-gradation to 2-Lane with hard shoulder of section from Km 242.0 to 298.0 of NH-223 (New NH-4) in UT of A&N islands on EPC mode (Package-II) | NH(O) | NH | 223/ 4 | 55.46 | - | 55.457 | 409.85 | 190.69 | 2017-03-28 | 2017-03-31 | 2017-12-05 | 95.34 | 95.1 | 2019-12-04 | Under Termination | - | Vasishta Constructions Pvt. Ltd.- Mantena Infra LLP (JV) | aditya.k@vasishta.in | Eptisa Servicios De Ingenieria S.L. | Normal Highway/Road Project
10 | DT-2 | Non-NER | Andaman & Nicobar | PMU-Mayabunder | 152098 | DN/09009/01025/AN | Completed | Physically Completed & CC Under Issue | Karala to Kalipur (Andaman Trunk Road) (Package-VIII) | Rehabilitation of section from Km 298.00 to Km 330.662 (Karala to Kalipur) of NH-04 to Intermediate lane with hard shoulder in UT of A&N islands on EPC mode under NH(O) (Package-VIII) | NH(O) | NH | 223/ 4 | 32.662 | - | 32.66 | 109.33 | 74.61 | 2019-03-09 | 2021-04-13 | 2021-07-01 | 100 | 96.6 | 2023-07-01 | 2026-08-31 | - | Kaba Infratech Pvt. Ltd. | shivam.agrawal@kabagroup.com | Eptisa Servicios De Ingenieria S.L. | Normal Highway/Road Project
11 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60009 | DN/19009/01006/AR | Completed | Completed | Mahadevpur - Buri Dihing Bridge point | 2 laning from Mahadevpur to Buri Dihing Bridge point section (NH-52B) (New NH-215) of the stretch from 0.00 km. to 25.135 km in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC basis | SARDP-NE | NH | 52B/215 | 25.135 | - | 25.135 | 136.6 | 107.16 | 2015-03-30 | 2015-03-31 | 2015-05-30 | 100 | 100 | 2018-05-30 | - | 2018-05-21 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) - Puna Hinda (JV) | punahinda@gmail.com | Voyants Solution Pvt Ltd. (VSPL) | Normal Highway/Road Project
12 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60013 | DN/19009/01008/AR | Completed | Completed | Bordumsa-Namchik (Buri Dihing-Jairampur) | 2-Laning from Bordumsa-Namchik (Buri Dihing-Jairampur) road of NH-52B (New NH-215) from Km 0.15 km (starting Chainage near Buridihing Bridge) to km 22.380 in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC Mode | SARDP-NE | NH | 52B/215 | 22.23 | - | 22.13 | 189.91 | 143.21 | 2015-07-23 | 2015-07-23 | 2015-10-23 | 100 | 100 | 2018-10-22 | - | 2018-08-05 | Bhartia Infra Projects Limited(BIPL)-Bharat Vanijya Eastern Pvt. Ltd.(BVEPL) (JV) | biplbvepljv@rediffmail.com | Voyants Solution Pvt Ltd. (VSPL) | Normal Highway/Road Project
13 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60011 | DN/19009/01010/AR | Completed | Completed | Changlang-Tirap District Boundary | 2-Laning from Changlang/Tirap District Boundary to Changlang of NH-52B (New NH-215) from design km 0.00 to km 18.266 (length 18.266 km) in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC mode | SARDP-NE | NH | 52B/215 | 18.266 | - | 18.266 | 172.75 | 130.1 | 2015-03-30 | 2015-03-31 | 2015-06-01 | 100 | 97.31 | 2018-05-31 | - | 2021-04-14 | T.K. Engineering Consortium Pvt. Ltd. (TKECPL) | tkeconltd@gmail.com debajitdz501@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
14 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60010 | DN/19009/01009/AR | Completed | Completed | Changlang-Tirap District Boundary to Khonsa | 2-Lanning from Changlang/Tirap District Boundary to Khonsa of NH 52B (New NH 215) (Length 42.844 km) i in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE Phase-II on EPC mode | SARDP-NE | NH | 52B/215 | 42.844 | - | 41.844 | 438.32 | 334.22 | 2016-01-14 | 2016-03-01 | 2016-06-15 | 100 | 100 | 2019-06-14 | - | 2019-03-04 | M.G. Contractors Pvt. Ltd.(MGCPL)-H.G. Infra Engineering Pvt. Ltd.(HGIEPL) (JV) | delhi@mgcpl.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
15 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60015 | DN/19009/01007/AR | Completed | Completed | Kanubari to Longding Section | 2-Laning from Kanubari to Longding Section of NH-52B (New NH215) From km.0.000 to km. 47.213 (DPR Length 47.213 km & Design length 45.600) in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC mode | SARDP-NE | NH | 52B/215 | 47.21 | - | 45.6 | 522.87 | 394 | 2015-03-30 | 2015-03-31 | 2015-06-02 | 100 | 96.94 | 2018-11-26 | - | 2021-03-31 | MonteCarlo Ltd. | kanubari.ap@mclindia.com | Voyants Solution Pvt Ltd. (VSPL) | Normal Highway/Road Project
16 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 157542 | DN/19001/02002/AR | Completed | Completed | Ram- Mandir to Arrowa section | Construction of 2-Laning with hard shoulder road of Ram- Mandir to Arrowa section of NH-113 from Design Km 0.000 to Km 2.910 (Existing Km 65.080 to Km 67.990) of total length 2.755 km excluding Tidding Bridge (155 m) on EPC mode | SARDP-NE | NH | 113 | 2.755 | - | 2.76 | 46.9 | 19.51 | 2023-09-18 | 2024-03-15 | 2024-06-28 | 100 | 97.79 | 2025-12-28 | Physically Completed C.C Under Issue | 2025-12-28 | GRRB Associates | grrb.tezu.hayuliang@gmail.com | Global Infra Solutions | Normal Highway/Road Project
17 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 150859 | DN/19001/02006/AR | Completed | Completed | Arrowa-Khupa-Hayuliang section | Construction of 2-Laning with hard shoulders of Arrowa-Khupa-Hayuliang section of NH-113 from Ch.68.550 to Ch.91.633 on EPC mode under SARDP-NE (NH(O)-NE) | SARDP-NE | NH | 113 | 23.083 | - | 18.37 | 301.06 | 132.9735 | 2020-07-31 | 2020-08-31 | 2020-10-25 | 100 | 99.76 | 2022-04-27 | - | 2025-04-27 | M. P. (Mahabir Prasad) Agarwala Pvt. Ltd. | mp.arrowa.khupa@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
18 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60025 | DN/19001/02003/AR | Completed | Completed | Hayuliang– Hawai Road Pkg- 1 | 2-Laning with hard shoulders of Khupa-Hayuliang-Hawai Road NH-113 on EPC basis from design Km. 0.000 (Khupa) to Km. 17.000 [Existing Km 95.800 of (Khupa – Hayuliang Road) to Km 8.970 (Hayuliang – Hawai Road)] Pkg - I under SARDP-NE | SARDP-NE | NH | 113 | 17 | - | 17 | 252.05 | 168.3 | 2017-01-25 | 2017-03-23 | 2017-11-10 | 100 | 99.67 | 2020-11-09 | - | 2022-10-19 | Sushee Infra & Mining Limited | susheehayuliang@gmail.com puttakishore333@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
19 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60026 | DN/19001/02004/AR | Completed | Completed | Hayuliang– Hawai Road Pkg- 2 | 2-Laning with hard shoulders of Hayuliang – Hawai Road on EPC basis from design Km. 17.000 (Khupa) to Km. 34.000 [Existing Km 16.950 to Km 34.310 (Hayuliang – Hawai Road)] Pkg - II under SARDP-NE | SARDP-NE | NH | 113 | 17 | - | 17.005 | 252.79 | 168.3 | 2017-02-15 | 2017-03-23 | 2017-11-10 | 100 | 99.75 | 2020-11-08 | - | 2023-01-31 | Sushee Infra & Mining Limited | susheehayuliang@gmail.com puttakishore333@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
20 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60027 | DN/19001/02005/AR | Completed | Completed | Hayuliang– Hawai Road Pkg- 3 | 2-Laning with hard shoulders of Hayuliang – Hawai Road on EPC basis from Design Km. 34.000 to Km. 51.825 [Existing Km 26.625 to Km 45.050 (Hayuliang – Hawai Road)] Pkg - III under SARDP-NE | SARDP-NE | NH | 113 | 17.825 | - | 17.83 | 263.31 | 177.3 | 2017-02-15 | 2017-03-23 | 2017-11-10 | 100 | 99.68 | 2020-11-09 | - | 2023-06-27 | Sushee Infra & Mining Limited | susheehayuliang@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
21 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 151889 | DN/19001/02001/AR | Completed | Completed | Hayuliang– Hawai Road Pkg- 4 | 2-Laning with hard shoulders of Hayuliang– Hawai bypass Road on EPC basis from design Km. 51.825 to Km. 63.131 (Existing Km 45.050 of Hayuliang – Hawai road to Hawai Town) Pkg - IV under SARDP-NE -Balance work | SARDP-NE | NH | 113 | 11.3 | - | 11.07 | 216.76 | 131.91 | 2017-01-25 | 2021-03-31 | 2021-05-03 | 93.1 | 93.1 | 2023-05-02 | - | 2024-12-31 | Poddar Infratech Pvt. Ltd. - GRRB Associates (JV) | poddargrrb@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
22 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 159588 | DN/09013/01010/AR | Ongoing | Under Construction (AD issued) | Hunli to Hayuliang Pkg-1 | Construction of Intermediate Lane with Hard Shoulder of Hunli to Hayuliang (Package-I) from Design Km 0.000 to Km 53.000 (Design Length 53.000 km, Greenfield) Section of Frontier Highway (NH-913) in the State of Arunachal Pradesh on EPC Mode | NH(O)-NE | NH | 913 | 53 | - | 4 | 1262.43 | 518.16 | 2024-02-27 | 2024-12-13 | 2025-03-01 | 18.1 | 15.75 | 2028-02-29 | 2028-03-01 | - | Bhartia Infra Projects Limited(BIPL)-Shivam Transcon Pvt. Ltd. (JV) | shivambhartiajv@gmail.com | JSC Institute Giprostroymost in JV with - Agnitio Infrastructure Projects Pvt. Ltd.(AIPPL) in Association with - Zoma Engineers (JV) | Normal Highway/Road Project
23 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 159342 | DN/09013/01009/AR | Ongoing | Under Construction (AD issued) | Hunli to Hayuliang Pkg-3 | Construction of Intermediate Lane with Hard Shoulder of Hunli to Hayuliang (Package-III) from design Km 60.000 to Km 121.500 (Design Length 61.500 km, Greenfield) Section of Frontier Highway (NH-913) in the State of Arunachal Pradesh on EPC Mode | NH(O)-NE | NH | 913 | 61.5 | - | 0 | 1418.67 | 610 | 2024-02-27 | 2024-10-30 | 2025-07-18 | 1.7 | 1.69 | 2028-07-17 | 2028-07-17 | - | Bhartia Infra Projects Limited(BIPL) | biplpkg003@gmail.com | JSC Institute Giprostroymost in JV with - Agnitio Infrastructure Projects Pvt. Ltd.(AIPPL) in Association with - Zoma Engineers (JV) | Normal Highway/Road Project
24 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 157540 | DN/09013/02001/AR | Ongoing | Under Construction (AD issued) | Hunli to Ithun Bridge section (Frontier Highway) | Construction of Intermediate Lane Road with hard shoulder from design Km 0.000 to Km 17.387 (Total length 17.387 km) of Hunli to Ithun Bridge section on NH-913 (Frontier Highway) in State of Arunachal Pradesh” on EPC mode under NH(O)-NE | NH(O)-NE | NH | 913 | 17.387 | - | 9 | 275.5 | 146.9 | 2024-02-27 | 2024-03-15 | 2025-01-30 | 54.11 | 47.47 | 2027-01-30 | 2027-01-30 | - | J Infratech Limited (JIL) | infojcipl@gmail.com | JSC Institute Giprostroymost in JV with - Agnitio Infrastructure Projects Pvt. Ltd.(AIPPL) in Association with - Zoma Engineers (JV) | Normal Highway/Road Project
25 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | 157541 | DN/09013/03001/AR | Ongoing | Under Construction (AD issued) | Tato to Monigong section (Frontier Highway) | Construction of lntermediate Lane Road with hard shoulder from design chainage Km 0.000 to Km 53.040 (Existing Length:68.500 Km & Total Design length 53.04 km) of Tato to Monigong section of NH-913 (Frontier Highway) on Nafra (Bomdila) to Vijaynagar along China border in state of Arunachal pradesh on EPC mode | NH(O)-NE | NH | 913 | 53.04 | - | 0 | 625.61 | 299.87 | 2023-12-07 | 2024-03-15 | 2025-05-15 | 21.97 | 20.41 | 2027-11-14 | 2027-11-14 | - | ABCI Infrastructures Pvt. Ltd.-Brand Eagles (JV) | abcibe.jv@gmail.com | Agnitio Infrastructure Project Pvt. Ltd. (AIPPL) in JV with - Infrastructure Development Consultants (IDC) (JV) | Normal Highway/Road Project
26 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | AR-1 | DN/09013/04002/AR | Awarded, Not Appointed | Awarded, Not Appointed | Tuting-Zido (Frontier Highway) | Construction of lntermediate Lane Road with hard shoulder from design Km 0.000 to Km 13.080 of Tuting-Zido section on NH-913 (Frontier Highway) on EPC Mode | NH(O)-NE | NH | 913 | 13.08 | - | 0 | 316.44 | 191 | 2024-02-27 | 2026-02-27 | To be given | 0 | 0 | - | - | - | Poddar Infratech Private Limited-GRRB Associates (JV) | info@poddarinfra.com, varun@poddarinfra.com, grrb.ska@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
27 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | 158669 | DN/09013/05001/AR | Ongoing | Under Construction (AD issued) | Pango to Jorging Road Pkg-1 | Construction of Intermediate Lane of Pango to Jorging Road from 0+000 to Design Km Design Km 40+000 (Design Length: 40.00 Km, Pkg-l, Greenfield Alignment) in the State of Arunachal Pradesh on EPC mode (Pkg-1) | NH(O)-NE | NH | 913 | 40 | - | 10 | 898.19 | 426.91 | 2024-01-15 | 2024-09-10 | 2025-01-14 | 39.8 | 37.71 | 2027-07-16 | 2027-07-16 | - | TTC Infra India | ttcii.pango@gmail.com | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
28 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | AR-2 | DN/09013/05002/AR | Awarded, Not Appointed | Awarded, Not Appointed | Pango to Jorging Road Pkg-2 | Construction of Intermediate Lane of Package-Il of Pango to Jorging Road from Design Km 40+000 to Design Km 82+060 (Design Length: 42.06 Km, Greenfield Alignment) in the State of Arunachal Pradesh on EPC Mode (Pkg-2) | NH(O)-NE | NH | 913 | 42.06 | - | 0 | 883.85 | 424.1865 | 2024-01-15 | 2026-02-05 | To be given | 0 | 0 | - | - | - | TTC Infra India | - | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
29 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60032 | DN/19005/01010/AR | Ongoing | Under Construction (AD issued) | Roing -Hunli Road (Green Field alignment) | Construction of 2-lane road from km. 0.00 (Existing km. 16.00 of Roing -Hunli Road) to Km. 74.00 (Ithun Bridge near existing km. 21.50 of Anini Road)-Green Field alignment | SARDP-NE | NH | 313 | 74.86 | - | 65.7 | 1718.59 | 1058.25 | 2017-01-25 | 2017-03-24 | 2018-03-05 | 82.32 | 80.01 | 2022-03-04 | 2026-10-31 | - | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) - Iron Triangle (ITL) (JV) | roymonpm1962@gmail.com | Infrastructure Development Consultants (IDC) - Specialized Engineering Services Pvt. Ltd.- Dracs Consultancy and Construction Pvt. Ltd. (JV) (Re-awarded) | Normal Highway/Road Project
30 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 149013 | DN/19005/01018/AR | Completed | Completed | Strengthening/OTI of Hunli-Anini Road | Rehabilitation/ Restoration (One Time Improvement) of Hunli -Anini Road on NH-313 from km 0.00 to km 21.500 in the State of Arunachal Pradesh on EPC basis | NH(O) | NH | 313 | 21.5 | - | 21.5 | 23.56 | 22.12 | 2019-02-11 | 2019-02-22 | 2019-10-10 | 100 | 100 | 2020-10-09 | - | 2021-01-06 | Nani Mamung Enterprises(NME)-N.M. Enterprises (JV) | n.menterprises.n751@gmail.com | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Normal Highway/Road Project
31 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 154361 | DN/19005/01011/AR | Completed | Physically Completed & CC Under Issue | One Major bridge of span 160 m (Hunli-Anini Road (Pkg.1)-COS work | Construction of 1 Major bridges at Existing Ch. 23+650 (Design Ch. 23+550) of bridge span 160 m along the Existing Hunli-Anini Road (Pkg.1) from Km 21.500 to Km 37.500 on EPC mode | SARDP-NE | NH | 313 | 0.16 | 0.16 | 0.16 | 30 | 60 | 2016-04-25 | 2021-09-28 | 2021-12-17 | 100 | 99.8 | 2023-06-19 | 2026-06-30 | - | Poddar Infratech Pvt. Ltd. | varun@poddarinfra.com | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Standalone MJB(Major Bridge) Project
32 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | AR-3 | DN/19005/01027/AR | Ongoing | Under Construction (AD issued) | One Major bridge of span 216 m (Hunli-Anini Road (Pkg.1)-COS work | Construction of a Major bridge at Design Ch. 28+200 along the Existing Hunli-Anini Road (Pkg.1) from Km 21.500 to Km 37.500 on EPC mode under SARDP | SARDP-NE | NH | 313 | 0.216 | - | 0 | 30 | 28 | 2016-04-25 | 2024-08-08 | 2024-11-18 | 0.35 | 0 | 2027-05-20 | 2027-05-20 | - | North East Engineering & Construction Agency | - | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Standalone MJB(Major Bridge) Project
33 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60014 | DN/19005/01012/AR | Completed | Completed | Hunli-Anini road Pkg-1 | Construction of 2-lane road from design km. 21.50 (Near Ithun Bridge) to Km. 37.500 (existing Km 21.450 to Km 40.160) of Hunli-Anini road in the State of Arunachal Pradesh on EPC basis under SARDP-NE (Pkg.-1) | SARDP-NE | NH | 313 | 16 | - | 15.54 | 318.8 | 235.9232 | 2016-04-25 | 2016-05-06 | 2016-12-21 | 100 | 98.04 | 2019-12-20 | - | 2022-10-15 | Madhucon Projects Limited | gm.bd@madhucon.com | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Normal Highway/Road Project
34 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60031 | DN/19005/01017/AR | Completed | Completed | Hunli-Anini road Pkg-2 | Construction of 2-lane existing Hunli-Anini road from Design km. 37.500 to Km. 53.500 (Existing km 40.160 to 56.320) on EPC basis under SARDP-NE - (Pkg.-2) | SARDP-NE | NH | 313 | 16 | - | 15.25 | 259.52 | 198 | 2016-04-25 | 2016-05-06 | 2016-10-07 | 100 | 71.4 | 2019-10-06 | - | 2019-12-19 | Madhucon Projects Limited | gm.bd@madhucon.com | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Normal Highway/Road Project
35 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60016 | DN/19005/01013/AR | Completed | Completed | Hunli-Anini road Pkg-3 | Construction of 2-lane Hunli-Anini road from Design km 53.500 to km 92.500 (Existing Km 56.320 to Km 97.650) on EPC basis under SARDP-NE - (Pkg.-3) | SARDP-NE | NH | 313 | 39 | - | 39 | 516.7 | 434.06 | 2016-06-20 | 2016-09-12 | 2016-12-16 | 100 | 98.46 | 2019-12-15 | - | 2024-09-15 | Progressive Construction Limited (PCL) -Eagle Infra India Limited (JV) | pcl.etalin@gmail.com | Dhruv Consultancy Services Ltd in Ass. with Agnitio infrastructure projects pvt ltd.(AIPPL) (JV) | Normal Highway/Road Project
36 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60017 | DN/19005/01014/AR | Completed | Completed | Hunli-Anini road Pkg-4 | Construction of 2-lane of Hunli-Anini road from Design Km 92.500 to Km 106.200 (Existing Km 97.670 to Km 111.600) on EPC basis under SARDP-NE - (Pkg.-4) | SARDP-NE | NH | 313 | 13.7 | - | 13.7 | 188.78 | 145.8 | 2016-03-31 | 2016-12-14 | 2017-01-19 | 100 | 99.97 | 2020-01-18 | - | 2022-10-15 | Sushee Infra & Mining Limited | ttc.hapkg6@gmail.com | Lion Engineering Consultants in ass. With Armenge Engg. & management consultants pvt. Ltd. (JV) | Normal Highway/Road Project
37 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60029 | DN/19005/01015/AR | Completed | Completed | Hunli-Anini road Pkg-5 | Construction of 2-lane of Hunli-Anini road from Design km. 106.200 to Km. 120.00 on EPC basis under SARDP-NE - (Pkg.-5) | SARDP-NE | NH | 313 | 13.8 | - | 13.8 | 200.44 | 154.8 | 2016-03-31 | 2016-12-14 | 2017-01-19 | 100 | 99.37 | 2020-01-19 | - | 2023-09-15 | Sushee Infra & Mining Limited | puttakishore333@gmail.com | Lion Engineering Consultants in ass. With Armenge Engg. & management consultants pvt. Ltd. (JV) | Normal Highway/Road Project
38 | DT-1 | NER | Arunachal Pradesh | PMU-Roing | 60030 | DN/19005/01016/AR | Completed | Completed | Hunli-Anini road Pkg-6 | Construction of 2-lane of Hunli-Anini road from Existing km. 120.000 to Km. 130.300 on EPC basis under SARDP-NE - (Pkg.-6) | SARDP-NE | NH | 313 | 10.3 | - | 10.1 | 145.17 | 105 | 2016-03-31 | 2018-03-16 | 2018-06-15 | 100 | 99.94 | 2021-06-14 | - | 2022-07-30 | TTC Infra India | ttc.hapkg6@gmail.com | Lion Engineering Consultants in ass. With Armenge Engg. & management consultants pvt. Ltd. (JV) | Normal Highway/Road Project
39 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | 60020 | DN/19003/01005/AR | Completed | Completed | Akajan-Likabali-Bame Road Pkg-1 | 2-Laning of existing Akajan-Likabali- Bame Road on EPC basis from design Km.12+000 to Km. 33+000 (existing Km.12+000 to Km.36+000) in the state of Arunachal Pradesh under SARDP-NE (Pkg-1) | SARDP-NE | Non NH | State Road | 21 | - | 21 | 210.5 | 148 | 2015-10-16 | 2015-11-02 | 2016-01-20 | 99.84 | 99.34 | 2019-01-18 | - | 2021-11-10 | Jugal Kishore Mahanta Infra works (JKM)-Keti Constructions Limited (KCL) (JV) | jkmlikabali@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
40 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | 151432 | DN/19003/01006/AR | Completed | Completed | Akajan-Likabali-Bame Road Pkg-2 | Construction of Balance work of 2-Laning of existing Akajan-Likabali- Bame Road on EPC basis from design Km 33.00 to Km 65.810 (Existing km 36.00 to km 71.00) in the state of Arunachal Pradesh under SARDP-NE (Pkg-2) | SARDP-NE | Non NH | State Road | 32.81 | - | 32.81 | 263.397 | 93 | 2015-07-22 | 2021-06-30 | 2021-09-01 | 100 | 99.46 | 2023-03-03 | - | 2024-03-31 | MVV Satyanaryana | mvvs.alb2@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
41 | DT-1 | NER | Arunachal Pradesh | PMU-Pasighat (Basar) | 60023 | DN/19003/01004/AR | Completed | Completed | Akajan-Likabali-Bame Road Pkg-3 | Construction of 2-lane with hard shoulder of Akajan-Likabali-Bame road from existing km 71.00 to km 99.00 (Design Km 65.810 to Km 91.928) in the state of Arunachal Pradesh under SARDP-NE (Pkg-3) | SARDP-NE | Non NH | State Road | 26.118 | - | 26.118 | 323.49 | 220.17 | 2017-03-29 | 2017-03-31 | 2018-03-21 | 100 | 100 | 2021-03-19 | - | 2022-12-23 | SCIW-Shivam Transcon Pvt. Ltd. (JV) | sciwshivamjv.nhidcl@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
42 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 63151 | DN/19004/01010/AR | Completed | Completed | Joram – Koloriang Pkg-1 | Construction of 2-Lane with Paved shoulder of Joram – Koloriang Road (NH-713) from design Km. 20+000 to Km. 32+050 (Existing Km 20.000 to Km 35.150) in Arunachal Pradesh on EPC Mode under SARDP-NE (Pkg-1) | SARDP-NE | NH | 713 | 12.05 | - | 12.05 | 175.65 | 102.63 | 2017-02-15 | 2017-03-24 | 2019-04-22 | 100 | 98.8 | 2022-04-20 | - | 2022-02-28 | T.K. Engineering Consortium Pvt. Ltd. (TKECPL)-Brand Eagles(BE) (JV) | debajitdz501@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
43 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 63152 | DN/19004/01009/AR | Completed | Completed | Joram – Koloriang Pkg-2 | Construction of 2-Lane with Paved shoulder of Joram – Koloriang Road (NH-713) from design Km. 32+050 to Km. 44+000 [Existing Km 35.150 to Km 50.050] in Arunachal Pradesh on EPC Mode under SARDP-NE (Pkg-2) | SARDP-NE | NH | 713 | 11.95 | - | 11.95 | 176.22 | 103.48 | 2017-02-15 | 2017-03-24 | 2019-04-22 | 100 | 98.46 | 2022-04-20 | - | 2022-04-09 | T.K. Engineering Consortium Pvt. Ltd. (TKECPL)-Brand Eagles(BE) (JV) | debajitdz501@gmail.com | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
44 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 150992 | DN/19004/01015/AR | Completed | Completed | Joram – Koloriang Pkg-3 | Construction of Balance work of 2-Lane with PS of Joram-Koloriang Road (NH-713) on EPC basis from Design Km 44.989 to Km 61.547 (Existing Km 50.050 to Km 70.000) in the state of Arunachal Pradesh under SARDP-NE (Pkg-3) | SARDP-NE | NH | 713 | 16.558 | - | 16.25 | 228.71 | 100.21 | 2017-02-15 | 2020-08-10 | 2020-10-01 | 99.52 | 98.18 | 2022-04-02 | - | 2024-09-30 | Valecha Engg. Ltd. | contracts@valecha.in | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
45 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 150993 | DN/19004/01013/AR | Completed | Completed | Joram – Koloriang Pkg-4 | Construction of Balance work of 2-Lane with P S of Joram – Koloriang Road (NH-713) on EPC basis from Design Km 61.547 to Km 78.724 (Existing Km 70.000 to Km 88.700) in the state of Arunachal Pradesh under SARDP-NE (Pkg-4) | SARDP-NE | NH | 713 | 17.177 | - | 17.17 | 294.04 | 147.13 | 2017-02-15 | 2020-08-11 | 2020-10-01 | 100 | 98.75 | 2022-04-02 | - | 2024-09-30 | Bhimji Velji Sorathia Construction Pvt. Ltd. | gm.jkroad@bvscpl.in | Highway Engg. Consultant (HEC)-Agnitio Infrastructure project pvt. Ltd (AIPPL ) (JV) | Normal Highway/Road Project
46 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 150994 | DN/19004/01012/AR | Completed | Completed | Joram – Koloriang Pkg-5 | Construction of Balance work of 2-Lane with P S of Joram – Koloriang (NH-713) on EPC basis from existing km 88.700 to 104.850 [Design km. 78.724 to Km 93.724] in the state of Arunachal Pradesh under SARDP-NE (Pkg-5) | SARDP-NE | NH | 713 | 15 | - | 15 | 229.7 | 121.58 | 2017-02-15 | 2020-08-14 | 2020-10-01 | 100 | 99.59 | 2022-04-02 | - | 2023-11-06 | Bhimji Velji Sorathia Construction Pvt. Ltd. | kuvraji@yahoo.com kbh@bvscpl.in gm.jkroad@bvscpl.in | Highway Engg. Consultant (HEC) - Manglam Associates (JV) | Normal Highway/Road Project
47 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 150995 | DN/19004/01011/AR | Completed | Completed | Joram – Koloriang Pkg-6 | Construction of Balance work of 2-Lane with P S of Joram – Koloriang Road (NH-713) on EPC basis from existing km 104.850 to km 122.600 [Design km. 93.724 to km. 108.724] (Design length – 15 km) in the state of Arunachal Pradesh under SARDP-NE (Pkg-6) | SARDP-NE | NH | 713 | 14.6 | - | 14.6 | 199.03 | 110.726 | 2017-02-15 | 2020-08-17 | 2020-10-01 | 100 | 100 | 2022-04-02 | - | 2023-07-31 | Jainco Enterprises Pvt. Ltd. | arunachaljainco@gmail.com jainco.kota@gmail.com | Highway Engg. Consultant (HEC) - Manglam Associates (JV) | Normal Highway/Road Project
48 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 150996 | DN/19004/01016/AR | Completed | Physically Completed & CC Under Issue | Joram – Koloriang Pkg-7 | Construction of Balance work of 2-Lane with PS of Joram – Koloriang Road from existing Km122.600 to km138.00 [Design Km108.724 to Km123.714] in Arunachal Pradesh on EPC Mode under SARDP-NE (Pkg-7) | SARDP-NE | NH | 713 | 14.99 | - | 14.94 | 184.88 | 101.95 | 2017-02-15 | 2020-08-07 | 2020-10-01 | 99.69 | 99.53 | 2022-04-02 | Physically Completed C.C Under Issue | 2026-01-14 | Jainco Enterprises Pvt. Ltd. | Jainco Enterprises <jainco.kota@gmail.com> arunachaljainco@gmail.com | Highway Engg. Consultant (HEC) - Manglam Associates (JV) | Normal Highway/Road Project
49 | DT-1 | NER | Arunachal Pradesh | PMU-Ziro | 153209 | DN/19004/01014/AR | Completed | Completed | Joram – Koloriang Pkg-8 | Construction of Balance Work of 2-Lane with Paved Shoulders of Joram-Koloriang Road (NH-713) on EPC basis from existing km 138.000 to km158.000 [Design km. 122.353 to km. 138.389] (design length – 16.036 km) in the state of Arunachal Pradesh under SARDP-NE (Pkg-8) | SARDP-NE | NH | 713 | 16.035 | - | 15.83 | 244.1 | 94.97 | 2017-02-15 | 2022-03-07 | 2022-05-07 | 96.62 | 95.45 | 2023-11-06 | - | 2024-12-23 | Puna Hinda | Jainco Enterprises <jainco.kota@gmail.com> arunachaljainco@gmail.com | Highway Engg. Consultant (HEC) - Manglam Associates (JV) | Normal Highway/Road Project
50 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60007 | DN/19008/01003/AR | Completed | Completed | Pasighat to Pangin 0 to Km 28 (Section-I) | 2-Laning from Pasighat to Pangin section of NH-229 (New NH-13) from km 0 to Km 28 (Existing Km 1013.85 to Km 1041.85) of 28 Km (Section-I) under SARDP-NE in Arunachal Pradesh on EPC Mode | SARDP-NE | NH | 229/13 | 26.58 | - | 26.58 | 299.66 | 235.08 | 2015-03-30 | 2015-03-31 | 2015-05-27 | 100 | 100 | 2018-05-25 | - | 2018-12-28 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | punahinda@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
51 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60006 | DN/19008/01004/AR | Completed | Completed | Pasighat to Pangin section (Section-III) | 2-Laning from Pasighat to Pangin section of NH-229 (New NH-13) from km 41.3 to 58.420 (Existing Km 982.85 to Km 998.85 of Existing 16Km) (Section-III) under SARDP-NE in Arunachal Pradesh on EPC Mode | SARDP-NE | NH | 229/13 | 17.12 | - | 17.12 | 247.44 | 194.11 | 2015-03-25 | 2015-03-27 | 2015-05-27 | 100 | 99.95 | 2018-05-25 | - | 2020-07-31 | T.K. Engineering Consortium Pvt. Ltd. (TKECPL) | tkeconltd@gmail.com debajitdz501@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
52 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60012 | DN/19010/01002/AR | Completed | Completed | Singer River to Sijon River Section | Construction of 2-Laning of Pasighat-Mariyang-Yingkiong road (New NH-513) from Singer River to Sijon River from 19.880km to 43.257km in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC basis | SARDP-NE | NH | 513 | 23.38 | - | 23.38 | 238.46 | 179.82 | 2015-10-21 | 2015-11-09 | 2016-01-15 | 100 | 100 | 2019-01-19 | - | 2019-07-07 | Ashoka Buildcon Limited (ABL)-Bhartia Infra Projects Limited(BIPL) (JV) | Bipl.tinsukia@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
53 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 60008 | DN/19008/02002/AR | Completed | Completed | Pasighat to Bomjur section | 2-Laning with paved shoulder of NH-52 (New NH-13) from km 583.450 to km 605.600 (Existing chainage from km 583.450 to km 595.000) from Pasighat to Bomjur Road including Re-alignment from km 591.900 to km 602.600 in Arunachal Pradesh under Arunachal Pradesh package of SARDP-NE on EPC Mode | SARDP-NE | NH | 52/13 | 22.15 | - | 22.15 | 244.82 | 155.81 | 2016-01-29 | 2016-03-02 | 2017-02-24 | 100 | 99 | 2020-02-23 | - | 2020-08-10 | Bhartia Infra Projects Limited(BIPL) -Ashoka Buildcon Limited (ABL) (JV ) | Bipl.tinsukia@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
54 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 160163 | DN/19008/03001/AR | Ongoing | Under Construction (AD issued) | Demwe-Brahmakund section | Construction of 2-Laning with hard shoulders of Demwe-Brahmakund section of NH-13 from Ch.0.00 km to 18.464 km on EPC under SARDP-NE (NH(O)-NE) -Balance Work | SARDP-NE | NH | 13 | 18.464 | - | 7 | 353.9 | 140.66 | 2020-08-19 | 2025-03-31 | 2025-06-19 | 19.55 | 16 | 2027-12-18 | 2027-12-18 | - | SPICA Projects & Infrastructures Pvt. Ltd. | spicaprojectspvtltd@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
55 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | AR-4 | DN/19008/03005/AR | Ongoing | Under Construction (AD issued) | Brahmakund T-junction to Kamlang T-Junction (Pkg-1) | lmprovement and Widening to 2-lane with Paved Shoulder of NH-13 & 15 (Old NH-52) from Existing Km 745.60 (Design Km 0.000) to Existing km 770.600 (Design Km 24.819) (Brahmakund T-junction to Kamlang T-Junction, Existing Length: 25.00 Km, Design Length: 24.819 Km) in the state of Arunachal Pradesh on EPC mode (Pkg-1) | NH(O)-NE | NH | 13 & 15 | 24.819 | - | 0 | 441.41 | 159.9 | 2023-12-08 | 2026-03-30 | 2026-06-03 | 0 | 0 | 2028-06-02 | 2028-06-02 | - | J Infratech Limited (JIL) | infojcipl@gmail.com | Technocrats Advisory Services Private Limited (TASPL) in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
56 | DT-1 | NER | Arunachal Pradesh | PMU-Namsai | 160151 | DN/19008/03002/AR | Ongoing | Under Construction (AD issued) | Kamlang T-Junction to Chowkham (Pkg-2) | lmprovement and Widening to 2 lane with paved Shoulder of NH-15 (old NH-52) from Existing Km 770.600 (Design Km 24.819) to Existing km 805.750 (Design Km 59.885) (Kamlang T-Junction to Chowkham, Existing Length: 35.150 Km, Design Length-35.066 Km) in the state of Arunachal Pradesh on EPC mode (Pkg-2) | NH(O)-NE | NH | 52/15 | 35.066 | - | 0 | 316.73 | 106.05 | 2023-12-08 | 2025-03-31 | 2026-02-27 | 0 | 0 | 2028-02-27 | 2028-02-27 | - | Jay Shree International-BK Construction (JV) | jayshreegroupttd@gmait. Com | Technocrats Advisory Services Private Limited (TASPL) in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
57 | DT-1 | NER | Assam | PMU-Silchar | 60052 | DN/09004/01002/AS | Completed | Completed | Strengthening of Chand Khera to Kurti Bridge | Improvement and Strenghtening of Road Section from Chand Khera to Kurti Bridge on NH-208A on (Assam-Tripura Border) in the state of Assam on EPC Mode under NH(O) | NH(O) | NH | 208A | 17.95 | - | 17.95 | 66.94 | 60.21 | 2016-10-27 | 2016-10-04 | 2016-11-28 | 100 | 98 | 2018-01-24 | - | 2018-03-31 | Ganesh Ram Dokania | - | Rodic Consultants Pvt. Ltd. | Normal Highway/Road Project
58 | DT-1 | NER | Assam | PMU-Dibrugarh | 150699 | DN/12017/01001/AS | Completed | Completed | Strengthening/OTI of Moran Town section | One time improvement of Moran Town section of NH-37 from km 555.000 to km 558.500 in Assam on EPC Mode under NH(O) | NH(O) | NH | 37 | 3.5 | - | 3.5 | 14.52 | 13.51 | 2019-02-22 | 2019-05-31 | 2019-08-19 | 100 | 82.1 | 2020-08-17 | - | 2020-12-31 | BB Enterprises | binudborgohain1972@gmail.com | Voyants Solution Pvt Ltd. (VSPL) | Normal Highway/Road Project
59 | DT-1 | NER | Assam | PMU-Dibrugarh | 151237 | DN/12018/01001/AS | Completed | Completed | Strengthening/OTI of Digboi to Ledo Town section | One time improvement of Digboi to Ledo Town section (via Powal and Margherita ) of NH-38 from km 20.000 to km 53.000 in Assam on EPC Mode under NH(O) | NH(O) | NH | 38/315 | 33 | - | 31.5 | 30.84 | 26.93 | 2019-02-22 | 2019-07-29 | 2019-09-25 | 100 | 99.57 | 2020-09-23 | - | 2020-09-03 | Ganpati Builders | ganpatidib@gmail.com op.sharma0082@gmail.com ganpatibuilders0082@gmail.com | Voyants Solution Pvt Ltd. (VSPL) | Normal Highway/Road Project
60 | DT-1 | NER | Assam | PMU-Silchar | 60038 | DN/18003/01001/AS | Completed | Completed | Silchar- Badarpur section (Srikona Railway Level Crossing -RoB) | 2-laning with paved shoulders from km 6.25 to 10.40 including RoB (Railway Over Bridge) at Srikona Railway Level Crossing at km 9.901 of Silchar- Badarpur section of NH-53 in state of Assam under SARDP-NE | SARDP-NE | NH | 53/37 | 4.15 | - | 3.673 | 76.78 | 53.21 | 2015-03-30 | 2015-03-23 | 2015-10-01 | 100 | 98.41 | 2017-12-11 | - | 2022-06-10 | Shree Gautam Construction Company Ltd. | sgcclsilchar@gmail.com | Rodic Consultants Pvt. Ltd. | Standalone RoB (Railway Over Bridge) Project
61 | DT-1 | NER | Assam | PMU-Tezpur | 149360 | DN/19006/01013/AS | Completed | Completed | Nagaon By-pass to Teliagaon | 4-Laning of NH-37 (New NH-127) from Nagaon By-pass to Teliagaon (km 278.600 to km 288.600) in the state of Assam under SARDP-NE Phase-A on EPC mode-Package-1 | SARDP-NE | NH | 37/127 | 10 | - | 10 | 275.66 | 87.11 | 2016-01-14 | 2020-03-23 | 2020-07-01 | 100 | 98.68 | 2021-12-23 | - | 2023-03-09 | PRL Projects & Infra Structure Ltd. | rcplassam1@gmail.com, nagaonnh127@prlinfra.com | STUP Consultants in ass. with Ayoleeza Consultants (JV) | Normal Highway/Road Project
62 | DT-1 | NER | Assam | PMU-Tezpur | 149361 | DN/19006/01014/AS | Completed | Completed | Teliagaon to Rangagara | 4-Laning of NH-37 (New NH-127) from Teliagaon to Rangagara (km 288.600 to km 297.000) in the state of Assam under SARDP-NE Phase-A on EPC mode – Package - 2 | SARDP-NE | NH | 37/127 | 8.4 | - | 8.402 | 170.28 | 66.26 | 2016-01-14 | 2020-03-20 | 2020-07-01 | 100 | 98.18 | 2021-12-23 | - | 2023-03-30 | Ganga Sagar Singh | support@gss.org.in | STUP Consultants in ass. with Ayoleeza Consultants (JV) | Normal Highway/Road Project
62 | DT-1 | NER | Assam | PMU-Tezpur | 60051 | DN/19006/01010/AS | Terminated- To be Reawarded | Terminated- To be Reawarded | Rangagara to Kaliabor Tiniali | 4-Laning from Rangagara to Kaliabor Tiniali (from km 297.00 to km 315.315) of NH-37 (New NH-127) under SARDP-NE, Phase A on EPC Mode in Assam | SARDP-NE | NH | 37/127 | 18.315 | - | 18.322 | 462.88 | 196.24 | 2016-01-12 | 2017-01-16 | 2017-10-23 | 97.13 | 94.82 | 2020-04-21 | - | - | Simplex Infrastructures Ltd. | c3172@simplexinfra.com | STUP Consultants in ass. with Ayoleeza Consultants (JV) | Normal Highway/Road Project
63 | DT-1 | NER | Assam | PMU-Tezpur | 60042 | DN/19006/01015/AS | Completed | Completed | Kaliabor Tiniali to Dolabari Road Junction (including construction of new Brahmaputra Bridge of 3.015Km) | 4-Laning from Km 0.000 (Kaliabor Tiniali road junction) to Km 17.300 (Dolabari Road Junction) including construction of new Brahmaputra Bridge of 3.015Km (from Ch. 9+325 to Ch. 12+365) alongside of existing Kaliabhomora Bridge of NH 37A (New NH-715) on EPC basis under Phase A of SARDP-NE (with Toll Plaza at Ch.7+050) | SARDP-NE | NH | 37A/ 715 | 17.3 | - | 17.265 | 843.62 | 588.95 | 2014-10-31 | 2014-10-31 | 2014-11-29 | 100 | 99.89 | 2018-11-28 | - | 2023-09-30 | Gammon India Ltd.- Satpal (S. P.) Singla construction Pvt. Ltd.[SPSCPL] (JV) | manoj.rathore@gammonengineers.com 9303_newbrahmaputra.planing@ gammonengineers.com | S A Infrastructure Consultant Pvt. Ltd. | Normal Highway/Road Project-(including Bridge)
64 | DT-1 | NER | Assam | PMU-Tezpur | 158117 | DN/19006/01009/AS | Ongoing | Under Construction (AD issued) | Construction of Service Road and RCC Drain on both sides of NH-37A from Kaliabor - Tiniali (Km 0.000) to Kolong Bridge (Km - 0.600) | Construction of Service Road and RCC Drain on both sides of NH-37A from Kaliabor - Tiniali (Km 0.000) to Kolong Bridge (Km - 0.600) in Nagaon district in the state of Assam under EPC mode- COS Work | SARDP-NE | NH | 37A/ 715 | 0.86 | - | 0.84 | 2.99 | 3 | 31-10-2014 | 16-03-2024 | 2024-05-17 | 99.48 | 82.6 | 2024-09-14 | 2026-07-15 | - | Sanjay Kumar Singh | - | STUP Consultants Pvt. Limited in association with Ayoleeza Consultants Pvt Ltd | Normal Highway/Road Project
65 | DT-1 | NER | Assam | PMU-Tezpur | 152733 | DN/19006/01025/AS | Completed | Completed | Dolabari and Jamuguri | 4-Lane highway connecting km 17.300 of old NH-37A (New NH-715) and km 182 of NH-52 (New NH-15) between Dolabari and Jamuguri Section in Assam on EPC basis under SARDP-NE, Phase-A- (Balance work) | SARDP-NE | NH | 37A/715 & 52/15 | 16.862 | - | 16.86 | 592.01 | 124.58 | 2017-03-08 | 2021-11-05 | 2022-02-07 | 100 | 95.02 | 2023-08-08 | - | 2023-12-13 | BN Infra Project LLP | mkcilrsmjv@gmail.com, jatin.s@rsminfra.in, jiabharali.dc@mkcinfrastructureltd.com | TPF Getinsa Euroestudios S.L in association with Rodic Consultant Pvt. Ltd. | Normal Highway/Road Project
66 | DT-1 | NER | Assam | PMU-Tezpur | 151410 | DN/19006/01012/AS | Completed | Completed | 4-L Jia Bharali Bridge on Dolabari-Jamuguri section | Construction of 4-L Jia Bharali Bridge (1.23 Km at km 26+607) along with its approaches and River Training Work from km 25.552 to km 27.500 of NH-37A (New NH-715) (de-scoped portion of Dolabari and Jamuguri section/CoS work) | SARDP-NE | NH | 37A/ 715 | 1.948 | - | 1.94 | 863.49 | 448.03 | 2017-03-08 | 2020-12-21 | 2021-02-17 | 98.03 | 97.34 | 2023-08-05 | - | 2023-12-14 | MKC Infrastructure Ltd. - RSM Infra Projects (JV) | dccindiaproject@gmail.com | TPF Getinsa Euroestudios S.L in association with Rodic Consultant Pvt. Ltd. | Standalone Bridge Project
67 | DT-1 | NER | Assam | PMU-Tezpur | 60044 | DN/19006/01011/AS | Completed | Physically Completed & CC Under Issue | Jamugurihat to end of Biswanath Chariali By-Pass | Up-gradation to 4-Laning of Jamugurihat to end of Biswanath Chariali By-Pass from Km 182.000 to Km 208.000 of NH-52 on EPC mode in state of Assam under SARDP-NE | SARDP-NE | NH | 52/15 | 26 | - | 25.9955 | 735.17 | 303.49 | 2015-03-31 | 2016-10-13 | 2016-12-19 | 100 | 92.1 | 2019-06-19 | Physically Completed C.C Under Issue | 2025-07-30 | T.K. Engineering Consortium Pvt. Ltd. (TKECPL) | info@ganpatibharat | Marc Technocrats Pvt. Ltd. in JV with Bloom Companies LLC (JV) | Normal Highway/Road Project
68 | DT-1 | NER | Assam | PMU-Tezpur | 152731 | DN/19006/01016/AS | Completed | Completed | Biswanath Chariali by-pass to Gohpur | Up-gradation to 4-Laning from end of Biswanath Chariali by-pass (Km 208.000) to Gohpur (Km 265.500) of NH-52 (New NH-15) (Total length 57.50) in the state of Assam on EPC basis Under SARDP-NE (with Toll Plaza at Ch. 219+200) | SARDP-NE | NH | 52/15 | 57.5 | - | 57.5 | 1451.16 | 393.48 | 2015-03-31 | 2021-10-18 | 2021-12-11 | 100 | 98.41 | 2023-06-14 | - | 2023-12-15 | Dhatarwal Construction Company Pvt. Ltd. | babulsayan@gmail.com ,babulnath40@gmail.com dolabari.jamuguri@gmail.com | Marc Technocrats Pvt. Ltd. in JV with Bloom Companies LLC (JV) | Normal Highway/Road Project
69 | DT-1 | NER | Assam | PMU-Tezpur | 60034 | DN/19006/01017/AS | Completed | Completed | Gohpur to Holongi | Up-gradation to 4-Laning of NH-52A from Gohpur (Km 264.100 on NH-52) to Holongi (Km.20.370 on NH-52A) in Assam on EPC under SARDP-NE | SARDP-NE | NH | 52A/415 | 10.08 | - | 9.4715 | 429.91 | 168.4 | 2015-03-31 | 2015-03-30 | 2015-12-11 | 100 | 98.38 | 2018-12-10 | - | 2022-10-31 | ECI Engineering & Constr. Co. Ltd. | pmgohpur@eciecc.com ecigohpur@gmail.com | Marc Technocrats Pvt. Ltd. in JV with Bloom Companies LLC (JV) | Normal Highway/Road Project
69 | DT-1 | NER | Assam | PMU-Tezpur | AS-2 | DN/09026/01002/AS | Sanctioned not awarded | Sanctioned not awarded | 4-L Road cum Rail Underwater Tunnel connecting Gohupur (on Norh Bank) on NH-15 and Numaligarh (on South Bank) on NH-715 across river Brahmaputra in Assam | Construction of 4-Lane Access Controlled Greenfield Twin Tube Road cum Rail Underwater Tunnel under River Brahmaputra, including 4 Lane approaches along with provision of Railway infrastructure in one of the tubes, in the state of Assam on EPC Mode with total length of project as 33.7 Km under NH(O) | NH(O) | NH | Connecting NH-15 & NH-715 | 33.7 | - | 0 | 18662.02 | 0 | 2026-03-11 | - | - | - | - | - | - | - | To be Awarded | - | - | Standalone Tunnel Project
70 | DT-1 | NER | Assam | PMU-Jorhat | 60039 | DN/19007/05002/AS | Completed | Completed | Numaligarh to Jorhat section | 4-Laning of Numaligarh to Jorhat section from Km. 402.500 to Km. 453.000 (Design Km 403.200 to Km 454.240) of NH-37 except construction of Dergaon bypass from Km 426.800 to Km 437.420 (Design Km 427.400 to 438.720) in Assam on EPC mode under SARDP-NE Phase-A (with Toll Plaza at Ch. 424+400 near Rangamati) | SARDP-NE | NH | 37/ 715 | 39.72 | - | 39.72 | 1655.44 | 454.89 | 2014-10-31 | 2014-10-31 | 2015-05-23 | 99.3 | 98.39 | 2018-05-22 | - | 2024-03-15 | Hindustan Construction Company (HCC) | njrp.pd@hccindia.com, njrp.qclab@hccindia.com, njrp@hccindia.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Normal Highway/Road Project
71 | DT-1 | NER | Assam | PMU-Jorhat | 149353 | DN/19007/05001/AS | Completed | Completed | Dergaon Town section on Numaligarh to Jorhat section | Rehabilitation & up-gradation to 4-Lane with Paved shoulder of Dergaon Town section from Km 426.800 to Km 437.400 on NH-37(New NH-715) in Assam on EPC basis | SARDP-NE | NH | 37/ 715 | 10.6 | - | 10.6 | 426.15 | 121.89 | 2020-01-10 | 2020-03-19 | 2020-06-30 | 100 | 97.63 | 2022-06-19 | - | 2024-02-29 | Rajinder Infrastructure Pvt.Ltd. | jornh37@gmail.com ripl.chd@gmail.com | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
71 | DT-1 | NER | Assam | PMU-Jorhat | 157352 | DN/19007/01012/AS | Terminated- To be Reawarded | Terminated- To be Reawarded | Jorhat to Jhanji section Pkg-1 | Construction of Balance Work of 4-Laning of the Section from Jorhat to Jhanji of NH-37 (Old): Pkg-I: Road Works from Km 453+000 to Km 463+000 (10.000 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 715 | 10 | - | 31.746 | 478.3 | 102.67 | 2014-10-31 | 2024-01-15 | 2024-02-14 | 96.79 | 93.18 | 2024-08-11 | - | - | Sadguru Engineers & Allied Services Pvt. Ltd. | seaspvtltdghy@gmail.com | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
71 | DT-1 | NER | Assam | PMU-Jorhat | 157353 | DN/19007/04002/AS | Terminated- To be Reawarded | Terminated- To be Reawarded | Jorhat to Jhanji section Pkg-2 | Construction of Balance Work of the 4-Laning of the Section from Jorhat to Jhanji of NH-37 (Old): Pkg-II: Road Works from Km 463.00 to Km 477.000 (14.000 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 715 | 14 | - | 3.15 | 438.44 | 0 | 2014-10-31 | Terminated (To be Re-awarded-5) | - | - | - | - | - | - | To be Re-awarded | - | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
72 | DT-1 | NER | Assam | PMU-Jorhat | 157354 | DN/19007/04001/AS | Completed | Physically Completed & CC Under Issue | Jorhat to Jhanji section Pkg-3 | Construction of Balance Work of the 4-Laning of the Section from Jorhat to Jhanji of NH-37 (Old): Pkg-III: Road Works from Km 477.000 to Km 490+800 (13.800 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 715 | 13.8 | - | 2.91 | 358.72 | 85.9153 | 2014-10-31 | 2024-01-15 | 2024-02-14 | 100 | 98.79 | 2024-08-11 | 2026-06-30 | 2026-02-28 | M. P. (Mahabir Prasad) Agarwala Pvt. Ltd. | mpagarwalapvtltd@gmail.com | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
72 | DT-1 | NER | Assam | PMU-Jorhat | 157357 | DN/19007/04003/AS | Terminated- To be Reawarded | Terminated- To be Reawarded | Jorhat to Jhanji section Pkg-4 | Construction of Balance Work of the 4-Laning of the Section from Jorhat to Jhanji of NH-37 (Old) from Km 453.000 to Km 490.800, under SARDP- NE , under EPC Mode in the state of Assam : Pkg-IV (Structures & Toll Plaza) | SARDP-NE | NH | 37/ 715 | - | - | 0 | 279.01 | 63 | 2014-10-31 | 2024-01-15 | 2024-02-14 | 94.73 | 92.35 | 2024-08-11 | - | - | Sadguru Engineers & Allied Services Pvt. Ltd. | seaspvtltdghy@gmail.com | MSV International in ass. with - Agnitio Infrastructure project pvt. Ltd. (MSV - AIPPL) (JV) | Standalone Structure Project
73 | DT-1 | NER | Assam | PMU-Jorhat | AS-3 | DN/19007/04006/AS | Ongoing | Under Construction (AD issued) | Improvement of riding quality of the selected sections of Jorhat-Jhanji | Improvement of riding quality, Repair, Maintenance of the selected sections of Jorhat-Jhanji on NH-37(Old) in the State of Assam in FY:25-26 | SARDP-NE | NH | 37/ 715 | 17.397 | - | 1.1 | - | 85.56 | 2014-10-31 | 2026-01-30 | 2026-02-22 | 3.67 | 0 | 2026-08-21 | 2026-08-21 | - | J Infratech Limited (JIL) | - | - | Normal Highway/Road Project
74 | DT-1 | NER | Assam | PMU-Jorhat | 158522 | DN/19007/03004/AS | Ongoing | Under Construction (AD issued) | Jhanji to Demow Pkg-1 | Construction of Balance Work of 4-Laning of the Section from Jhanji to Demow of NH-37 (Old): Pkg-I: Road Works from Km 490.800 to Km 501.800 (11.000 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 2 | 11 | - | 31.168 | 476.5 | 91.86 | 2014-10-31 | 2024-08-06 | 2024-10-03 | 87.33 | 84.68 | 2025-09-28 | 2026-07-31 | - | Regal Enterprises | regaljdpkg1@gmail.com regal.jitender@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
75 | DT-1 | NER | Assam | PMU-Jorhat | 158527 | DN/19007/03003/AS | Ongoing | Under Construction (AD issued) | Jhanji to Demow Pkg-2 | Construction of Balance Work of 4-Laning of the Section from Jhanji to Demow of NH-37 (Old): Pkg-II: Road Works from Km 501.800 to Km 514.800 (13.000 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 2 | 13 | - | 5.44 | 542.87 | 99.91 | 2014-10-31 | 2024-08-06 | 2024-10-10 | 73.88 | 70.79 | 2025-10-05 | 2026-07-31 | - | Bharat Vanijya Eastern Pvt. Ltd.(BVEPL) | contact@bvepl.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
76 | DT-1 | NER | Assam | PMU-Jorhat | 158526 | DN/19007/03002/AS | Ongoing | Under Construction (AD issued) | Jhanji to Demow Pkg-3 | Construction of Balance Work of 4-Laning of the Section from Jhanji to Demow of NH-37 (Old): Pkg-III: Road Works from Km 514.800 to Km 534.800 (20.000 Km), under SARDP- NE under EPC Mode in the state of Assam | SARDP-NE | NH | 37/ 2 | 20 | - | 5.72 | 619.7 | 67.69 | 2014-10-31 | 2024-08-06 | 2024-10-03 | 72 | 69.56 | 2025-09-28 | 2026-07-31 | - | Kaushal Sharma | ksharma.tsk@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
77 | DT-1 | NER | Assam | PMU-Jorhat | 158549 | DN/19007/03001/AS | Ongoing | Under Construction (AD issued) | Jhanji to Demow Pkg-4 (Structure) | Construction of Balance Work of 4-Laning of the Section from Jhanji to Demow of NH-37 (Old): Pkg- IV: (Structures & Toll Plaza) from Km 490.800 to Km 534.800, under SARDP- NE , under EPC Mode in the state of Assam (with Toll Plaza at Ch.525.245) | SARDP-NE | NH | 37/ 2 | - | - | 0 | 100.22 | 36.74 | 2014-10-31 | 2024-08-19 | 2024-10-18 | 58.19 | 46.39 | 2025-10-13 | 2026-07-31 | - | Bhardwaj Unibuild Pvt. Ltd. | bupljd4@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Standalone Structure Project
78 | DT-1 | NER | Assam | PMU-Jorhat | AS-4 | DN/19007/03008/AS | Ongoing | Under Construction (AD issued) | 2 Major Bridges (on Jhanji to Demow Pkg-4) | Construction of 2 Nos. of Major Bridge at Km. 508.414 and Km. 523.271 in Jhanji to Demow section of NH-37 (Old) in State of Assam in FY: 25-26 on Item Rate basis | SARDP-NE | NH | 37/ 2 | 0.296 | - | 0 | 0 | 33.5265 | 2014-10-31 | 2025-11-12 | 2025-12-06 | 20.35 | 13.28 | 2026-05-05 | 2026-12-31 | - | Ganpati Bharat Private Limited | info@ganpatibharat.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Standalone MJB(Major Bridge) Project
79 | DT-1 | NER | Assam | PMU-Jorhat | AS-5 | DN/19007/03009/AS | Ongoing | Under Construction (AD issued) | Reconstruction of selected stretches (on Jhanji to Demow Pkg-4) | Reconstruction of selected stretches between Km 514.360 and Km 534.800 of Jhanji to Demow section of NH-37(Old) in State of Assam in FY 25- 26 on Item Rate basis | SARDP-NE | NH | 37/ 2 | 7.927 | - | 5.83 | 0 | 116.44 | 2014-10-31 | 2025-10-13 | 2025-11-13 | 58.16 | 53.84 | 2026-02-13 | 2026-07-31 | - | J Infratech Limited (JIL) | infojcipl@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
80 | DT-1 | NER | Assam | PMU-Dibrugarh | 154230 | DN/19007/01011/AS | Completed | Physically Completed & CC Under Issue | Demow to End of Moran Bypass | 4-Laning of NH-37 Section between Demow to End of Moran Bypass (From Km. 534.800 to Km. 561.700) including Emergency Landing Facility (ELF) under SARDP-NE, Phase 'A' in the State of Assam on EPC mode | SARDP-NE | NH | 37/ 2 | 26.9 | - | 26.9 | 385.57 | 122.5 | 2016-01-14 | 2022-10-14 | 2023-01-20 | 100 | 98.21 | 2024-07-20 | Physically Completed C.C Under Issue | 2025-07-14 | Mohan Lal Jain | msmljaindurgapur@yahoo.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
81 | DT-1 | NER | Assam | PMU-Dibrugarh | 158467 | DN/19007/01009/AS | Completed | Physically Completed & CC Under Issue | End of Moran Bypass to Bogibeel junction Pkg-1 | Construction of Balance Work of 4-Laning of NH-37 Section between End of Moran Bypass to Bogibeel junction near Lapetketa ((Km. 561.700-Km. 580.875) under SARDP-NE, Phase 'A' in the State of Assam on EPC mode Pkg-I: Road works & Toll Plaza | SARDP-NE | NH | 37/ 2 | 19.175 | - | 19.18 | 274.34 | 96.89 | 2016-01-12 | 2024-07-26 | 2024-09-16 | 100 | 96.21 | 2025-03-14 | Physically Completed C.C Under Issue | 2025-08-11 | Mohan Lal Jain | mljmobohw@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
82 | DT-1 | NER | Assam | PMU-Dibrugarh | 158464 | DN/19007/01010/AS | Completed | Physically Completed & CC Under Issue | End of Moran Bypass to Bogibeel junction Pkg-2 (Structure) | Construction of Balance Work of 4-Laning of NH-37 Section between End of Moran Bypass to Bogibeel junction near Lapetketa ((Km. 561.700-Km. 580.875) under SARDP-NE, Phase 'A' in the State of Assam on EPC mode Pkg-II: Structures | SARDP-NE | NH | 37/ 2 | 0 | - | 0 | 55.96 | 43.82 | 2016-01-12 | 2024-07-26 | 2024-09-16 | 100 | 98.05 | 2025-03-14 | Physically Completed C.C Under Issue | 2025-08-12 | Mehta Construction Co. | mccmobostr@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Standalone Structure Project
83 | DT-1 | NER | Assam | PMU-Dibrugarh | 60036 | DN/19007/02002/AS | Completed | Completed | Dibrugarh ByPass | Construction of 2-L Dibrugarh By Pass / realignment of NH-37 from Bogibeel Junction at km. 581.700 to km. 597.147 on EPC basis in the state of Assam under SARDP-NE | SARDP-NE | NH | 37/ 15 | 15.447 | - | 15.447 | 379.32 | 96.84 | 2015-02-25 | 2015-02-20 | 2015-11-02 | 100 | 99.9 | 2018-10-31 | - | 2020-10-31 | ABCI Infrastructures Pvt. Ltd.-Jugal Kishore Mahanta Infra works LLP (JKM) (JV) | jkmdbrproject@gmail.com jkmdibrugarhbypass@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
84 | DT-1 | NER | Assam | PMU-Silchar | 60048 | DN/09012/01002/AS | Completed | Completed | Balachera-Harangjao section | 4-Laning of Balachera-Harangjao section of NH-54 (ext.) (New NH-27) from km 275.00 to km 244.00 in the state of Assam on EPC mode under East-West corridor project under NHDP-II | NHDP-II | NH | 54 Ext./ 27 | 25.25 | - | 25.25 | 887.68 | 519.3 | 2017-09-08 | 2017-10-31 | 2017-12-26 | 100 | 99.24 | 2020-06-24 | - | 2024-04-15 | Sushee Infra & Mining Limited - JSC Purpetruboprovodstroy (JSC PTPS) (JV) | planning.balachera@gmail.com | Rodic Consultants Pvt. Ltd. | Normal Highway/Road Project
85 | DT-1 | NER | Assam | PMU-Bongaigaon | 149300 | DN/01001/02001/AS | Completed | Physically Completed & CC Under Issue | Hapachara to Tulungia road | Construction and up gradation to 4-Lane of existing two lane with paved shoulder from Hapachara to Tulungia road of NH-117 of existing Km 0.00 to km 14.050 and (Design Km 0.000 to km 14.660), (Design length- 14.660 km) under BMP | NH(O)-NE | NH | 31/ 117 | 14.66 | - | 14.6605 | 224.85 | 138.25 | 2020-03-17 | 2020-03-26 | 2020-06-26 | 97.76 | 93.19 | 2022-12-26 | Physically Completed C.C Under Issue | 2024-06-30 | B.K.Sons Infra Pvt. Ltd. | info@bksonsinfra.com | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
86 | DT-1 | NER | Assam | PMU-Dhubri | 157469 | DN/01001/01019/AS | Ongoing | Under Construction (AD issued) | Bilasipara- Guwahati road Pkg-1 | Widening/lmprovement to 4-Lane with Paved Shoulder from Ch.5.580 Km to Ch.25.633 Km (Design Ch.0.000 Km to Ch.17.737km) (Km 901.100 to Km 921.145 of old NH-31) of Bilasipara- Guwahati road (NH-17) (Section: Near Chirakuta to near Mowatari, before Chapar Bypass) in the state ol Assam on HAM mode (Package-1) | NH(O)-NE | NH | 31/17 | 17.737 | - | 4.1 | 1081.15 | 575 | 2024-02-07 | 2024-03-11 | 2025-02-05 | 30.8 | 14 | 2027-08-04 | 2027-08-04 | - | Bilasipara Guwahati Pvt. Ltd. | finance@bhartiainfra.com | Agnitio Infrastructure Projects Pvt. Ltd (AIPPL) - Ayoleeza Consultants Private Limited (JV) | Normal Highway/Road Project
87 | DT-1 | NER | Assam | PMU-Bongaigaon | 157470 | DN/01001/01018/AS | Ongoing | Under Construction (AD issued) | Bilasipara- Guwahati road Pkg-2 | Widening/ improvement to 4-Lane with paved Shoulder from Ch. 25.633 Km to Ch. 52.470 Km (Design Ch. 21.850 Km to Ch.48.670 Km) for Package-2 of Bilasipura- Guwahati road (NH-17) (Section: Near Mowatari, before Chapar Bypass to Tulungia (junction with NH-17)) in the state of Assam on HAM mode under NH(O)-NE (Pkg-2) | NH(O)-NE | NH | 31/17 | 26.82 | - | 0 | 1338.61 | 759.18 | 2023-11-30 | 2024-03-11 | 2024-12-05 | 12.45 | 5 | 2027-06-03 | 2027-06-03 | - | Naresh Kumar Garg Infrastructure Ltd. (NKG)-Mowatari Guwahati Road Pvt. Ltd. | nkg@nkginfra.com | MSV International Inc in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
88 | DT-1 | NER | Assam | PMU-Bongaigaon | 151637 | DN/01001/01017/AS | Completed | Completed | Tulungia-Jogighopa Bridge Approach Section (on Bilasipara- Guwahati road) (Package-5) | Widening/Improvement to 4 -Lane with Paved Shoulder from Ch. 52.470km to Ch.71.500 km (Design Ch.48.655km to Ch.67.556km)of Tulungia-Jogighopa Bridge Approach Section of Bilasipura- Guwahati road (NH 17) on EPC (Package-5) | NH(O)-NE | NH | 31/17 | 18.9 | - | 18.88 | 691.53 | 418.49 | 2021-03-31 | 2021-03-22 | 2021-07-09 | 99.47 | 99.14 | 2022-12-31 | - | 2024-01-31 | Rajendra Singh Bhamboo Infra Pvt. Ltd. | rajendrabhamboo@yahoo.co.in | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
89 | DT-1 | NER | Assam | PMU-Bongaigaon | 152291 | DN/01001/01015/AS | Ongoing | Under Construction (AD issued) | Jogighopa Bridge | Construction of New 2-Lane EXTRADOSED CABLE STAYED Bridge with its approaches from km 0+000 to Km 4+385 across River Brahmaputra on NH-17 at Jogighopa in Assam on EPC mode | NH(O)-NE | NH | 31/17 | 4.385 | - | 1.33 | 746.76 | 402.75 | 2021-09-09 | 2021-08-10 | 2021-11-12 | 81.07 | 79.62 | 2024-11-10 | 2026-12-18 | - | Satpal (S. P.) Singla construction Pvt. Ltd.[SPSCPL] | spsjogighopa@spsingla.com | Chaitanya Projects in ass. - Shree Bhawani (JV) | Standalone Bridge Project
90 | DT-1 | NER | Assam | PMU-Bongaigaon | 150559 | DN/01001/01016/AS | Completed | Completed | Bilasipara- Guwahati road Pkg-6 | Widening/Improvement to 4-Lane with paved shoulder from Ch.75.330Km to Ch.88.00km (Design Ch.71.800 to 84.100 km) of Jogighopa Bridge Approach (Near Pancharatna)- Agia (near Nichinta) section of Bilasipura-Guwahati road (NH-17) on EPC under BMP (Pkg. 6) 1 Toll Plaza at (Ch73+750 Km) | NH(O)-NE | NH | 31/17 | 11.78 | - | 11.7785 | 203.2 | 114.31 | 2020-07-07 | 2020-08-25 | 2020-10-26 | 100 | 99.61 | 2022-04-19 | - | 2024-07-06 | Mayasheel Construction | msc.pkg6@gmail.com | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
91 | DT-1 | NER | Assam | PMU-Bongaigaon | 155196 | DN/01001/01014/AS | Completed | Completed | Bilasipara- Guwahati road Pkg-7 | Widening/Improvement to 4 -Lane with Paved Shoulder from Ch. 88.000km to Ch.99.930 km (Design Ch.84.100km to Ch.96.000 km) of Sagunbashi forest (near Nichinta) to starting of Krishnai Bypass Section (Package-7) of Bilasipura Guwahati road (NH 17) | NH(O)-NE | NH | 31/17 | 11.9 | - | 11.9 | 286.72 | 135.89 | 2021-03-30 | 2023-03-24 | 2023-10-25 | 100 | 95.45 | 2025-10-25 | - | 2025-08-12 | Mayasheel Construction | msc.pkg7@gmail.com | Marc Technocrates Pvt. Ltd | Normal Highway/Road Project
92 | DT-1 | NER | Assam | PMU-Bongaigaon | 155081 | DN/01001/01013/AS | Ongoing | Under Construction (AD issued) | Bilasipara- Guwahati road Pkg-8 | Widening/Improvement to 4-Lane with paved shoulder from Km 99+930 to Km 143+680 (Design Chainage 96+000 to 139+750) of (Paikan to Dhupdhara Sahar) of Bilasipura-Guwahati Road on NH-17 in the state of Assam on EPC mode under Bharatmala Pariyojana in Economic Corridors (Project Length – 43.750km) under NH(O)-NE (Package-8) | NH(O)-NE | NH | 31/17 | 43.75 | - | 27.97 | 1457.59 | 795.1275 | 2023-03-07 | 2023-03-14 | 2023-12-27 | 84.39 | 79.29 | 2026-12-25 | 2026-12-25 | - | YFC Projects Pvt. Ltd. - TTC Infra India (JV) | ttcii.bg.pkg8@gmail.com | Indian Technocrat Ltd. (ITL)- Mspark Futuristics in assn. with imaGIS Engg. (JV) | Normal Highway/Road Project
93 | DT-1 | NER | Assam | PMU-Boko-SO | 155106 | DN/01001/01012/AS | Ongoing | Under Construction (AD issued) | Bilasipara- Guwahati road Pkg-9 | Widening/Improvement to 4-Lane with Paved Shoulder from Ch. 143+680km to Ch.177+372km (Design Ch.139+750km to Ch.173+434km) of Bilasipura- Guwahati road on NH-17 (Section: Dhupdhara Sahar to Milmila Reserve Forest (before Chayagaon Market)) in the state of Assam on EPC mode under Bharatmala Pariyojana in Economic Corridors (Project Length – 33.684km) NH(O)-NE (Package-9) | NH(O)-NE | NH | 31/17 | 33.684 | - | 23.52 | 1000.27 | 458.47 | 2023-03-07 | 2023-03-20 | 2023-12-11 | 57.46 | 45.64 | 2026-06-11 | 2027-03-31 | - | ANIL Das - SAILAJA Commercial Construction Pvt. Ltd. (JV) | anilsailajaprojects@gmail.com | K&J Projects Pvt. Ltd. In association with Mahamarg Infra Consultants Pvt. Ltd. (JV) | Normal Highway/Road Project
94 | DT-1 | NER | Assam | PMU-Boko-SO | 155294 | DN/01001/01011/AS | Ongoing | Under Construction (AD issued) | Bilasipara- Guwahati road Pkg-10 | Widening/Improvement to 4-Lane with Paved Shoulder from Ch. 177+372km to Ch.203+783km (Design Ch.173+434km to Ch.200+750km) of Bilasipura- Guwahati road (NH 17) (Section: Milmila R.F (before Chayagaon Market) to Approach of Airport Junction (VIP Chowk) in the State of Assam on EPC mode under Bharatmala Pariyojana in Economic Corridors (Project Length - 27.316km) for (Package-10) | NH(O)-NE | NH | 31/17 | 27.31 | - | 15.37 | 1264.9 | 593.93 | 2023-03-31 | 2023-03-31 | 2023-12-18 | 63.15 | 42.05 | 2026-06-18 | 2027-03-31 | - | ANIL Das - SAILAJA Commercial Construction Pvt. Ltd. (JV) | anilsailajaprojectspkg10@gmail.com | K&J Projects Pvt. Ltd. In association with Mahamarg Infra Consultants Pvt. Ltd. (JV) | Normal Highway/Road Project
95 | DT-1 | NER | Assam | PMU-Diphu | 155006 | DN/01017/01002/AS | Completed | Physically Completed & CC Under Issue | Daboka Bypass of Daboka – Parokhaowa Pkg-1 | Widening/Improvement to 4-Lane with Paved Shoulder from KM 38+500 to Km 51+246 (Design Chainage 38+500 to 50+959) with proposed Daboka Bypass of Daboka – Parokhaowa of NH 29 under NH(O)-NE (Package-1) | NH(O)-NE | NH | 29 | 12.459 | - | 12.46 | 516.88 | 229.82 | 2023-01-05 | 2023-02-24 | 2023-11-30 | 99.7 | 97.26 | 2025-11-29 | 2026-06-25 | - | Mehta Construction Co. | mehtapkg1nh29@gmail.com | Mspark Futuristics & Associates in JV with Indian Technocrat Ltd. (ITL) and in association with imaGIS Engineering Solutions Pvt. Ltd. (JV) | Normal Highway/Road Project
96 | DT-1 | NER | Assam | PMU-Diphu | 151703 | DN/01017/01006/AS | Completed | Completed | Parokhuwa-Dokmoka section Pkg-2 | Widening/lmprovement to 4-Lane with paved shoulders from Km. 51+246 to Km. 66+000 (Design Chainage 50+710 Km to 65+923 Km) of Parokhuwa-Dokmoka section of NH-29 in the state of Assam under Bharatmala Pariyojana on EPC mode (Package-2) | NH(O)-NE | NH | 29 | 15.213 | - | 13.3005 | 257.5 | 138.33 | 2021-03-31 | 2021-03-26 | 2021-07-12 | 89.35 | 87.83 | 2023-01-03 | - | 2023-04-30 | P.D. Agrawal Infrastructure Ltd. -Apex Structure Pvt Ltd. (JV) | apexcompany2009@yahoo.in | Bloom Companies LLC - JR Consultancy (JV) | Normal Highway/Road Project
97 | DT-1 | NER | Assam | PMU-Diphu | 150844 | DN/01017/01003/AS | Completed | Completed | Dokmoka - Loring Thepi section Pkg-3 | Widening/Improvement to 4-Lane with Paved shoulder from km 66.00 to km 81.00 (Design Chainage 65.923 to 80.930) of Dokmoka - LoringThepi section- (Package-3) | NH(O)-NE | NH | 29 | 15.007 | - | 15.011 | 266.26 | 129.14 | 2020-07-13 | 2020-08-10 | 2020-09-30 | 100 | 97.38 | 2022-03-24 | - | 2022-12-27 | Skylark Infra Engg. Pvt. Ltd. | pm.dokmoka@skylarkworld.com | K&J Projects Private Limited | Normal Highway/Road Project
98 | DT-1 | NER | Assam | PMU-Diphu | 151433 | DN/01017/01004/AS | Completed | Completed | Loring Thepi - Ganapath Gaur Gaon Section - (Package-4) | Widening/Improvement to 4-Lane with Paved Shoulder from km 81+000 to km 95+400 (Design Chainage 80+930 to 96+400) of Loring Thepi - Ganapath Gaur Gaon Section in the state of Assam under Bharatmala Pariyojana on EPC mode (Package-4) | NH(O)-NE | NH | 29 | 15.47 | - | 14.7165 | 260.07 | 141.35 | 2021-02-12 | 2021-02-03 | 2021-06-25 | 96.18 | 96.07 | 2022-12-17 | - | 2023-03-29 | S S Builders | ssbuilderspkg4@gmail.com, | K&J Projects Private Limited | Normal Highway/Road Project
99 | DT-1 | NER | Assam | PMU-Diphu | 151704 | DN/01017/01005/AS | Completed | Completed | Ganpath Gaur Gaon- Kwaram Taro Vitlage- Pkg-5 | Widening/lmprovement to 4-Lane of Daboka Dimapur Stretch from Km 95+400 to Km 113+830 (Design Chainage 96+400 Km to 113+830 Km) of Ganpath Gaur Gaon- Kwaram Taro Vitlage in the state of Assam under Bharatmala Pariyojana on EPC mode (Package-5) | NH(O)-NE | NH | 29 | 17.43 | - | 17.43 | 288.85 | 141.46 | 2021-03-31 | 2021-03-31 | 2021-07-12 | 100 | 99.41 | 2023-01-12 | - | 2024-11-19 | B.K.Sons Infra Pvt. Ltd. | info@bksonsinfra.com | Technocrats Advisory Services Private Limited(TASPL) in association with - Abhishira Infrastructure Consultants Private Limited (JV) | Normal Highway/Road Project
100 | DT-1 | NER | Assam | PMU-Diphu | 152336 | DN/01017/01010/AS | Completed | Completed | Kwaram Taro Village - Dillai Section Pkg-6 | Widening/Improvement to 4-Lane with Paved Shoulder from KM 113+300 to Km 146+230 (Design Chainage 113+830 to 145+712) of Kwaram Taro Village - Dillai Section (Package-6) | NH(O)-NE | NH | 29 | 31.88 | - | 31.88 | 625.64 | 282.11 | 2021-09-09 | 2021-09-10 | 2022-07-14 | 100 | 98.11 | 2024-07-13 | - | 2025-03-31 | Ashoka Buildcon Limited (ABL) | ablnh29pkg6@ashokabuildcon.in | Chaitanya Projects Consultancy Pvt. Ltd. - MAV Associates (JV) | Normal Highway/Road Project
101 | DT-1 | NER | Assam | PMU-Diphu | 153923 | DN/01017/01011/AS | Ongoing | Under Construction (AD issued) | Dillai - Lahorijan Pkg- 7 | Widening/lmprovement to 4-Lane with Paved Shoulder from Dillai at Km 146+230 to Lahorijan at Km 157+46O (Design Chainage 145+712 to 156+502) of Dillai - Lahorijan NH-29 (Package - 7) -Balance Work on Item Rate Basis in FY-25-26 | NH(O)-NE | NH | 29 | 10.79 | - | 10.04 | 204.1 | 9.477 | 2021-11-23 | 2026-01-08 | 2026-02-28 | 0 | 0 | 2026-05-28 | 2026-07-31 | - | Ecova at RISK &COST of the EPC contractor | ecovaindia@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - MAV Associates (JV) | Normal Highway/Road Project
102 | DT-1 | NER | Assam | PMU-Dhubri | 151239 | DN/05003/01007/AS | Ongoing | Under Construction (AD issued) | Dhubri - Phulbari Bridge | Construction of 4-Lane Bridge including approaches over River Brahmaputra between Dhubri (on North Bank,Assam) and Phulbari (on south Bank,Meghalaya) on NH-127B under JICA ODA Loan assistance (Phase-III) | EAP (JICA) | NH | 127B | 19.282 | 1.02 | 9.08 | 4997.04 | 3166 | 2019-05-06 | 2020-11-24 | 2020-12-15 | 76.01 | 73.96 | 2028-09-12 | 2028-09-12 | - | Larsen & Toubro Ltd. Heavy Civil Infrastructure IC Larsen & Toubro Ltd.(L&T) | dpbplnt@gmail.com | AECOM Asia Company Ltd. - PADECO Co. Ltd. (JV) | Standalone Bridge Project
103 | DT-1 | NER | Assam | PMU-Dhubri | 158630 | DN/05003/01005/AS | Ongoing | Under Construction (AD issued) | Srirampur - Dhubri Pkg-1 | Widening / Improvement to 4-Lane with Paved Shoulder configuration of existing single lane road from Srirampur (near Bhairiguri Village) to Kachukhana Harichara Paglagaunj (Package-I) of Srirampur - Dhubri Section of NH-127B from existing Km 0.000 to Km 28.050 (Design Km 0.000 to Km 27.650), (Design Length=27.650 Km) under JICA ODA Loan assistance (Phase-V) -Balance work [Srirampur - Dhubri Pkg-1] | EAP (JICA) | NH | 127B | 27.65 | 0.26 | 26.19 | 613.89 | 257.5 | 2022-03-11 | 2024-09-06 | 2024-11-25 | 84.98 | 77.27 | 2026-11-25 | 2026-11-25 | - | R&C Infra Engineers Pvt. Ltd-J Infratech Limited (JIL) (JV) | rc.jandupkg1@jinfratech.com | Intercontinental Consultants and Technocrats PVT. Ltd. inassociation with Innovative Engineering Advisory LLP. | Normal Highway/Road Project
104 | DT-1 | NER | Assam | PMU-Dhubri | 153745 | DN/05003/01006/AS | Completed | Completed | Srirampur - Dhubri Pkg-2 | Widening / Improvement to 4-Lane with Paved Shoulder configuration of existing single lane road from Kachukhana Harichara Paglagaunj to Dhubri - Phulbari Bridge approach (Package-II) of Srirampur - Dhubri Section of NH-127B from existing Km 28.050 to Km 55.060 (Design Km 27.650 to Km 54.154), (Design Length=26.504 Km) under JICA ODA Loan assistance (Phase-V) [Srirampur - Dhubri Pkg-2] | EAP (JICA) | NH | 127B | 26.504 | - | 26.5 | 909.02 | 453.9 | 2022-03-11 | 2022-08-04 | 2023-01-02 | 100 | 100 | 2025-01-01 | - | 2025-06-30 | J Infratech Limited (JIL) | assam.pkg2@gmail.com assam.pkg2@jinfratech.com | Intercontinental Consultants and Technocrats PVT. Ltd. inassociation with Innovative Engineering Advisory LLP. | Normal Highway/Road Project
105 | DT-1 | NER | Assam | PMU-Dibrugarh | 153150 | DN/01019/01002/AS | Completed | Completed | Dibrugarh-Lahoal-Chabua Bypass Pkg-1 | Widening/improvement to 4-Lane with paved shoulder from km. 581+700 to km 606+300 of NH-37 on existing Dibrugarh-Lahoal-Chabua Bypass i.e. from Lepetketa to Kandulibari Grant Gaon section in Assam on EPCMode under NH(O)-NE [Pkg.1] | NH(O)-NE | NH | 37/15 | 24.6 | - | 24.6 | 215.27 | 115.82 | 2022-02-24 | 2022-03-31 | 2022-07-25 | 100 | 96.53 | 2024-07-24 | - | 2024-10-09 | Ganpati Builders | op.sharma0082@gmail.com , ganpatibuilders0082@gmail.com , ganpatidib@gmail.com | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
106 | DT-1 | NER | Assam | PMU-Dibrugarh | 153193 | DN/01019/01001/AS | Completed | Completed | Lahoal-Chabua Bypass Pkg-2 | Widening/improvement to 4-Lane with paved shoulder from km. 606+300 to km 626+030 of NH-37 on existing Lahoal-Chabua Bypass i.e. Kandulibari Grant Gaon to Nalanihulla section in Assam on EPCMode under NH(O)-NE [Pkg.2] | NH(O)-NE | NH | 37/15 | 19.73 | - | 19.73 | 170.95 | 101.16 | 2022-02-25 | 2022-04-05 | 2022-07-25 | 100 | 98.81 | 2024-07-24 | - | 2024-08-22 | Jugal Kishore Mahanta Infra works (JKM) | jkmahanta@jkminfra.net , jkmho@jiminfra.net , jkmdbrproject@gmail.com | MSV International INC in association with Vaishnavi Infratech Services Pvt. Ltd. (JV) | Normal Highway/Road Project
107 | DT-1 | NER | Assam | PMU-Dibrugarh | 154861 | DN/01019/01005/AS | Ongoing | Under Construction (AD issued) | Nalani hulla Gaon- Chotahapjan on Tinsukia -Makum Bypass Pkg-3 | Widening/Improvement to 4-Lane with Paved Shoulder from km 626+030 (Nalani hulla Gaon) to km 650+450 (Chotahapjan) on existing Tinsukhia -Makum Bypass of NH-15 (OLD NH-37) and Strengthening of existing NH-315 (OLD NH-38) from Km 0+000 (Chotahapjan) to Km 16+900 (Bogapani section) (2-Lane +PS) in Assam on EPCMode under NH(O)-NE (Pkg-3) | NH(O)-NE | NH | 37/15 & 38/315 | 41.32 | - | 39.81 | 458.59 | 210 | 2023-01-03 | 2023-02-03 | 2023-05-19 | 88.45 | 83.42 | 2025-05-17 | 2026-10-31 | - | TTC Infra India | ttcii.tm@gmail.com | Almondz Global Infra consultant Ltd. - Ayoleeza Consultants Pvt. Ltd. (JV) | Normal Highway/Road Project
107 | DT-1 | NER | Assam | PMU-Dibrugarh | 155007 | DN/01019/01004/AS | Terminated- To be Reawarded | Terminated- To be Reawarded | Dibrugarh to Ledo section (Digboi Bypass) Pkg-4 | Widening/Improvement to 2-Lane Lane with Paved Shoulder from km 16+900 (Bogapani) to km 27+150 (Golai Goan) on existing Dibrugarh to Ledo section with proposed Digboi Bypass (Green Field and Brownfield) (2-Lane+PS) of NH-315 (OLD NH-38) in Tinsukia District under NH(O)- NE (Pkg-4) | NH(O)-NE | NH | 38/315 | 10.25 | - | 1.47 | 356.65 | - | 2023-01-04 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | Almondz Global Infra consultant Ltd. - Ayoleeza Consultants Pvt. Ltd. (JV) | Standalone Bypass Project
108 | DT-1 | NER | Assam | PMU-Dibrugarh | 155282 | DN/01019/01008/AS | Awarded, Not Appointed | Awarded, Not Appointed | Margherita - Ledo Bypass (Pkg-5) (Bypass) | Widening/Improvement to 2-Lane with paved shoulder from km 27+150 (Golai Gaon) to km 47+682 (Ledo) on existing Dibrugarh to Ledo section with proposed Margherita - Ledo Bypass (Greenfield) (2-Lane +PS) of NH-315 (Old NH-38) in Tinsukia District in the State of Assam on EPC (Package-5) under Bharatmala Pariyojana in Economic Corridors -Balance work | NH(O)-NE | NH | 38/315 | 20.532 | - | 0 | 643.42 | 246.76 | 2023-03-23 | 2026-03-03 | To be given | 0 | 0 | - | - | - | Bhartia Infra Projects Limited(BIPL) | info@bhartiainfra.com, tender@bhartiainfra.com | Almondz Global Infra consultant Ltd. - Ayoleeza Consultants Pvt. Ltd. (JV) | Standalone Bypass Project
109 | DT-1 | NER | Assam | PMU-Silchar | 155122 | DN/01012/01008/AS | Ongoing | Under Construction (AD issued) | Silchar - Vairengte - Sairang road Pkg-1 | 4-Laning of Silchar - Dhanehari section from Existing Chainage km 263+800 of NH 37 to km 12+920 of NH 306 (Design Chainage km 0+000 to km 20+000) on Silchar - Vairengte - Sairang road in the State of Assam under Bharatmala Pariyojna on EPC mode. (Project Length – 20.00 km) (Package-1) | NH(O)-NE | NH | 37 & 306 | 20 | - | 9.47 | 1256.9 | 504.34 | 2023-02-28 | 2023-03-21 | 2024-01-22 | 59.65 | 43.79 | 2026-07-23 | 2026-07-22 | - | YFC Projects Pvt. Ltd. - TTC Infra India (JV) | ttcii.sd.pkg1@gmail.com | Egis India Consulting Engineers Pvt. Ltd.- Sri Infotech (JV) | Normal Highway/Road Project
110 | DT-1 | NER | Assam | PMU-Silchar | 155293 | DN/01012/01007/AS | Ongoing | Under Construction (AD issued) | Silchar - Vairengte - Sairang road Pkg-2 | 4-Laning of Dhanehari Lailapur / Vairengte section from Existing Chainage km 12+920 to km 43+000 of NH 306 (Design Chainage km 20+000 to km 49+360) on Silchar - Vairengte Sairang road in the State of Assam under Bharatmala Pariyojna on EPC mode. (Project Length 29.360 km) under NH(O)-NE (Package-2) | NH(O)-NE | NH | 306 | 29.36 | - | 19.88 | 1716.21 | 592.8 | 2023-03-31 | 2023-03-31 | 2024-02-14 | 81.65 | 61.3 | 2026-08-14 | 2026-08-14 | - | J Infratech Limited (JIL) | jandu.silchar@jinfratech.com | Egis India Consulting Engineers Pvt. Ltd.- Sri Infotech (JV) | Normal Highway/Road Project
111 | DT-1 | NER | Assam | PMU-Silchar | 157475 | DN/01011/01009/AS | Ongoing | Under Construction (AD issued) | Silchar-Badarpur-Karimganj– Churaibari Pkg-1 | Widening/lmprovement of Existing 2 lane to 4-Laning of Karimganj-Silchar section of NH-37 from Design Ch 0.000 near Silchar ISBT to Design Ch 15.970 near Kalinagar Pt I on NH-37 in Assam on HAM Mode (Pkg-1) | NH(O)-NE | NH | 37 | 15.97 | - | 0 | 1181.55 | 696.5 | 2024-03-11 | 2024-03-11 | 2025-09-17 | 41.26 | 0 | 2027-09-17 | 2027-09-17 | - | Jandu Silchar Highway Pvt. Ltd. | jandu.panchgram@jinfratech.com | Ayoleeza Consultants Private Limited - Agnitio Infrastructure Projects Pvt. Ltd.(AIPPL) - BESHTECH Infrastructure Private Limited (JV) | Normal Highway/Road Project
112 | DT-1 | NER | Assam | PMU-Silchar | 156858 | DN/01011/01004/AS | Ongoing | Under Construction (AD issued) | Panchgram Bypass (on Silchar- Churaibari Pkg-2) | Construction of 4-Lane Panchgram Bypass from Design Chainage km 15+500 on NH-37 (Old NH-53) at Kalinagar Pt.-I Village to Design Chainage km 27+300 at crossing with NH-6 (Old NH-44) Near Siddeswar Pt.-I Village on Silchar - Churaibari stretch in the State of Assam on EPC Mode under Bharatmala Pariyojana in Economic Corridors | NH(O)-NE | NH | 6 & 37 | 11.8 | - | 5.5 | 728.97 | 409.25 | 2023-03-16 | 2023-10-31 | 2024-08-10 | 57.17 | 48.75 | 2027-02-09 | 2027-02-09 | - | J Infratech Limited (JIL) | isbt.silchar@jinfratech.com | Agnitio Infrastructure Projects Pvt Ltd.(AIPPL) - Indian Technocrat Ltd. (ITL) (JV) | Standalone Bypass Project
113 | DT-1 | NER | Assam | PMU-Silchar | 155087 | DN/01011/01003/AS | Ongoing | Under Construction (AD issued) | Badarpur Bypass (on Silchar- Churaibari Pkg-3) | Construction of 4-Lane Badarpur Bypass from Design Chainage km 27+300 at crossing with NH-6 (Old NH-44) Near Siddeswar Pt.-I Village to Design Chainage km 38+600 on NH-37 (Old NH-44) at Kandigram Chaita Village on Silchar - Churaibari stretch in the State of Assam on EPC Mode under Bharatmala Pariyojana in Economic Corridors (Project Length – 11.1 km). | NH(O)-NE | NH | 6 & 37 | 11.1 | - | 5.5 | 574.26 | 292.29 | 2023-02-28 | 2023-03-16 | 2024-02-09 | 71.09 | 58.91 | 2026-08-09 | 2026-08-10 | - | S S Builders | badarpurkmr@gmail.com | Agnitio Infrastructure Projects Pvt Ltd.(AIPPL) - Indian Technocrat Ltd. (ITL) (JV) | Standalone Bypass Project
114 | DT-1 | NER | Assam | PMU-Karimganj | 157471 | DN/01011/01005/AS | Ongoing | Under Construction (AD issued) | Silchar-Badarpur-Karimganj– Churaibari Pkg-4 | Widening/lmprovement to 4-Laning and Greenfield alignment with Paved shoulder of Silchar-Badarpur – Churaibari section of NH-37 & NH-8 from Design chainage 38.600 (End point of proposed Badarpur Bypass) to Km. 62.800 (Start point of proposed Nilambazar/Cheragi Bypass) in the state of Assam on HAM Mode (Package-4) | NH(O)-NE | NH | 37 & 8 | 24.2 | - | 0 | 1319.55 | 554.16 | 2024-02-28 | 2024-03-11 | 2025-08-18 | 14.6 | 8 | 2027-09-18 | 2027-08-18 | - | MKC Badarpur Churaibari Kamakhya Highways Pvt. Ltd. | engineering@mkcinfrastructureltd.com | M/s Agnitio JV with Ayoleeza Infra Pvt. Ltd. | Normal Highway/Road Project
115 | DT-1 | NER | Assam | PMU-Karimganj | 157472 | DN/01011/01008/AS | Ongoing | Under Construction (AD issued) | Silchar-Badarpur-Karimganj– Churaibari Pkg-5 | Widening/lmprovement to 4-Lane with Paved Shoulder from existing road and Greenfield alignment form Design Ch. 62.800 (start of proposed Nilambazar/Cheragi Bypass) to Design Ch. 87.700 near Chandkhira Village of NH-8 on Silchar-Churaibari in the state of Assam on HAM Mode (Package-5) | NH(O)-NE | NH | 8 | 24.9 | - | 0 | 1258.13 | 690 | 2024-02-27 | 2024-03-11 | 2025-04-26 | 11 | 8 | 2027-10-23 | 2027-10-23 | - | Bhartia Infra Projects Limited(BIPL) | ccb_silchar@yahoo.co.in | Lion Engineering Consultants Private Limited in Association with - Synergy Engineers Group Pvt Ltd (JV) | Normal Highway/Road Project
116 | DT-1 | NER | Assam | PMU-Karimganj | 157473 | DN/01011/01007/AS | Ongoing | Under Construction (AD issued) | Badarpur – Churaibari Pkg-6 | Widening/lmprovement to 4-Lane with Paved shoulder for existing as well as Greenfield alignment of Badarpur – Churaibari section of NH-8 from Design chainage 87.700 (Chandkhira) to Km. 106.500 (Churaibari) section (Assam-Tripura border) in the state of Assam on HAM Mode (Package-6) | NH(O)-NE | NH | 8 | 18.8 | - | 0 | 870 | 449.81 | 2024-03-04 | 2024-03-11 | 2025-03-07 | 31.83 | 16 | 2027-03-07 | 2027-03-07 | - | MKC Infrastructure Pvt. Ltd | engineering@mkcinfrastructureltd.com | Agnitio Infrastructure Projects Pvt. Ltd (AIPPL) - Ayoleeza Consultants Private Limited (JV) | Normal Highway/Road Project
117 | DT-1 | NER | Assam | PMU-Karimganj | 157474 | DN/01011/01006/AS | Ongoing | Under Construction (AD issued) | Karimgani - sutarkandi section on Silchar-Churaibari Pkg-7 | Widening/lmprovement to 4-L of Karimgani - sutarkandi section of NH 37 from design Ch 0+020 (Start of proposed Karimganj Bypass from NH -8) to design Chainage Km 14+380 near Sutarkandi (Spur Connectivity to Indo/Bangladesh Border) on Silchar-Churaibari in the State of Assam on HAM Mode (Package-7) | NH(O)-NE | NH | 37 | 14.36 | - | 0 | 791.79 | 380.26 | 2024-02-28 | 2024-03-11 | 2025-02-28 | 40.4 | 16 | 2027-02-28 | 2027-02-28 | - | MKC Infrastructure Pvt. Ltd | engineering@mkcinfrastructureltd.com | Technocrats Advisory Services Private Limited (TASPL) in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
118 | DT-1 | NER | Assam | PMU-Silchar | 157476 | DN/01018/01001/AS | Ongoing | Under Construction (AD issued) | Silchar-Jiribam Pkg-1 | lmprovement to 4-Lane with Paved Shoulder from existing km 260+000 (Design Ch.4+560 km) to existing km Ch.233+000 (D. Ch.24+560) of Silchar (near Nutan Dayapur village) - Budha Nagar Section (Length-20.00 Km) of NH-37 under Package: Silchar-Jiribam Pkg-1 in the state of Assam on HAM Mode | NH(O)-NE | NH | 53/ 37 | 20 | - | 5.5 | 957.95 | 476 | 2024-01-24 | 2024-03-11 | 2025-01-15 | 47.27 | 8 | 2028-01-15 | 2028-01-15 | - | Silchar Jiribam Highways Private Limited | headoffice@dccinfra.co.in | GEO Designs and Research Private Limited | Normal Highway/Road Project
119 | DT-1 | NER | Assam | PMU-Silchar | AS-1 | DN/01018/01002/AS | Awarded, Not Appointed | Awarded, Not Appointed | Silchar-Jiribam (including 770m Tunnel) Pkg-2 | 4 - laning of silchar (near Budha Nagar) at Existing km 233+000 (D. Ch. 24.560) to Jiribam at Existing km 212+060 (D. ch. 37.650) including Tunnel of NH-37 (Length:13,09 km) in the State of Assam and Manipur under NH(O)-NE on Hybrid Annuity Mode (HAM) (Pkg-2) | NH(O)-NE | NH | 53/ 37 | 13.09 | - | 0 | 1186.2 | 742.78 | 2025-03-27 | 2025-10-15 | To be given | 0 | 0 | - | - | - | Bhartia Infra Projects Limited(BIPL) | info@bhartiainfra.com | - | Standalone Tunnel Project
120 | DT-1 | NER | Assam | PMU-Bongaigaon | 155286 | DN/01005/01004/AS | Completed | Physically Completed & CC Under Issue | Dudhnoi - Dainadubi section | Widening & Improvement to 2-lane with Paved shoulder configuration of Dudhnoi - Dainadubi section (NH-217) under Bharatmala Pariyojana from design km 0+000 to km 8+415 (existing km 0+000 to km 8+600 of Old NH-62) in the State of Assam on EPC mode under NH(O)-NE, (Assam portion) | NH(O)-NE | NH | 62/217 | 8.415 | - | 8.41 | 88.56 | 33.7 | 2023-03-24 | 2023-03-31 | 2024-03-26 | 100 | 89.62 | 2025-09-25 | Physically Completed & CC Under Issue | 2026-05-31 | Shyama Construction | shyamaconstructionnh217@gmail.com | Dhruv Consultancy Services Limited in association with M S Consultant | Normal Highway/Road Project
121 | DT-1 | NER | Assam | PMU-Silchar | 157188 | DN/02002/01004/AS | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-7 | Wideinig & Upgradation to 2-lanes with paved shoulders road from Tamenglong to Mahur (NH-137) in the State of Assam starting from km 96.870 near Jiri River to km 116.550 near Hangrum (Package-7) on EPC mode (Assam portion) | NH(O)-NE | NH | 137 | 19.68 | - | 16.19 | 846.82 | 264.36 | 2023-12-11 | 2024-01-22 | 2024-03-04 | 90.36 | 67.99 | 2026-03-04 | 2026-12-31 | - | Rajinder Infrastructure Pvt.Ltd. | official.riplassam@gmail.com | Theme Engineering Services Pvt. Ltd. in assn. with- Ishita Info Solutions Pvt. Ltd. (JV) | Normal Highway/Road Project
122 | DT-1 | NER | Assam | PMU-Silchar | 155284 | DN/02002/01003/AS | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-8 | Widening & Upgradation to 2-lanes with paved shoulders road from Tamenglong to Mahur (NH-137) in the State of Assam starting from km 116.480 near Hangrum to km 136.500 near Hejaichak (Package-8) on EPC mode under NH(O)-NE (Assam portion) | NH(O)-NE | NH | 137 | 20.02 | - | 18.54 | 904.04 | 344.66 | 2023-03-29 | 2023-03-31 | 2023-08-29 | 85.2 | 60.44 | 2025-08-29 | 2026-09-25 | - | Anusha Projects Pvt. Ltd.- BKD Infrastructures Pvt. Ltd. (JV) | appl.tmr8@gmail.com | Theme Engineering Services Pvt. Ltd. in assn. with- Ishita Info Solutions Pvt. Ltd. (JV) | Normal Highway/Road Project
123 | DT-1 | NER | Assam | PMU-Silchar | 155288 | DN/02002/01002/AS | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-9 | Widening & Upgradation to 2 lanes with paved shoulders road from Tamenglong to Mahur (NH-137) in the State of Assam starting from km 136.500 near Hejaichak to km 156.489 near P. Leikul (Package-9) on EPC mode under NH(O)-NE (Assam portion) | NH(O)-NE | NH | 137 | 19.989 | - | 19.7 | 614.43 | 344.66 | 2023-03-31 | 2023-03-31 | 2023-08-29 | 87.5 | 50.71 | 2025-08-29 | 2026-07-30 | - | KPC Projects Ltd. | pc.nh137@kpc.co | Technocrats Advisory Services Private Limited (TASPL) in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
124 | DT-1 | NER | Assam | PMU-Silchar | 155287 | DN/02002/01001/AS | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-10 | Widening & Upgradation to 2 lanes with paved shoulders road from Tamenglong to Mahur (NH-137) in the State of Assam starting from km 156.489 near P. Leikul to km 176.410 near Borowapu (Package-10) on EPC mode under NH (O)-NE (Assam portion) | NH(O)-NE | NH | 137 | 19.921 | - | 18.93 | 693.15 | 354.69 | 2023-03-31 | 2023-03-31 | 2023-08-29 | 90.5 | 58.63 | 2025-08-29 | 2026-09-25 | - | Anusha Projects Pvt. Ltd.- BKD Infrastructures Pvt. Ltd. (JV) | anushaprojects@gmail.com | Technocrats Advisory Services Private Limited (TASPL) in Association with - MAV Associates LLP (JV) | Normal Highway/Road Project
125 | DT-1 | NER | Assam | PMU-Dibrugarh | 155289 | DN/02003/01003/AS | Completed | Completed | Kandulijan Gaon to Simen Chapori Pkg-1 | Widening/Improvement to 4-Lane with Paved Shoulder from km 0+800 (Kandulijan Gaon) to km 27+701 (Simen Chapori) of NH-515 in the State of Assam on EPC mode under Bharatmala Pariyojna (Dibrugarh-Oyan, Package-1) | NH(O)-NE | NH | 52/ 515 | 26.901 | - | 26.9 | 609.16 | 267.62 | 2023-03-28 | 2023-03-31 | 2023-10-18 | 100 | 99.45 | 2026-04-17 | - | 2025-08-11 | Kaluwala Construction Pvt. Ltd.-Nirmal Buildinfra Pvt. Ltd. (JV) | kcpl.assam@kaluwalaconstruction.in | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
126 | DT-1 | NER | Assam | PMU-Dibrugarh | 155281 | DN/02003/01002/AS | Completed | Completed | Simen Chapori to Nagabang Gamsuk Pkg-2 | Widening/Improvement to 4-Lane with Paved Shoulder from km 27+701 (Simen Chapori) to km 55+000 (Nagabang Gamsuk) in Dhemaji district in the State of Assam on EPC mode under Bharatmala Pariyojna (Package-2) | NH(O)-NE | NH | 52/ 515 | 27.299 | - | 27.3 | 562.05 | 249.4 | 2023-03-29 | 2023-03-31 | 2023-08-11 | 100 | 99.79 | 2026-02-08 | - | 2025-07-31 | Kaluwala Construction Pvt. Ltd.-Nirmal Buildinfra Pvt. Ltd. (JV) | kcpl.assam@kaluwalaconstruction.in | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
127 | DT-1 | NER | Assam | PMU-Dibrugarh | 155291 | DN/02003/01001/AS | Ongoing | Under Construction (AD issued) | Nagabang Gamsuk- Oyan Pkg-3 | Widening/Improvement to 4-Lane with Paved Shoulder from km 55+000 (Nagabang Gamsuk) to km 82+514 (Oyan) in the State of Assam and Arunachal Pradesh on EPC mode under Bharatmala Pariyojna of Length 27.514 Km (Package-3) | NH(O)-NE | NH | 52/ 515 | 27.52 | 0.41 | 25.55 | 665.47 | 266.24 | 2023-03-31 | 2023-03-31 | 2024-09-16 | 96.7 | 92.44 | 2027-03-17 | 2027-03-17 | - | Kaluwala Construction Pvt. Ltd.-Nirmal Buildinfra Pvt. Ltd. (JV) | kcpl.assam@kaluwalaconstruction.in | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
128 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | 151044 | DN/09008/02020/JM | Completed | Completed | Strengthening of Batote-Kishtwar-Chatroo- Sinthan top road Km 170.000 to Km 184.000 | Restoration of Road by way of clearance of landslide, surface boulders side drain, culverts including construction of R/wall/Scuppers and laying of WBM-II, WBM-III, & Pre- Mixed Surfacing/Mixed seal Surfacing (PC) on Batote-Kishtwar-Chatroo- Sinthan top road NH-244 Km from Km 170.000 to Km 184.000 on Item Rate basis | NH(O) | NH | 244 | 14 | - | 14 | 8.01 | 6.55 | 2017-10-06 | 2018-03-01 | 2018-03-07 | 100 | 100 | 2019-08-31 | - | 2020-10-11 | Khanday Infrastructure Ltd. | directorkipl@gmail.com | M/s Khanday Infrastructure Pvt Ltd | Normal Highway/Road Project
129 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | 157024 | DN/09008/02019/JM | Completed | Completed | Strengthening of Sinthanpass- Anantnag –Khanabal road Km 184.00 to Km 265.00 | Restoration of road by way of clearance of landslide, surface boulders side drain, culverts including construction of R/wall and B/walls and laying of WBM-I, WBM-II, WBM-III & Bituminous Carpeting on Sinthanpass- Anantnag –Khanabal road (Km 184.00 to Km 265.000) on Item Rate basis | NH(O) | NH | 244 | 23.2 | - | 23.2 | 16.49 | 12.47 | 2017-10-06 | 2018-02-16 | 2018-03-22 | 0 | 0 | 2019-08-31 | - | 2019-08-31 | Khanday Infrastructure Ltd. | - | M/s Khanday Infrastructure Pvt Ltd | Normal Highway/Road Project
130 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Akhnoor | 154039 | DN/09014/01010/JM | Ongoing | Under Construction (AD issued) | Jammu-Akhnoor (Flyover) Pkg-1 | Construction of a 4-Lane elevated flyover with paved shoulder configuration along with service road from 4th Tawi bridge (D.Ch. 0.000) near Bhagwati chowk to Canal Head (D.Ch. 1.350) on Jammu-Akhnoor road section of NH-144A (Pkg-1) | NH(O) | NH | 144A | 1.15 | - | 1.15 | 245.34 | 135.12 | 2018-03-14 | 2022-09-24 | 2023-01-10 | 75.19 | 65.48 | 2025-01-09 | 2026-07-31 | - | Maan Builders | maanbuildersjammu@gmail.com maanbuilderspkl@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project-(including Bridge)
131 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Akhnoor | 80719 | DN/09014/01008/JM | Completed | Completed | Jammu-Akhnoor Canal head - to Ganesh Vihar (Flyover) Pkg-2 | Up-gradation to 4-lane with Paved Shoulder of Jammu-Akhnoor road section of NH-144A from Canal head (Km 0.800) to Ganesh Vihar (Km 6.000) in UT of Jammu and Kashmir on EPC basis (Pkg-2) | NH(O) | NH | 144A | 5.2 | - | 5.2 | 458.06 | 272.77 | 2018-03-14 | 2018-03-15 | 2018-08-07 | 100 | 99.16 | 2021-02-04 | - | 2022-10-15 | Satpal (S. P.) Singla construction Pvt. Ltd.[SPSCPL] | salwanguleria@spsingla.com, spsakhnoor@spsingla.com | TPF Getinsa in association with Segmental Consulting | Normal Highway/Road Project-(including Bridge)
132 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Akhnoor | 138017 | DN/09014/01007/JM | Ongoing | Under Construction (AD issued) | Jammu-Akhnoor Ganesh Vihar to Khati Chowk Pkg-3A | Up-gradation to 4-lane with Paved Shoulder of Jammu-Akhnoor road section of NH-144A from Ganesh Vihar (Km 6.000) to Khati Chowk (Km 26.350) in UT of Jammu and Kashmir on EPC basis (Pkg-3A) 1 No. TOLL of 8- Lane @ Ch. 20+440 | NH(O) | NH | 144A | 20.61 | - | 20.6065 | 435.82 | 193.99 | 2018-03-14 | 2019-03-02 | 2019-07-12 | 92.21 | 90.04 | 2021-07-11 | 2026-07-31 | - | Tarmat Ltd. | tarmatakhnoor@gmail.com | TPF Getinsa in association with Segmental Consulting | Normal Highway/Road Project
133 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Akhnoor | 154301 | DN/09014/01006/JM | Ongoing | Under Construction (AD issued) | Jammu - Akhnoor Khati Chowk Hanuman Chowk Pkg-3B | Upgradadtion of existing 2 lane to 4-L with Paved Shoulder configuration from Km 26.350 (Design Chainage 26+615) (Khati Chowk) to Km 30.097 (Design Chainage 30+359) (Hanuman Chowk) including bridge on Chenab river of Jammu - Akhnoor Section of NH 144A (Pkg-3B) | NH(O) | NH | 144A | 3.75 | - | 3.74 | 198.28 | 102.47 | 2018-03-14 | 2022-12-14 | 2023-03-14 | 93.95 | 93.9 | 2025-03-13 | 2026-09-30 | - | V. K. Gupta & Associates | 1. amitkumar@vkga.in 2. contact@vkga.in 3. vkg.brconst@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
134 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Akhnoor | 66765 | DN/09008/02011/JM | Completed | Physically Completed & CC Under Issue | Chenani – Sudhmahadev | Widening and Up-gradation to 2-Lane with Paved Shoulder of configuration and geometric improvement from Km 0.000 to Km 16.990 on Chenani – Sudhmahadev section of NH-244 in UT of Jammu and Kashmir to be executed on EPC basis | NH(O) | NH | 244 | 16.99 | - | 16.99 | 264.21 | 155.04 | 2018-03-14 | 2018-03-27 | 2018-11-22 | 94.06 | 93.76 | 2020-11-21 | Physically Completed C.C Under Issue | 2025-02-10 | ECI Engineering & Constr. Co. Ltd.-SRM (Shri Ram Mehta) Contractors Pvt. Ltd. (JV) | srmcontractors@gmail.com srmcplc@gmail.com | TPF Getinsa in association with Segmental Consulting | Normal Highway/Road Project
135 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 150870 | DN/09008/02007/JM | Ongoing | Under Construction (AD issued) | Goha-Khellani Pkg-1 | Up-gradation to 2-lane with Paved Shoulder from Km 12.850 to Km20.300 of 7.450Km length on Goha-Khellani section and a link road to Goha village of 2.016 km on NH-244 in UT of Jammu and Kashmir on EPC Mode (Pkg-1) | NH(O) | NH | 244 | 9.46 | - | 8.47 | 225.3731 | 118.41 | 2020-07-14 | 2020-07-31 | 2020-10-01 | 94.26 | 92.51 | 2022-04-01 | 2026-10-31 | - | OASIS Technocon Ltd - Vidya Infrabuild Pvt. Ltd. (VIPL) (JV) | info@oasisprojects.com pkg1a.goha@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
136 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 150872 | DN/09008/02013/JM | Completed | Physically Completed & CC Under Issue | Goha-Khellani Pkg-2 | Up-gradation to 2-lane with Paved Shoulder from Km 20.300 to Km 29.030 of 8.730 Km length on Goha-Khellani section on NH-244 in UT of Jammu and Kashmir on EPC Mode (Package II) | NH(O) | NH | 244 | 8.73 | - | 8.4 | 210.79 | 99 | 2020-07-14 | 2020-07-31 | 2020-10-01 | 96.95 | 96.44 | 2022-04-01 | Physically Completed C.C Under Issue | 2026-02-27 | E5 Infrastructure Pvt. Ltd. | package2gohakhellani@gmail.com construction@e5infra.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
137 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 151439 | DN/09008/02012/JM | Completed | Completed | Khellani Tunnel Pkg-3 | Up-gradation to 2-lane with Paved Shoulder form Km 29+030 to Km 31+449 of 2.419 Km length of Uni-Directional (1.574 Km) Khellani Tunnel including its approach road on NH-244 in UT of Jammu and Kashmir on EPC Mode under NH(O)-Gen (Package III) | NH(O) | NH | 244 | 2.419 | - | 2.42 | 749.61 | 431.28 | 2021-01-29 | 2021-02-08 | 2021-03-25 | 100 | 100 | 2023-03-24 | - | 2025-03-17 | APCO Infratech Pvt. Ltd | ddbabu@apcoinfra.com dc.ktp@apcoinfra.com | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. in JV with SA Infrastructure Consultants Pvt. Ltd | Standalone Tunnel Project
138 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 151430 | DN/09008/02010/JM | Completed | Completed | Khellani - Kishtwar - Chattroo Pkg-1 | Construction & Upgradation to 2 lane with paved shoulder from Design Km. 31.449 (Khellani) (Ex. Km 44.946) to Km 51.700 (Prem Nagar) (Ex. Km 68+617) of 20.251 Km length on Khellani - Kishtwar - Chattroo section of NH-244 in the UT of J&K on EPC Mode under NH(O)-Gen (PKG- 1) | NH(O) | NH | 244 | 20.251 | - | 18.66 | 486.45 | 208.58 | 2021-02-02 | 2021-02-03 | 2021-03-29 | 97.21 | 97.16 | 2022-09-28 | - | 2024-11-01 | R&C Infra Engineers Pvt. Ltd.- SKS Infra Projects Pvt. Ltd. (JV) | randcinfraengineers@gmail.com randcdodaoffice@gmail.com | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. in JV with SA Infrastructure Consultants Pvt. Ltd | Normal Highway/Road Project
139 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 152091 | DN/09008/02009/JM | Ongoing | Under Construction (AD issued) | Khellani - Kishtwar - Chattroo Pkg-2 | Construction & Upgradation to 2-lane with paved shoulder from Design Ch. Km 51+700 (at Premnagar km 66+315) to Km 66+535 New Thatri (at Start of Km 83rd, Tunnel Km 82+665) of 14.835 Km design length on Chenani-Sudhmahadev-Goha Khellani-Kishtwar-Vailoo Donipawa-Ashajipora section of NH-244 in the UT of J&K on EPC Mode under NH(O)-Gen (Pkg - 2) | NH(O) | NH | 244 | 14.84 | - | 11.4 | 512.43 | 220.33 | 2021-03-30 | 2021-07-19 | 2021-08-26 | 53.49 | 50.08 | 2023-02-24 | 2026-10-31 | - | Mathiyan Construction Pvt. Ltd. - Unique Construction (JV) | mathiyan_mzn@rediffmail.com pm.jk@mathiyan.com | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. in JV with SA Infrastructure Consultants Pvt. Ltd | Normal Highway/Road Project
139 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Doda | 149359 | DN/09008/02008/JM | Terminated- To be Reawarded | Terminated- To be Reawarded | Bi-directional Tunnel at "Km 83" on Khellani-Kishtwar Section | Construction of Bi-directional Tunnel at "Km 83" of Length 495 m including approach road of 664 m and a Major Bridge of 110 m from Design Ch. 66.535 to Ch. 67.805 (Existing Km 82.675 to Km 82.925) (Khellani-Kishtwar) on NH-244 in UT of J&K on EPC Mode under NH(O) | NH(O) | NH | 244 | 1.269 | - | 0 | 91.29 | - | 2019-11-27 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Standalone Tunnel Project
140 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | 151691 | DN/09008/02015/JM | Completed | Physically Completed & CC Under Issue | Khellani - Kishtwar - Chattroo Pkg-3 | Construction & Upgradation to 2-lane with paved shoulder from Design Km 67.805 (at the end of Km 83rd Tunnel near Dhrabshalla) (Ex. Km 83+905) to Km 80.675 (start of Kishtwar Bypass - Dulhasti) (Ex. Km 97+0751) of 12.870 Km length on chenani-Sudhmahadev-Goha Khellani-Kishtwar-vailoo-Donipawa-Ashajipora section of NH-244 in the UT of J&K on EPC Mode under NH(O)-Gen (Pkg-3) | NH(O) | NH | 244 | 12.87 | - | 11.91 | 398.51 | 134.35 | 2021-03-30 | 2021-03-30 | 2021-07-01 | 98.55 | 97.34 | 2022-12-31 | Physically Completed C.C Under Issue | 2025-03-31 | R & B Infra Project Pvt. Ltd | legal@rathoregroup.co | Shrikhande Consultants Pvt. Ltd. in association with Infra Design Studio Pvt. Ltd. | Normal Highway/Road Project
141 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | J&K-1 | DN/09008/02027/JM | Awarded, Not Appointed | Awarded, Not Appointed | Re-alignment of submergence area near Rattle Dam on (Left-over work of Khellani - Kishtwar - Chattroo Pkg-3) | Construction of left-over work 2-L+PS of the road stretch of Pkg-III at Kandni Village from design Ch. 0+000 to Ch. 4+037 (Ch. 70+900 to Ch. 74+650 of NH-244) in 4.037 km length on Khellani-Kishtwar-Chhatroo section of NH-244 in UT of Jammu & Kashmir on EPC Mode | NH(O) | NH | 244 | 4.037 | - | 0 | 132.99 | 61.7715 | 2021-03-30 | 2026-02-27 | To be given | 0 | 0 | - | - | - | R & B Infra Project Pvt. Ltd | tender@rathoregroup.co | Shrikhande Consultants Pvt. Ltd. in association with Infra Design Studio Pvt. Ltd. | Normal Highway/Road Project
142 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | 152003 | DN/09008/02014/JM | Ongoing | Under Construction (AD issued) | Khellani - Kishtwar - Chattroo (Kishtwar Bypass) Pkg-4 | Construction of Kishtwar bypass with 2 lane with paved shoulder from Design Km. 80.675 (Dulhasti) to km 95.550 (Bandarkoot ) of 14.88 km & a link road to Kishtwar town from 0+000 to 1.871 of length=1.871 Km on Khellani - Kishtwar - Chattroo section in UT of Jammu and Kashmir on EPC Mode (Pkg-4) | NH(O) | NH | 244 | 17.68 | - | 8.39 | 859.67 | 436.33 | 2021-03-30 | 2021-07-07 | 2021-08-24 | 50.05 | 49.66 | 2023-08-23 | 2027-06-30 | - | APS Hydro Pvt. Ltd. - Unique Construction (APS - UC) (JV) | apshydro@gmail.com rohit.malik@apshydro.com | Shrikhande Consultants Pvt. Ltd. in association with Infra Design Studio Pvt. Ltd. | Standalone Bypass Project
143 | DT-3 | Non-NER | Jammu & Kashmir (RO-Jammu) | PMU-Kishtwar | 151693 | DN/09008/02016/JM | Completed | Physically Completed & CC Under Issue | Khellani - Kishtwar - Chattroo Pkg-5 | Construction/upgradation to 2-lane with paved shoulder from Design Km 95.55 (Bandarkoot) to Km. 111.06 (Chattroo) of 15.52 Km length on Chenani-sudhmahadev-Goha-Khellani-Kishtwar-vailoo-Donipawa-Ashajipoora section on NH-244 in UT of Jammu and Kashmir on EPC Mode (Pkg-5) | NH(O) | NH | 244 | 15.52 | - | 15.5 | 497.09 | 202.6 | 2021-03-31 | 2021-07-13 | 2021-08-24 | 99.97 | 97.18 | 2023-02-19 | Physically Completed & CC Under Issue | 2026-03-31 | Shree Girrajjee Infra Heights Pvt. Itd. - Narendra Builders (SGIHPL-NB) (JV) | sginbpkg5@gmail.com | Shrikhande Consultants Pvt. Ltd. in association with Infra Design Studio Pvt. Ltd. | Normal Highway/Road Project
144 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Sonamarg | 60060 | DN/09023/01005/SR | Completed | Completed | Z-Morh Tunnel (Sonamarg Tunnel) | Construction Operation and Maintenance of 2L bi-directional single tube Z-Morh Tunnel (Sonamarg Tunnel)of 6.412 km long with parallel 6.426 km long escape tunnel and 0.6 km long Ventilation Tunnel with approaches of length 5.568 Km from approximately km 69.000 to km 81.300 on new alignment between Kullan and Sonmarg in the UT of Jammu and Kashmir under Srinagar-Leh section on NH-1 (Srinagar- Sonamarg- Gumri road) on DBFOT (semi-Annuity basis) | NH(O) | NH | 1 | 11.98 | - | 11.98 | 2716.9 | 2378.76 | 2016-07-06 | 2019-12-19 | 2020-06-24 | 100 | 0 | 2023-12-21 | - | 2024-07-27 | APCO Infratech Pvt. Ltd | dksaini@apcoinfra.com | Intercontinental Consultants & Technocrats Pvt. Ltd. (ICT)- Anandjiwala Infra Advisory (JV) [ ICT-AIAPL (JV)] ] | Standalone Tunnel Project
145 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Sonamarg | 150679 | DN/09023/02001/SR | Ongoing | Under Construction (AD issued) | Zojila Tunnel & Connecting road to Z-Morh Tunnel | Construction of (I) Connecting road from Z-Morh Tunnel to Zojila Tunnel (Road Length= 18.475km) in F.Y.- 2020-21 and (II) 14.150 Km long 2-L Bi- directional single tube Zoji-la Tunnel accross Zojila Pass on Sonamarg - Kargil section from Km 82 to Km 118 of NH-01 under PMDP | NH(O)-TSP | NH | 1 | 30.893 | - | 16.96 | 6808.69 | 4509.5 | 2018-01-18 | 2020-08-25 | 2020-10-01 | 68.8 | 63.15 | 2026-09-30 | 2028-02-28 | - | Megha Engineering & Infrastructures Ltd (MEIL) | meilplanning.zojila@meghaeng.com | Intercontinental Consultants & Technocrats Pvt. Ltd. (ICT)- Anandjiwala Infra Advisory (JV) [ ICT-AIAPL (JV)] ] | Standalone Tunnel Project
146 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Anantnag | 151431 | DN/09008/02017/SR | Completed | Completed | Khellani-Khanabal section Pkg-6 | Construction & Upgradation to 2/ 4-Lane with paved shoulder from Design Km 148+589 (Existing km 235+070) (Vailoo )to Design Km 176+532 (Existing km 263+070) Donipawa of 27.943 km length on Khellani-Khanabal section (PKG- 6) | NH(O) | NH | 244 | 27.943 | - | 27.94 | 285.28 | 158.15 | 2021-02-02 | 2021-02-03 | 2021-03-31 | 98 | 97 | 2022-09-30 | - | 2023-05-11 | New India Contractors & Developers Pvt. Ltd. - Khanday Infrastructure Ltd. (JV) | directorkipl@gmail.com | Magot Engineering Pvt. Ltd. In JV with Technical Consultancy Services In Association with Sofi Infrastructure Pvt. Ltd. | Normal Highway/Road Project
146 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Anantnag | J&K-2 | DN/09008/02026/JM | Sanctioned not awarded | Sanctioned not awarded | 4-L Vailoo-Donipawa (on Khellani-Khanabal section) | Widening and Upgradation of intermittent 2-lane with Paved Shoulder stretches to 4-lane between Vailoo (Km 148+589) and Donipawa (Km 176+532), totaling 9.866 km, on the Khellani—Khanabal section of NH- 244 in the UT of Jammu & Kashmir on EPC mode under NH(O) | NH(O) | NH | 244 | 9.866 | - | 0 | 157.25 | 0 | 2026-03-03 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
147 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Anantnag | 151692 | DN/09008/02018/SR | Completed | Completed | Khellani-Khanabal section Pkg-7 (Donipawa -Ashajipora ByPass project) | Construction of New 2-Lane bypass from Design Km 176+532 (Existing km 263+070; (Donipawa) to Design Km 185+002 (Near Khudwani on NH-44 at Existing km 238+500) Alstop via Ashajipora of 8.470 Km length i.e., to connecting NH-244 & NH-44 (Pkg-7) | NH(O) | NH | Connecting NH-244 & NH-44 | 8.47 | - | 6.6 | 260.4 | 57.26 | 2021-03-30 | 2021-03-30 | 2021-06-15 | 100 | 97.92 | 2022-12-16 | - | 2024-07-31 | E5 Infrastructure Pvt. Ltd. | syedaesan821@gmail.com | Magot Engineering Pvt. Ltd. In JV with Technical Consultancy Services In Association with Sofi Infrastructure Pvt. Ltd. | Standalone Bypass Project
148 | DT-3 | Non-NER | Jammu & Kashmir (RO-Srinagar) | PMU-Sonamarg | 150682 | DN/09002/02002/SR | Completed | Completed | Strengthening of Baramulla-Gulmarg | Strengthening & Upgradation of existing carriageway to intermediate lane from km 0.000 to km 42.820 of Length 42.820kms on Baramulla-Gulmarg section of NH-701A in the UT of Jammu & Kashmir on EPC mode | NH(O) | NH | 701A | 42.82 | - | 42.82 | 131.6 | 84.62 | 2020-07-31 | 2020-08-31 | 2020-10-08 | 98.51 | 97.9 | 2022-04-06 | - | 2022-10-06 | United Jehlum Road Roof Builders - Jehlum Construction Co (JV) | danish.mir3@gmail.com | Magot Engineering Pvt. Ltd. In JV with Technical Consultancy Services In Association with Sofi Infrastructure Pvt. Ltd. | Normal Highway/Road Project
148 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151694 | DN/09016/03003/LA | Terminated- To be Reawarded | Terminated- To be Reawarded | Kargil Zanskar Road Pkg-1 | Widening & Upgradation to 2 lane with paved shoulder of NH-301 Kargil Zanskar Road from Design Km 0.000 (Ex. Km.0.000) to Km 30.040 (Ex. Km. 30.000) of 30.040 Km length (Pkg-I) | NH(O)-TSP | NH | 301 | 24.04 | - | 11.584 | 384.24 | - | 2021-03-31 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
149 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151695 | DN/09016/03002/LA | Ongoing | Under Construction (AD issued) | Kargil Zanskar Road Pkg-2 | Widening & Up-gradation to 2 lane with paved shoulder of NH-301 Kargil- Zanskar Road from Design Km .30.040 (Ex. Km. 30.000) to Design Km 57.000 (Ex. Km. 57.905) of 26.960 Km length (Pkg-II) | NH(O)-TSP | NH | 301 | 26.96 | - | 23.26 | 404.89 | 229.19 | 2021-03-31 | 2021-03-31 | 2021-07-01 | 84.68 | 78.46 | 2023-01-02 | 2026-10-05 | - | Topline Infra Projects Pvt. Ltd. | topline.infra@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
150 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151696 | DN/09016/03001/LA | Ongoing | Under Construction (AD issued) | Kargil Zanskar Road Pkg-3 | Widening & Up-gradation to 2 lane with Paved shoulder of NH-301 Kargil- Zanskar Road from Design km 57.000 (Ex. Km. 57.905) to Km 87.000 (Ex. Km. 88.2491) of 30.000 Km length (Pkg-lll) | NH(O)-TSP | NH | 301 | 30 | - | 26.06 | 381.01 | 217.09 | 2021-03-31 | 2021-03-31 | 2021-07-01 | 89.3 | 82.36 | 2023-01-02 | 2026-07-29 | - | Topline Infra Projects Pvt. Ltd. | topline.infra@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
151 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151458 | DN/09016/03009/LA | Ongoing | Under Construction (AD issued) | Kargil Zanskar Road Pkg-4 | Up-gradation to 2 lane with Paved shoulder of NH-301 Kargil- Zanskar road from km 87+00 to KM 98+524 in the UT of Ladakh(Formally State of J&K) on EPC Mode (PKG-IV) | NH(O)-TSP | NH | 301 | 11.52 | 0.01 | 10.74 | 214.21 | 167.19 | 2019-12-16 | 2020-08-05 | 2021-03-02 | 96.16 | 88.53 | 2024-03-01 | 2026-07-30 | - | United Jehlum Road Roof Builders | united.kargil.nh301@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
152 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151459 | DN/09016/03007/LA | Completed | Completed | Kargil Zanskar Road Pkg-5 | Up-gradation to 2 lane with Paved shoulder of NH-301 Kargil- Zanskar road from Km 98+524 to Km. 117+180 in the UT of Ladakh (Formally State of J&K) on EPC Mode (PKG-V) | NH(O)-TSP | NH | 301 | 18.65 | - | 18.65 | 313.39 | 151.74 | 2019-12-26 | 2020-08-11 | 2020-12-10 | 100 | 94.94 | 2023-12-09 | - | 2023-06-26 | S&P lnfrastructure Developers Pvt. Ltd. - Skylark lnfra Engineering Pvt Ltd. (JV) | planning.epc@skylarkworld.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
153 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151460 | DN/09016/03006/LA | Completed | Completed | Kargil Zanskar Road Pkg-6 | Up-Gradation to 2 lane with Paved shoulder of NH-301 Kargil- Zanskar Road from Km 117+180 to Km. 148+320 in the UT Ladakh (Formerly State of J&K) on EPC mode (PKG-VI) | NH(O)-TSP | NH | 301 | 31.14 | - | 31.14 | 400.09 | 185.37 | 2020-02-14 | 2021-01-27 | 2021-05-24 | 100 | 96.39 | 2024-05-23 | - | 2023-12-01 | S&P lnfrastructure Developers Pvt. Ltd. - Skylark lnfra Engineering Pvt Ltd. (JV) | planning.epc@skylarkworld.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
154 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151461 | DN/09016/03010/LA | Completed | Completed | Kargil Zanskar Road Pkg-7 | Up-Gradation to 2 lane with Paved shoulder of NH-301 Kargil- Zanskar Road from Km 148+320 to Km. 196+250 in the UT of Ladakh (Formerly State of J&K) on EPC mode (PKG-VII) | NH(O)-TSP | NH | 301 | 47.93 | - | 47.93 | 498.71 | 239 | 2020-03-19 | 2021-01-27 | 2021-06-14 | 100 | 97.59 | 2024-06-13 | - | 2023-12-01 | S&P lnfrastructure Developers Pvt. Ltd. - Skylark lnfra Engineering Pvt Ltd. (JV) | planning.epc@skylarkworld.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
155 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 151697 | DN/09016/02009/LA | Ongoing | Under Construction (AD issued) | Kargil Zanskar Road Pkg-8 | Widening & Up-gradation to 2 lane with paved shoulder of NH-301 Kargil Zanskar Road from Design Km 196.250 (Ex. Km. 194.1901 to Design Km 230.020 (Ex Km. 231.692) of 33.770 Km length (PKG-Vlll) | NH(O)-TSP | NH | 301 | 33.77 | 1.4 | 31.5 | 398.37 | 195.28 | 2021-03-31 | 2021-03-31 | 2021-07-01 | 95.02 | 95.02 | 2023-01-02 | 2026-07-15 | - | Satish Aggarwal & Co. | sarccompany@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL) JV in assosiation with JR Consultancy Services Pvt. Ltd. | Normal Highway/Road Project
156 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 153735 | DN/09016/03008/LA | Completed | Completed | Kargil-Zanskar Road (Bridge-3) (3x25 M Span MNB) | Construction of 3 No. of 1x25 M Span Bridge at Km. 165.296, Km. 172.965 and Km. 185.509 including its approaches on NH-301, Kargil-Zanskar Road on EPC Mode (Bridge-3) | NH(O)-TSP | NH | 301 | 0.075 | - | 0 | 28.48 | 14.06 | 2019-03-22 | 2020-08-28 | 2021-06-01 | 100 | 99.98 | 2024-07-01 | - | 2024-01-03 | SGF Infra Pvt Ltd | hafizconstco@gmail.com | - | Standalone MNB(Minor Bridge) Project
157 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 153736 | DN/09016/03005/LA | Completed | Completed | Kargil-Zanskar Road (Bridge-1) (1x15 M, 1x20M & 1x10M Span MNB) | Construction of 1x15 M Span Bridge at Km 125.493, 1x20 M Span Bridge at Km 125.852 and 1x10 M Span Bridge at Km 129.445 including its approaches on NH-301, Kargil-Zanskar Road on EPC Mode (Bridge-1) | NH(O)-TSP | NH | 301 | 0.19 | - | 0.19 | 34.11 | 15 | 2019-03-22 | 2020-08-28 | 2021-06-01 | 100 | 99.98 | 2024-07-01 | - | 2024-06-30 | Hafiz Construction Pvt Ltd | hafizconstco@gmail.com | - | Standalone MNB(Minor Bridge) Project
158 | DT-3 | Non-NER | Ladakh | PMU-Kargil | 153737 | DN/09016/03004/LA | Completed | Completed | Kargil - Zanskar Road (Bridge-2) (1x45 M Span MNB) | Construction of 1x45 M Span Bridge including its approaches at Km 130.230 on NH-301 on Kargil - Zanskar Road on EPC mode (Bridge-2) | NH(O)-TSP | NH | 301 | 0.95 | - | 0.95 | 18.21 | 8.51 | 2019-03-22 | 2020-08-21 | 2021-07-01 | 100 | 98.38 | 2024-07-01 | - | 2024-06-30 | Hafiz Construction Pvt Ltd | sgfjammu@gmail.com | - | Standalone MNB(Minor Bridge) Project
159 | DT-3 | NER | Manipur | PMU-Noney | 60077 | DN/01018/02009/MN | Completed | Completed | Barak & Makru Bridge | Construction and Maintenance of : (i) 154m span steel superstructure Bridge at km 145.090 over river Barak & (ii) 122m span steel superstructure Bridge at km 189.800 over river Makru and Approaches of both the Bridges to be constructed is 1595m (Total Length 1.870Km) on Jiribam-Barak road on NH-53 (New NH-37) in Manipur on EPC mode | NH(O) | NH | 53/ 37 | 1.875 | - | 1.875 | 141.14 | 109.92 | 2016-11-22 | 2016-12-02 | 2017-04-27 | 100 | 83.18 | 2020-04-24 | - | 2022-04-27 | Bhartia Infra Projects Limited(BIPL) | info@bhartiainfra.com | Indian Technocrat Ltd. (ITL) | Standalone Bridge Project
160 | DT-3 | NER | Manipur | PMU-Noney | 151269 | DN/01018/02003/MN | Completed | Completed | Irang River Bridge (on Imphal-Jiribam road section) | Construction of 4-Lane Bridge over Irang River on Imphal-Jiribam road section (at 95.50 Km) on NH-53 (New NH-37) on EPC mode in Manipur | NH(O) | NH | 53/ 37 | 0.13 | - | 0.09 | 49.31 | 41.88 | 2018-10-12 | 2020-11-27 | 2021-01-04 | 100 | 98.36 | 2022-10-16 | - | 2024-12-27 | Paratech Constructions Pvt. Ltd. | paratech@paratechconstructions.com | Bloom - Shree Bhawani SBCSPL (JV) | Standalone Bridge Project
161 | DT-3 | NER | Manipur | PMU-Noney | 151709 | DN/01018/02002/MN | Completed | Physically Completed & CC Under Issue | Imphal - Khongsang - Jiribam Pkg-1 | Widening to 2 -Lane with Paved shoulder of Imphal-Khongsang-Jiribam section of NH-37 from Design Chainage 3.275 km to 15.940 Km (Total length=12.665 Km) (PKG-1) | NH(O)-NE | NH | 53/ 37 | 12.67 | - | 12.67 | 139.38 | 78.99 | 2021-03-31 | 2021-03-30 | 2021-07-01 | 100 | 83.22 | 2023-01-02 | Physically Completed C.C Under Issue | 2025-02-24 | Avantika Contractor (I) Ltd. | sriavantikaimphal21@gmail.com | Bloom - Shree Bhawani SBCSPL (JV) | Normal Highway/Road Project
162 | DT-3 | NER | Manipur | PMU-Noney | 160493 | DN/01018/02008/MN | Ongoing | Under Construction (AD issued) | Imphal - Khongsang - Jiribam Pkg-2 | Widening to 2-Lane with Paved shoulder of Imphal to Jiribam section of NH-37 from Design Chainage 15.940 km to 33.120 Km (Existing Chainage Km 15.946 to Km 33.395) (Total length=17.180 Km) in the State of Manipur on (EPC) mode (PKG-2) - Balance Works & Rectification works | NH(O)-NE | NH | 53/ 37 | 17.18 | 0.35 | 16.53 | 195.14 | 72.72 | 2021-03-31 | 2025-02-07 | 2025-03-18 | 92.99 | 91.4 | 2026-03-18 | 2026-08-03 | - | SCONS Infrastructures Pvt. Ltd. | sipl@sconsinfra.in; | Bloom - Shree Bhawani SBCSPL (JV) | Normal Highway/Road Project
163 | DT-3 | NER | Manipur | PMU-Noney | 152089 | DN/01018/02007/MN | Completed | Physically Completed & CC Under Issue | Imphal - Khongsang - Jiribam Pkg-3 | Widening to 2 -Lane with Paved shoulder of Imphal to Jiribam section of NH-37 from Design Chainage 33.000 km to 66.390 Km (Existing Chainage from km 33.395 to km 67.496) on EPC Mode in Manipur (PKG-3) | NH(O)-NE | NH | 53/ 37 | 33.16 | - | 30.53 | 467 | 253.84 | 2021-03-31 | 2021-07-15 | 2021-09-15 | 86.33 | 85.15 | 2023-03-19 | Physically Completed C.C Under Issue | 2026-02-01 | Mehta Construction Co. - Ganpati Builders (JV) | mehtaganpatijv@gmail.com | Bloom - Shree Bhawani SBCSPL (JV) | Normal Highway/Road Project
164 | DT-3 | NER | Manipur | PMU-Noney | 152292 | DN/01018/02006/MN | Ongoing | Under Construction (AD issued) | Imphal - Khongsang - Jiribam Pkg-4 | Widening to 2 -Lane with Paved shoulder of Imphal to Jiribam section of NH-37 from Design Chainage 66.110 km to 101.280 Km (Existing Chainage km 67.496 to km 103.557) on EPC Mode in Manipur (PKG-4) | NH(O)-TSP | NH | 53/ 37 | 35.17 | 0.44 | 34.11 | 579.63 | 268.33 | 2021-09-02 | 2021-08-23 | 2022-06-27 | 85.98 | 83.23 | 2023-12-29 | 2026-07-31 | - | BLA Projects Private Limited - G P Projects Ltd. (JV) | nh37.pkg4@gpprojects.n | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
165 | DT-3 | NER | Manipur | PMU-Noney | 153048 | DN/01018/02005/MN | Ongoing | Under Construction (AD issued) | Imphal - Khongsang - Jiribam Pkg-5 | Widening to 2 Lane with Paved shoulder of lmphal to Jiribam section of NH-37 from Design Ch. from Km 101+280 Near Khongsang Village to Km 131+280 near Puilon (Kambiron) Village on EPC Mode in Manipur (PKG-5) | NH(O)-TSP | NH | 53/ 37 | 30 | - | 28.15 | 410.68 | 218.52 | 2021-12-03 | 2022-03-25 | 2022-11-09 | 90.61 | 86.3 | 2024-05-12 | 2026-08-12 | - | Aarpee Infraprojects Pvt. Ltd. | imphaljiribampkg5@gmail.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
166 | DT-3 | NER | Manipur | PMU-Noney | 153148 | DN/01018/02004/MN | Ongoing | Under Construction (AD issued) | Imphal - Khongsang - Jiribam Pkg-6 | Widening to 2 Lane with Paved shoulder of lmphal to Jiribam section of NH-37 from Design Ch. from km 131.280 to km 169.570 (PKG-6) on EPC mode under NH(O)-TSP | NH(O)-TSP | NH | 53/ 37 | 38.29 | - | 35.92 | 504.76 | 243.99 | 2021-12-13 | 2022-03-31 | 2023-02-07 | 95.2 | 93.32 | 2025-02-06 | 2026-09-16 | - | Sarjan Infracon Pvt. Ltd. | info@sarjaninfra.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
167 | DT-3 | NER | Manipur | PMU-Noney | 154594 | DN/01018/02001/MN | Ongoing | Under Construction (AD issued) | Imphal - Khongsang - Jiribam Pkg-7 | Widening to 2 lane with Paved shoulder of lmphal to Jiribam section of NH-37 from Design Ch. from km 169+570 Near Nungkao vlllage under Tamenglong District to km 205+974 near Jiribam Bridge under Jiribam district under NH(O)-NE (PKG-7) | NH(O)-NE | NH | 53/ 37 | 36.404 | - | 34.31 | 760.16 | 248.63 | 2023-01-03 | 2023-01-19 | 2023-12-30 | 92.52 | 91.55 | 2025-12-28 | 2026-12-25 | - | P.D. Agrawal Infrastructure Ltd. -Apex Structure Pvt Ltd. (JV) | pdagrawal_indore@yahoo.com, apexcompany2009@yahoo.in | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
168 | DT-3 | NER | Manipur | PMU-Tamenglong | 148456 | DN/18002/01002/MN | Completed | Completed | Khongsang to Tamenglong | Improvement / Widening To 2 Laning of Stretch from Khongsang to Tamenglong (Design length= 37.974 Km) of NH-137 in the state of Manipur on EPC mode under SARDP-NE | SARDP-NE | NH | 137 | 37.974 | - | 37.97 | 471.04 | 296.26 | 2019-02-27 | 2019-03-08 | 2019-08-01 | 100 | 97.5 | 2022-07-31 | - | 2023-04-08 | Shivalaya Construction co. Pvt. Ltd. (SCCPL) | scc.mn296@gmail.com | Ayoleeza Consultants Pvt. Ltd. - Sowil India Pvt. Ltd. (JV) | Normal Highway/Road Project
169 | DT-3 | NER | Manipur | PMU-Tamenglong | 151640 | DN/02002/01005/MN | Completed | Completed | Tamenglong to Mahur Pkg-1 | Construction of 2 -Lane with paved shoulders road from Tamenglong to Mahur in the state of Manipur from km 0.000 at Tamenglong to km 10.000 near Dialong (Package-1) | NH(O)-TSP | NH | 137 | 10 | - | 9.94 | 185.8 | 111.8 | 2021-03-30 | 2021-07-19 | 2021-09-15 | 100 | 98.15 | 2023-03-16 | - | 2025-01-10 | Roadridge Developers Pvt. Ltd.(RDPL)-Sunshine Overseas Pvt. Ltd.(SOPL) (JV) | rdplsopljvpkg1@gmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
170 | DT-3 | NER | Manipur | PMU-Tamenglong | 152087 | DN/02002/01006/MN | Completed | Physically Completed & CC Under Issue | Tamenglong to Mahur Pkg-2 | Construction of of 2 -Lane with paved shoulders road from Tamenglong-Tousem-Lisang-Mahur Road (NH-137) starting near Dialong Village from km 10.000 at Dialong to km 31.430 near Old Tamenglong , near Barak River on EPC Mode (Package-2) | NH(O)-TSP | NH | 137 | 21.43 | - | 20.84 | 483.87 | 292.45 | 2021-07-20 | 2021-07-20 | 2021-09-15 | 95.28 | 93.41 | 2023-03-16 | Physically Completed & CC Under Issue | 2026-04-30 | J Infratech Limited (JIL)-Niraj Cement Structurals Ltd. (JV) | jcipl.manipur@gmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
171 | DT-3 | NER | Manipur | PMU-Tamenglong | 151707 | DN/02002/01007/MN | Completed | Physically Completed & CC Under Issue | Tamenglong to Mahur Pkg-3 | Construction of 2 -Lane with paved shoulders road from Tamenglong to Mahur in the state of Manipur from km 31.430 at Old Tamenglong to km 43.480 ending near Phelong on EPC Mode (Package-3) | NH(O)-TSP | NH | 137 | 12.05 | - | 12.05 | 234.08 | 150.06 | 2021-03-30 | 2021-03-26 | 2021-06-21 | 98.5 | 98.16 | 2022-12-20 | Physically Completed C.C Under Issue | 2026-04-15 | Kalyan Toll Infrastructure Ltd. | tamenglongmahurpkg3@gmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
172 | DT-3 | NER | Manipur | PMU-Tamenglong | 151641 | DN/02002/01008/MN | Completed | Completed | Tamenglong to Mahur Pkg-4 | Construction of 2 -Lane with paved shoulders road from Tamenglong to Mahur in the state of Manipur from km 43.480 at Phelong to km 54.180 near Azuram on EPC Mode (Package-4) | NH(O)-NE | NH | 137 | 10.7 | - | 10.7 | 198.77 | 119.74 | 2021-03-30 | 2021-07-19 | 2021-09-15 | 100 | 97.6 | 2023-03-16 | - | 2025-03-24 | Roadridge Developers Pvt. Ltd.(RDPL)-Sunshine Overseas Pvt. Ltd.(SOPL) (JV) | rdplsopljvpkg4@gmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
173 | DT-3 | NER | Manipur | PMU-Tamenglong | 152293 | DN/02002/01009/MN | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-5 | Construction of 2 -Lane with paved shoulders road from Tamenglong to Mahur (NH-137) in Manipur starting from km 54.180 near Azuram to km 80.630 near Mandeu on EPC Mode (Package 5) | NH(O)-TSP | NH | 137 | 26.45 | - | 21.43 | 477.86 | 286.71 | 2021-09-09 | 2021-08-23 | 2021-11-18 | 84.87 | 81.79 | 2023-05-19 | 2026-12-31 | - | Shri Swami Samarth Engineers Ltd. | sssel.manipurpkg5@gmail.com | Planning & Infrastructural Development Consultants Pvt. Ltd. (PIDCPL) | Normal Highway/Road Project
174 | DT-3 | NER | Manipur | PMU-Tamenglong | 152328 | DN/02002/01010/MN | Ongoing | Under Construction (AD issued) | Tamenglong to Mahur Pkg-6 | Construction of 2 -Lane with paved shoulders road from Tamenglong to Mahur (NH-137) starting from km 80.630 near Mandeu to km 96.870 near Jiri River on EPC Mode (Package-6) (Manipur portion) | NH(O)-TSP | NH | 137 | 16.24 | - | 13.05 | 311.18 | 191.08 | 2021-09-13 | 2021-09-10 | 2021-11-19 | 87.3 | 84.54 | 2023-05-20 | 2027-02-28 | - | B R Goyal Infrastructure Ltd. | tamenglongmahurpkg6@gmail.com | Planning & Infrastructural Development Consultants Pvt. Ltd. (PIDCPL) | Normal Highway/Road Project
175 | DT-3 | NER | Manipur | PMU-Ukhrul | 149283 | DN/01007/03002/MN | Ongoing | Under Construction (AD issued) | Yaingangpokpi - Finch Pkg-1 | Widening/Improvement to 2-lane with earthen shoulder of Yaingangpokpi - Finch corner road section of NH-202 from Km 0.000 to Km 16.900 of NH-202 in the state of Manipur on EPC mode (Package-1) | NH(O)-NE | NH | 150/202 | 16.9 | - | 14.94 | 224.44 | 124.81 | 2020-03-13 | 2020-03-28 | 2020-07-01 | 88.96 | 86.49 | 2022-06-30 | 2026-08-31 | - | Varaha Infra Limited | varaha.imphal@gmail.com | Dhruv Consultancy Services Ltd. - MS Consultant (JV) | Normal Highway/Road Project
176 | DT-3 | NER | Manipur | PMU-Ukhrul | 149292 | DN/01007/03001/MN | Ongoing | Under Construction (AD issued) | Yaingangpokpi - Finch Pkg-2 | Widening/Improvement to 2-lane with earthen shoulder of Yaingangpokpi - Finch corner road section of NH-202 from Km 16.900 to Km 30.970 of NH-202 in the state of Manipur on EPC mode (Package-2) | NH(O)-NE | NH | 150/202 | 14.07 | - | 14.05 | 186.86 | 135.63 | 2020-03-13 | 2020-03-28 | 2020-07-01 | 98.12 | 96.19 | 2022-06-30 | 2026-08-22 | - | Varaha Infra Limited | varaha.imphal@gmail.com | Dhruv Consultancy Services Ltd. - MS Consultant (JV) | Normal Highway/Road Project
177 | DT-3 | NER | Manipur | PMU-Ukhrul | MN-1 | DN/01007/03007/MN | Awarded, Not Appointed | Awarded, Not Appointed | Finch Corner to Ukhrul Pkg-3 | Widening/Improvement to 2-lane with earthen shoulder of Finch Corner to Ukhrul section from existing km 34+650 to km 50+520 (Design Chainage km 30+970 to km 45+600) of NH-202 in the State of Manipur on EPC mode under NH(O)-NE (Package-3) | NH(O)-NE | NH | 150/202 | 14.63 | - | 0 | 242.68 | 112.97 | 2024-02-28 | 2026-03-23 | To be given | 0 | 0 | - | - | - | SCONS Infrastructures Pvt. Ltd. | sipl@sconsinfra.in | Global Infra Solution in association with - MS Consultants (JV) | Normal Highway/Road Project
178 | DT-3 | NER | Manipur | PMU-Ukhrul | 157539 | DN/01007/03005/MN | Ongoing | Under Construction (AD issued) | Strengthening of Ukhrul to Choithar section Pkg-4 | Strengthening of Ukhrul to Choithar section of NH-202 from existing km 50+520 to km 59+236 (Design Chainage km 45+600 to km 54+212) Length-8.612 km in the State of Manipur on EPC mode under NH(O)-NE (Package-4) | NH(O)-NE | NH | 150/202 | 8.612 | - | 2 | 26.25 | 16.37 | 2024-02-19 | 2024-03-15 | 2024-07-01 | 15.77 | 15.03 | 2025-06-30 | 2027-03-31 | - | Vertex Construction | Vertexmnp2022@gmail.com | Global Infra Solution in association with - MS Consultants (JV) | Normal Highway/Road Project
179 | DT-3 | NER | Manipur | PMU-Ukhrul | 155297 | DN/01007/03006/MN | Ongoing | Under Construction (AD issued) | Choithar to Marrem Khullen section Imphal- Ukhrul - Jessami Pkg-5 | Widening/Improvement to 2 lane with earthen shoulder of Choithar to Marrem Khullen section of NH-202 of Imphal Ukhrul Jessami Economic Corridor from Design Chainage km 53.110 to km 95.700 in the State of Manipur on EPC mode under Bharatmala Pariyojana, under NH(O)-NE (Package-5) | NH(O)-NE | NH | 150/202 | 42.59 | - | 0 | 564.05 | 225.82 | 2023-03-31 | 2023-03-31 | 2025-04-01 | 14.5 | 10.02 | 2027-03-31 | 2027-08-31 | - | S S Builders | Appointed date not yet declared | M/s Dhruv Consultancy Services Limited in JV with M/s Global Infra Solutions in Association with M/s M.S. Consultant. | Normal Highway/Road Project
180 | DT-3 | NER | Manipur | PMU-Ukhrul | 155298 | DN/01007/03004/MN | Ongoing | Under Construction (AD issued) | Marrem Khullen to Jessami section Imphal- Ukhrul - Jessami Pkg-6 | Widening/Improvement to 2 lane with earthen shoulder of Marrem Khullen to Jessami section of NH-202 of Imphal - Ukhrul - Jessami Economic Corridor from Design Chainage km 95.700 to km 140.180 in the State of Manipur on EPC mode under Bharatmala Pariyojana under NH(O)-NE (Package-6) | NH(O)-NE | NH | 150/202 | 44.48 | 1.54 | 2.57 | 554.66 | 221.23 | 2023-03-29 | 2023-03-31 | 2024-12-08 | 24.43 | 21.93 | 2026-12-07 | 2027-08-02 | - | HVS Construction Materials Pvt. Ltd. | hvs_construction@rediffmail.com | M/s Dhruv Consultancy Services Limited in JV with M/s Global Infra Solutions in Association with M/s M.S. Consultant. | Normal Highway/Road Project
181 | DT-3 | NER | Manipur | PMU-Ukhrul | 155299 | DN/01007/03003/MN | Ongoing | Under Construction (AD issued) | Jessami to Laynen bridge Ukhrul - Jessami Pkg-7 | Widening/Improvement to 2 Lane with earthen shoulder of Jessami to Laynen bridge (Nagaland border) section of NH-29 of Imphal -Ukhrul - Jessami Economic Corridor from km 0.000 to km 11.009 in the State of Manipur on EPC mode under Bharatmala Pariyojana, under NH(O)-NE (Package-7) | NH(O)-NE | NH | 29 | 11.009 | - | 0 | 164.89 | 68.43 | 2023-03-31 | 2023-03-31 | 2024-12-24 | 26.67 | 24.11 | 2026-06-26 | 2027-02-07 | - | HVS Construction Materials Pvt. Ltd. | hvs_construction@rediffmail.com | M/s Dhruv Consultancy Services Limited in JV with M/s Global Infra Solutions in Association with M/s M.S. Consultant. | Normal Highway/Road Project
182 | DT-3 | NER | Manipur | PMU-Ukhrul | 153460 | DN/03003/02002/MN | Completed | Completed | Akash bridge - Jessami Pkg-2 [Manipur Portion] | Construction of 2 laning with hard shoulder road of Akash bridge - Jessami section of NH-202 in Nagaland- Manipur from design Ch. 325.440 km to 340.160 km in the State of Manipur on EPC mode under NH(O)-NE (Pkg-II) (Manipur portion) | NH(O)-NE | NH | 202 | 14.72 | - | 14.72 | 152.11 | 73.48 | 2022-03-28 | 2022-06-21 | 2023-02-20 | 100 | 97.81 | 2025-02-19 | - | 2025-03-20 | HVS Construction Materials Pvt. Ltd. | hvs_construction@rediffmail.com | Artefact Project Ltd. - MS Consultants | Normal Highway/Road Project
182 | DT-3 | NER | Manipur | PMU-Senapati | 151444 | DN/09024/02005/MN | Under Termination | Under Termination | Maram -Peren Pkg-1A | Improvement of existing road to 2 laning with Hard Shoulders of Maram -Peren section (Package-1A, length- 22.340Km) from Design Chainage 0.000 km to 22.340 km on NH-129A in the State of Manipur on EPC mode | NH(O)-TSP | NH | 129A | 22.34 | - | 17.25 | 226.32 | 151.15 | 2021-02-11 | 2021-02-05 | 2021-06-21 | 75.08 | 72.94 | 2022-12-22 | 2027-03-31 | - | CSR Infratech India Pvt. Ltd.- Raam Infratech India Pvt. Ltd. (JV) | csrinfratechindia@gmail.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
183 | DT-3 | NER | Manipur | PMU-Senapati | 151445 | DN/09024/02004/MN | Completed | Physically Completed & CC Under Issue | Maram -Peren Pkg-1B | Improvement of existing road to 2 laning with Hard Shoulders of Maram-Peren section (Package-1B, length- 17.660 km) from Design Chainage 22.340 km to 40.000 km on NH-129A in the State of Manipur on EPC mode | NH(O)-TSP | NH | 129A | 17.66 | - | 17.66 | 188.36 | 128.54 | 2021-02-11 | 2021-02-05 | 2021-06-21 | 100 | 98.17 | 2022-12-22 | Physically Completed C.C Under Issue | 2026-03-06 | CSR Infratech India Pvt. Ltd.- Raam Infratech India Pvt. Ltd. (JV) | csrinfratechindia@gmail.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
184 | DT-3 | NER | Manipur | PMU-Senapati | 151446 | DN/09024/02001/MN | Completed | Completed | Maram-Peren section Pkg-2A | Improvement of existing road to 2 laning with Hard Shoulders of Maram-Peren section (Package-2A, length- 16.840 Km) from Design Chainage 40.000 km to 56.840 km on NH-129A in the State of Manipur on EPC mode | NH(O)-TSP | NH | 129A | 16.84 | - | 16.84 | 204.58 | 121 | 2021-02-11 | 2021-07-07 | 2021-09-15 | 100 | 97.3 | 2023-03-19 | - | 2023-02-12 | Heera Ram Godara - Dudi & Company (JV) | heeraramgodara@gmail.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
185 | DT-3 | NER | Manipur | PMU-Senapati | 151447 | DN/09024/02003/MN | Completed | Completed | Maram-Peren section Pkg-2B | Improvement of existing road to 2 laning with Hard Shoulders of Maram-Peren section (Package-2B, length- 18.160 Km) from Design Chainage 56.840 km to km 75.000 on NH-129A in the State of Manipur on EPC mode | NH(O)-TSP | NH | 129A | 18.16 | - | 18.16 | 232.63 | 145.87 | 2021-02-11 | 2021-02-12 | 2021-06-21 | 100 | 96.54 | 2022-12-22 | - | 2024-01-12 | Satya Builders | pm.sanjaysingh@satyagroupindia.in | GEO Designs and Research Private Limited | Normal Highway/Road Project
186 | DT-3 | NER | Manipur | PMU-Senapati | 152294 | DN/09024/02002/MN | Completed | Completed | Maram- Peren section Pkg-3 | Improvement of existing road to 2 lanning with Hard Shoulders of Maram Peren section (Package-III, length - 34.494 km) from Design Chainage km 75+000 to 109+494 km on NH-129A in the State of Manipur on EPC mode under NH(O)-TSP | NH(O)-TSP | NH | 129A | 34.494 | - | 34.49 | 467.41 | 269.42 | 2021-09-21 | 2021-08-27 | 2021-11-26 | 100 | 98.17 | 2023-11-25 | - | 2025-02-28 | New India Contractors & Developers Pvt. Ltd. - Bharat Construction Co. (JV) | bccjv3121@gmail.com | K&J Projects Pvt. Ltd in association with - MPG Engineering Consultancy Pvt. Ltd. (JV) | Normal Highway/Road Project
187 | DT-3 | NER | Manipur | PMU-Ukhrul | 157538 | DN/08015/02005/MN | Awarded, Not Appointed | Awarded, Not Appointed | Ukhrul - Tolloi - Tadubi Pkg-1 (Ukhrul Bypass) | Construction ol 2-lane Ukhrul bypass starting from km 537.850 old NH-202 & joining at km 8.840 of NH-102A (Ukhrul - Tolloi - Tadubi Road) and continuing up to km 9.840 of NH-102A (Length 6.571 km) in the State ol Manipur on EPC mode under NH(O)-NE (Package-1) | NH(O)-NE | NH | Connecting NH-202 & NH-102A | 6.571 | - | 0 | 204.3 | 90.77 | 2023-12-07 | 2024-03-15 | To be given | 0 | 0 | - | - | - | SCONS Infrastructures Pvt. Ltd.-Kaushal Sharma (JV) | - | Global Infra Solution in association with - MS Consultants (JV) | Standalone Bypass Project
188 | DT-3 | NER | Manipur | PMU-Senapati | 155085 | DN/08015/02002/MN | Ongoing | Under Construction (AD issued) | Ukhrul-Tolloi - Tadubi Pkg-2 | Construction of 2-laning with Hard shoulder of Ukhrul Tolloi - Tadubi section of NH-102A from Design Chainage km 9+450 to km 50+850 in the State of Manipur on EPC mode under NH(O)-NE (Package-2) | NH(O)-NE | NH | 102A | 41.4 | - | 35.99 | 578.98 | 235.82 | 2023-03-07 | 2023-03-15 | 2024-03-01 | 80.02 | 78.61 | 2026-03-01 | 2026-12-31 | - | S S Builders - Ganpati Builders (JV) | ganpatibuilders0082@gmail.com | Dhruv Consultancy Services Ltd. In Ass. With MS Consultant | Normal Highway/Road Project
189 | DT-3 | NER | Manipur | PMU-Senapati | 154500 | DN/08015/02003/MN | Ongoing | Under Construction (AD issued) | Ukhrul-Tolloi - Tadubi Pkg-3 | Construction of 2-laning with Hard shoulder road of Ukhrul - Tolloi - Tadubi section of NH-102A from Design Chainage 50.850 km to 81.870 km in the State of Manipur on EPC mode under NH(O)-TSP (Package -3) | NH(O)-TSP | NH | 102A | 31.02 | - | 24.07 | 315.56 | 155 | 2021-09-09 | 2022-12-16 | 2023-07-23 | 91.11 | 90.63 | 2025-01-20 | 2026-07-31 | - | Satish Aggarwal & Co. | nh102a.pkg03@gmail.com | Artefact Projects Ltd. - Infycons Creative Software Pvt. Ltd. | Normal Highway/Road Project
190 | DT-3 | NER | Manipur | PMU-Senapati | 152295 | DN/08015/02004/MN | Ongoing | Under Construction (AD issued) | Ukhrul -Tolloi - Tadubi Pkg-4 | Construction of 2-laning with Hard shoulder road of Ukhrul - Tolloi - Tadubi section of NH-102A from Design Chainage 81.870 km to 105.825 km in the State of Manipur on EPC mode under NH(O)-TSP(Package -4) | NH(O)-TSP | NH | 102A | 23.96 | 0.32 | 23.21 | 310.76 | 150.14 | 2021-09-07 | 2021-08-27 | 2022-08-27 | 97 | 94.03 | 2024-02-28 | 2026-08-31 | - | A K Shivhare Infrastructure Pvt. Ltd. | aks.nh102a@gmail.com | Artefact Projects Ltd. - Infycons Creative Software Pvt. Ltd. | Normal Highway/Road Project
191 | DT-3 | NER | Manipur | PMU-Churachandpur | 149281 | DN/01020/03001/MN | Completed | Completed | Churachandpur to Tuivai Pkg- 1A | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH 102B from km 0.000 to km 13.747 in the State of Manipur on EPC mode under NH(O) (Pkg- I A) | NH(O) | NH | 102B | 13.747 | - | 13.75 | 151.32 | 92.71 | 2020-04-27 | 2020-03-31 | 2020-07-01 | 100 | 83.71 | 2022-06-30 | - | 2023-05-15 | Krishna Construction Co. | kccnh102b@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
192 | DT-3 | NER | Manipur | PMU-Churachandpur | 149280 | DN/01020/03007/MN | Completed | Physically Completed & CC Under Issue | Churachandpur to Tuivai Pkg- 1B | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH-102B from km13.747 to km32.835 in the State of Manipur on EPC mode under NH(O) (Pkg- IB) | NH(O) | NH | 102B | 19.09 | - | 19.09 | 241.52 | 139.8 | 2020-04-27 | 2020-03-31 | 2020-07-01 | 100 | 96.55 | 2022-06-30 | Physically Completed C.C Under Issue | 2026-02-27 | RSM Infra Projects | rsminfraprojects@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
193 | DT-3 | NER | Manipur | PMU-Churachandpur | 149277 | DN/01020/03006/MN | Completed | Physically Completed & CC Under Issue | Churachandpur to Tuivai Pkg- 2A | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH-102B from km32.835 to km48.587 in the State of Manipur on EPC mode under NH(O) (Pkg- IIA) | NH(O) | NH | 102B | 15.75 | - | 15.752 | 232.99 | 139.2 | 2020-04-27 | 2020-03-31 | 2020-07-01 | 100 | 92.74 | 2022-06-30 | Physically Completed & CC Under Issue | 2026-03-28 | Bharat Vanijya Eastern Pvt. Ltd.(BVEPL) | bharatvanijyaimphalbranch@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
194 | DT-3 | NER | Manipur | PMU-Churachandpur | 150563 | DN/01020/03005/MN | Ongoing | Under Construction (AD issued) | Churachandpur to Tuivai Pkg- 2B | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section from Km 48.587 to Km 69.875 in the State of Manipur on EPC mode under NH(O) (Package-II B) | NH(O) | NH | 102B | 21.28 | - | 21.055 | 365.53 | 206.41 | 2020-06-18 | 2020-06-30 | 2020-08-05 | 88.2 | 80.37 | 2022-08-04 | 2026-08-31 | - | Bharat Vanijya Eastern Pvt. Ltd.(BVEPL) | bharatvanijyaimphalbranch@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
195 | DT-3 | NER | Manipur | PMU-Churachandpur | 152088 | DN/01020/03004/MN | Ongoing | Under Construction (AD issued) | Churachandpur to Tuivai Pkg- 3 | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH-102B from Design Chainage 69.875 Km to 121.769 Km in the State of Manipur on EPC mode (Pkg-3) | NH(O)-NE | NH | 102B | 51.89 | - | 47.32 | 673.27 | 404.48 | 2021-03-31 | 2021-07-14 | 2021-08-25 | 84.72 | 83.68 | 2023-08-24 | 2026-12-31 | - | M & S Co. | msco2008@gmail.com | Global Infra solution in association with - Infycons creative software Pvt Ltd (JV) | Normal Highway/Road Project
196 | DT-3 | NER | Manipur | PMU-Churachandpur | 160809 | DN/01020/03010/MN | Ongoing | Under Construction (AD issued) | Churachandpur to Tuivai Pkg- 4A | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH-102B from Km118.850 to km130.00 in the State of Manipur on EPC mode under NH(O) (Pkg- IVA) -(Balance Work) | NH(O) | NH | 102B | 11.15 | - | 8.401 | 204.12 | 70.95 | 2020-04-27 | 2025-06-06 | 2025-08-30 | 24.66 | 21.23 | 2026-08-29 | 2026-08-29 | - | A K Shivhare Infrastructure Pvt. Ltd. | akshivhare@rediffmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
197 | DT-3 | NER | Manipur | PMU-Churachandpur | 160830 | DN/01020/03009/MN | Ongoing | Under Construction (AD issued) | Churachandpur to Tuivai Pkg- 4B | Widening to 2-lane with Hard shoulder of Churachandpur to Tuivai Section of NH-102B from Km130.00 to km 141.029 in the State of Manipur on EPC mode under NH(O) (Pkg- IVB) -(Balance Work) | NH(O) | NH | 102B | 11.03 | - | 10.659 | 177.76 | 27.83 | 2020-06-15 | 2025-06-06 | 2025-11-08 | 7.45 | 3.68 | 2026-11-07 | 2026-11-07 | - | A K Shivhare Infrastructure Pvt. Ltd. | akshivhare@rediffmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - Mspark Futuristics & Associates (JV) | Normal Highway/Road Project
198 | DT-3 | NER | Manipur | PMU-Churachandpur | 149356 | DN/12019/01001/MN | Completed | Completed | Pallel-Chandel | Improvement/Strengtening to 2-lane with hard shoulder of Pallel-Chandel section of NH-102C (Km 0.000 to Km 18.292) in state of Mnaipur on EPC basis under NH(O) | NH(O) | NH | 102C | 18 | - | 17.765 | 107.72 | 71.01 | 2020-02-07 | 2020-03-27 | 2020-07-01 | 100 | 96.84 | 2022-07-01 | - | 2022-05-15 | Krishna Construction Co. | kccnh102c@gmail.com | Lion Engg. Consultants Pvt. Ltd. In ass. With Rudrabhishekh Enterprises (JV) | Normal Highway/Road Project
198 | DT-3 | NER | Manipur | PMU-Senapati | MN-2 | DN/01007/02007/MN | Sanctioned not awarded | Sanctioned not awarded | Strengthening of Mao to Senapati (on Kohima to Imphal section) of new NH-02 | Strengthening of Mao to Senapati (on Kohima to Imphal section) of new NH-02 (old NH-39) from existing Chainage Km 212+328 (Mao Gate) to Km 264+313 (Taphou Kuki); Length – 51.985Km in the State of Manipur on EPC mode under NH(O)-NE | NH(O)-NE | NH | 39/02 | 51.985 | - | 0 | 228.4 | 0 | 2026-03-27 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
199 | DT-3 | NER | Manipur | PMU-Senapati | 150572 | DN/01007/02003/MN | Ongoing | Under Construction (AD issued) | Imphal-Senapati-Kohima Road Pkg-4A | Improvement/Up-gradation of existing 2-lane to 4-Lane Divided Highway from Taphou Kuki to Daili section of Imphal-Kohima Road (Design Ch.: km 262.175 to 274.610) of NH-39 (New NH-02) in state of Manipur on EPC mode (Pkg-4A) | NH(O)-NE | NH | 39/02 | 8.025 | 0.6 | 7.9 | 379.39 | 212.54 | 2020-09-01 | 2020-08-31 | 2020-10-15 | 91.39 | 81.49 | 2022-04-18 | 2026-08-31 | - | Lekcon Infrastructure Pvt. Ltd. - R.S.V. constructions Pvt. Ltd. (JV) | civil@lekconinfra.com | Hexa Co. in JV with Sowil Limited in Association with Casta Engineers Pvt. Ltd. | Normal Highway/Road Project
200 | DT-3 | NER | Manipur | PMU-Senapati | 154486 | DN/01007/02002/MN | Ongoing | Under Construction (AD issued) | Imphal-Senapati-Kohima Road Pkg-4B | Improvement/Up-gradation of existing 2-lane to 4-Lane Divided Highway from Daili to Kuraopokpi section of Imphal-Kohima Road (Design Ch.: km 274.610 to 287.00 ) of NH-39 (New NH-02) in state of Manipur on EPC mode (Pkg-4B) | NH(O)-NE | NH | 39/02 | 12.39 | - | 7.22 | 268.98 | 132.98 | 2020-09-01 | 2022-12-16 | 2024-12-05 | 56.16 | 50.53 | 2026-06-05 | 2027-01-02 | - | A K Shivhare Infrastructure Pvt. Ltd. | aks.nh102a@gmail.com | Hexa Co. in JV with Sowil Limited in Association with Casta Engineers Pvt. Ltd. | Normal Highway/Road Project
201 | DT-3 | NER | Manipur | PMU-Senapati | 154501 | DN/01007/02004/MN | Ongoing | Under Construction (AD issued) | Imphal-Senapati-Kohima Road Pkg-5A | Widening/Improvement of existing 2-lane to 4-Lane Divided Highway from Kuraopokpi to Sekmai section of Imphal-Kohima Road (Design Ch.: km 287.00 to 297.700) of NH-39 (New NH-02) in state of Manipur on EPC mode (Pkg-5A) | NH(O)-NE | NH | 39/02 | 10.7 | 0.83 | 4.91 | 228.97 | 122.4 | 2020-09-01 | 2022-12-16 | 2025-02-26 | 48.31 | 32.83 | 2026-08-27 | 2026-08-27 | - | Allone Infra Pvt. Ltd. | prabhjot.singh@alloneinfra.com | Hexa Co. in JV with Sowil Limited in Association with Casta Engineers Pvt. Ltd. | Normal Highway/Road Project
202 | DT-3 | NER | Manipur | PMU-Senapati | 151706 | DN/01007/02001/MN | Ongoing | Under Construction (AD issued) | Imphal-Senapati-Kohima Road Pkg-5B | Widening/Improvement of existing 2-Lane road to 4-Lane Divided Highway from Sekmai to Nilakuthi section of Imphal-Kohima Road (Design Chainage from Km 297+700 to Km 308+729) of NH-39 (New NH-02) in state of Manipur on EPC mode (Pkg-5B) | NH(O)-NE | NH | 39/02 | 11.02 | 0.15 | 10.48 | 211.7 | 126.57 | 2021-03-30 | 2021-03-27 | 2021-07-20 | 93.54 | 88.47 | 2023-01-21 | 2026-09-07 | - | NSC Projects Pvt. Ltd | nscmanipu07@gmail.com | Hexa Co. in JV with Sowil Limited in Association with Casta Engineers Pvt. Ltd. | Normal Highway/Road Project
203 | DT-3 | NER | Manipur | PMU-Churachandpur | 66770 | DN/06001/02001/MN | Completed | Completed | Imphal – Moreh Pkg-1 | 4- Laning of Imphal – Moreh Section of NH-39 (New NH-102) on (AH-01) from Km 330.000 to Km 350.000 (design Km 349.555) (Package-I) on EPC mode by ADB fund under SASEC Tranche-2 | EAP (ADB) | NH | 39/102 | 19.555 | - | 19.55 | 820.56 | 352.28 | 2017-08-16 | 2019-09-05 | 2020-06-01 | 100 | 97.23 | 2023-05-31 | - | 2023-04-30 | GR Infra Projects ltd | planning.immo@grinfra.com | Feedback Infra Pvt. Ltd. | Normal Highway/Road Project
204 | DT-3 | NER | Manipur | PMU-Churachandpur | 60065 | DN/06001/02002/MN | Completed | Completed | Imphal – Moreh Pkg-2 | 2- Laning of Imphal – Moreh Section of NH-39 (New NH-102) on (AH-01) from Km 350.000 to Km 395.680 (Package- II) on EPC mode by ADB fund under SASEC Tranche-2 | EAP (ADB) | NH | 39/102 | 44.78 | - | 44.69 | 789.81 | 457.77 | 2017-08-16 | 2018-06-01 | 2018-10-16 | 100 | 97.8 | 2021-10-15 | - | 2021-06-30 | GR Infra Projects ltd | planning.imwa@grinfra.com | Feedback Infra | Normal Highway/Road Project
205 | DT-3 | NER | Manipur | PMU-Churachandpur | 151639 | DN/03004/01003/MN | Completed | Completed | Imphal – Moreh Pkg-3 | Widening and Improvement to 2-Lane with paved shoulders of Imphal-Moreh section of NH-39 (New NH-102) on (AH-01) from Km 395.680 to Km 406.000 in state of Manipur on EPC mode (Package-III) | NH(O)-NE | NH | 39/102 | 9.852 | - | 9.85 | 259.31 | 150.11 | 2019-09-19 | 2021-03-22 | 2021-06-21 | 100 | 97.11 | 2022-12-21 | - | 2024-06-30 | Dwarakamai Constructions Pvt. Ltd. | dmc.nsc.impkg3@gmail.com | Lion Engg. Consultants Pvt. Ltd. In ass. With Rudrabhishekh Enterprises (JV) | Normal Highway/Road Project
206 | DT-3 | NER | Manipur | PMU-Churachandpur | 151638 | DN/03004/01002/MN | Completed | Completed | Imphal – Moreh Pkg-4 | Widening and Improvement to 2-Lane with paved shoulders of Imphal-Moreh section of NH-39 (New NH-102) on (AH-01) from km 406.000 to Km 425.411 in state of Manipur on EPC mode (Package-IV) | NH(O)-NE | NH | 39/102 | 19.411 | - | 19.41 | 277.99 | 140 | 2019-09-19 | 2021-03-22 | 2021-07-20 | 100 | 97.68 | 2023-01-19 | - | 2024-04-30 | SKV Infratech Pvt. Ltd - SPG Infraprojects Pvt. Ltd (JV) | imphalmorehpkgiv@gmail.com | Lion Engg. Consultants Pvt. Ltd. In ass. With Rudrabhishekh Enterprises (JV) | Normal Highway/Road Project
207 | DT-3 | NER | Manipur | PMU-Churachandpur | 66774 | DN/03004/01001/MN | Completed | Completed | Imphal- Moreh (Bypass) | Construction of Moreh Bypass to 2-lane with Paved shoulder from km 421.950 to 425.411 of NH-39 (New NH-102) on (AH-01) near Indo-Myanmar border in state of Manipur on EPC mode under NH(O) | NH(O) | NH | 39/102 | 2.305 | - | 1.96 | 68.14 | 21.51 | 2020-02-26 | 2020-03-27 | 2020-07-01 | 100 | 97.96 | 2021-12-31 | - | 2023-11-17 | L.K. & Sons | kadamjitl@gmail.com | Lion Engg. Consultants Pvt. Ltd. In ass. With Rudrabhishekh Enterprises (JV) | Standalone Bypass Project
208 | DT-3 | NER | Manipur | PMU-Churachandpur | 160801 | DN/01020/04001/MN | Ongoing | Under Construction (AD issued) | Strengthening of Imphal-Moirang-Churachandpur | Strengthening of Churachandpur to Imphal section ol old NH-150 (new NH-02) from starting from Churachandpur Police Station (Km 402.000) to Malom oil Depot Gate (km 454.798) in Manipur on EPC mode under NH(O)-NE (Length=53.400Km) | NH(O)-NE | NH | 150/02 | 53.4 | 0.79 | 2.99 | 76.09 | 46.99 | 2025-03-31 | 2025-07-14 | 2025-10-03 | 5.77 | 0 | 2026-10-02 | 2026-10-02 | - | Jay Shree International | jayshreegroupltd@gmail.com | - | Normal Highway/Road Project
209 | DT-3 | NER | Meghalaya | PMU-Baghmara | 91260 | DN/25001/01006/ML | Completed | Completed | RMB Pkg-1 | 2 Lane with earthern shoulder from of Ranikor – Baghmara –Maheshkola Road Section from Ranikhor to Nongjri existing Km 0+000 to 31+700 (Design Length – 33.250 Km) EPC Mode in the state of Maghalaya under SARDP-NE Phase-A (Pkg-1) | SARDP-NE | Non NH | SH 04 | 30.204 | - | 30.205 | 306.28 | 216.33 | 2019-03-09 | 2019-03-09 | 2019-09-30 | 100 | 98.89 | 2022-03-29 | - | 2023-12-31 | Dhar Construction Company - Chanchal Paul (JV) | hvs_construction@rediffmail.com | Aushta Consulting Engineers (India) Pvt. Ltd. - DN Consultant - NM Engg. & Consultancy (JV) | Normal Highway/Road Project
210 | DT-3 | NER | Meghalaya | PMU-Baghmara | 152966 | DN/25001/01002/ML | Completed | Completed | RMB Pkg-2 | lmprovement/widening to 2-laning with earthen shoulder of Nongjri (Design Ch. 30.00km) to Maheshkola (Design Ch. 55.525km )[R-M-B Package 2] on SH-4 section of Ranikor- Maheshkhola- Baghmara Project in the state of Meghalaya under NH (O)-NE (Pkg-2) | SARDP-NE | Non NH | SH 04 | 25.525 | - | 25.53 | 261.4 | 140.93 | 2021-11-17 | 2022-03-07 | 2022-12-19 | 100 | 99.62 | 2024-06-19 | - | 2025-05-31 | Dhar Construction Company | dccshg2@gmail.com | Consulting Engineers Group Ltd. in Association with Sri Infotech & Shri Kushalsuri Engineering Services Pvt. Ltd. | Normal Highway/Road Project
211 | DT-3 | NER | Meghalaya | PMU-Baghmara | 151711 | DN/25001/01001/ML | Completed | Completed | RMB Pkg-3 | lmprovement/ widening to 2-laning with earthen shoulder from Maheshkola to kanai existing chainage from Ch. 59.270 to Ch. 85.970 (Design Ch. 55.525 to Ch. 79.680) on SH-4 Ranikor-Baghmara Project (Package-3) | SARDP-NE | Non NH | SH 04 | 24.155 | - | 24.15 | 260.21 | 150.2 | 2021-03-31 | 2021-03-27 | 2021-06-28 | 100 | 99.19 | 2022-12-28 | - | 2025-02-20 | DMR Builders Pvt. Ltd. | dmrmeghalayasite@gmail.com | Consulting Engineers Group Ltd. in Association with Sri Infotech & Shri Kushalsuri Engineering Services Pvt. Ltd. | Normal Highway/Road Project
212 | DT-3 | NER | Meghalaya | PMU-Baghmara | 150842 | DN/25001/01005/ML | Completed | Completed | RMB Pkg-4 | Improvement/widening to 2-lane with Earthen shoulder of Ranikor-Maheshkhola- Baghmara road section from Kanai to Rongara, existing Ch. From Km 85.970 to Km 102.345 (Design Ch. From Km 81.100 to Km 96.000) Design length-14.763 km on EPC (Pkg-4) | SARDP-NE | Non NH | SH 04 | 14.763 | - | 14.76 | 146.92 | 82.79 | 2020-10-08 | 2020-09-30 | 2020-10-24 | 100 | 99.29 | 2022-04-25 | - | 2025-02-27 | Narendra Sharma | nscdholpur@gmail.com nscbaghmara@gmail.com | Aushta Consulting Engineers (India) Pvt. Ltd. - DN Consultant - NM Engg. & Consultancy (JV) | Normal Highway/Road Project
213 | DT-3 | NER | Meghalaya | PMU-Baghmara | 150843 | DN/25001/01004/ML | Completed | Completed | RMB Pkg-5 | Improvement/widening to 2-lane with Earthen shoulder of Ranikor-Maheshkhola- Baghmara road section from Rongara to Panda, existing Ch. From Km 102.345 to Km 119.810 (design Ch. From Km 96.00 to Km 112.300) design length-16.30 km on EPC (Pkg-5) | SARDP-NE | Non NH | SH 04 | 16.3 | - | 15.99 | 146.88 | 74.41 | 2020-10-12 | 2020-09-30 | 2020-10-24 | 96.01 | 92.48 | 2022-04-24 | - | 2024-09-30 | Narendra Sharma | aks.nh102a@gmail.com akshivhare@rediffmail.com akshivhare2015@gmail.com | Aushta Consulting Engineers (India) Pvt. Ltd. - DN Consultant - NM Engg. & Consultancy (JV) | Normal Highway/Road Project
214 | DT-3 | NER | Meghalaya | PMU-Baghmara | 152812 | DN/25001/01003/ML | Completed | Completed | RMB Pkg-6 | lmprovement/ widening to 2-laning with earthen shoulder of Panda (Design Ch. 112.300 km) to Baghmara (Design Ch. 129.385 km ) on SH-4 section of Ranikor- Maheshkhola- Baghmara Project in the state of Meghalaya under NH(O)-NE [R-M-B Package-6] | SARDP-NE | Non NH | SH 04 | 17.085 | - | 17.09 | 144.99 | 82.34 | 2021-11-12 | 2022-01-27 | 2022-09-30 | 100 | 98.59 | 2024-03-31 | - | 2024-12-20 | Nidhi Creative Infrastructure Pvt. Ltd. | nidhi.cipl@yahoo.in nidhicreativebagmara@gmail.com | Consulting Engineers Group Ltd. in Association with Sri Infotech & Shri Kushalsuri Engineering Services Pvt. Ltd. | Normal Highway/Road Project
215 | DT-3 | NER | Meghalaya | PMU-Tura | 80717 | DN/06005/01002/ML | Completed | Completed | Tura-Dalu | Widening to 2- lane with Geometric improvement of Tura-Dalu Road from Km 85.000 to Km 95.000 & Km 101.000 to km 145.000 to 2-lanes with paved shoulder of Tura- Dalu section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 51/217 | 51.536 | - | 48.51 | 610.09 | 358.65 | 2017-04-20 | 2018-03-28 | 2018-09-15 | 88.07 | 87.04 | 2021-09-14 | - | 2025-06-15 | Manaranjan Brahma | nh51.turadalu.siteoffice@gmail.com | Voyants Solution Pvt. Ltd.in In Jv with YONGMA Engg Co. Ltd & in Association with Cho & Kim Engg Pvt. Ltd. (JV) | Normal Highway/Road Project
216 | DT-3 | NER | Meghalaya | PMU-Tura | MG-1 | DN/12002/01002/ML | Awarded, Not Appointed | Awarded, Not Appointed | Tura Bypass | Construction of 2-Lane with paved shoulder of Tura Bypass starting from existing km 57+500 of NH-127B (design chainage km 0+000) and ending at existing km 108+750 of NH-217 (Design chainage km 29+030) in Meghalaya on HAM Mode under NH(O)-NE | NH(O)-NE | NH | Connecting NH-127B & NH-217 | 29.03 | - | 0 | 951.27 | 451.55 | 2025-06-24 | 2026-03-25 | To be given | 0 | 0 | - | - | - | ABCI Infrastructures Pvt. Ltd. | silchar@abciinfra.com | - | Standalone Bypass Project
216 | DT-3 | NER | Meghalaya | PMU-Khliehriat | MG-2 | DN/22001/01004/ML | Sanctioned not awarded | Sanctioned not awarded | Shillong - Silchar (High Speed Corridor) Package-1 | Development, Maintenance, Management and Operation of Greenfield High-Speed Corridor from Mawlyngkhung (Near Shillong) in Meghalaya to Panchgram (Near Silchar) in Assam by 4-Laning with Paved Shoulders on Hybrid Annuity Basis (HAM) for Package-1: From Km 0+000 to Km 45+645 (Design Length – 45+645 Km) | NH(O)-NE | NH | 6 | 45.645 | - | 0 | 6256.74 | - | 2025-05-23 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
216 | DT-3 | NER | Meghalaya | PMU-Khliehriat | MG-3 | DN/22001/01003/ML | Sanctioned not awarded | Sanctioned not awarded | Shillong - Silchar (High Speed Corridor) Package-2 | Development, Maintenance, Management and Operation of Greenfield High-Speed Corridor from Mawlyngkhung (Near Shillong) in Meghalaya to Panchgram (Near Silchar) in Assam by 4-Laning with Paved Shoulders on Hybrid Annuity Basis (HAM) for Package-2: From Km 45+645 to KM 78+600 (Design Length – 32.955 Km) | NH(O)-NE | NH | 6 | 32.955 | - | 0 | 4517.27 | - | 2025-05-23 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
216 | DT-3 | NER | Meghalaya | PMU-Khliehriat | MG-4 | DN/22001/01002/ML | Sanctioned not awarded | Sanctioned not awarded | Shillong - Silchar (High Speed Corridor) Package-3 | Development, Maintenance, Management and Operation of Greenfield High-Speed Corridor from Mawlyngkhung (Near Shillong) in Meghalaya to Panchgram (Near Silchar) in Assam by 4-Laning with Paved Shoulders on Hybrid Annuity Basis (HAM) for Package-3: From Km 78+600 to Km 133+320 (Design Length – 54.720 Km) | NH(O)-NE | NH | 6 | 54.72 | - | 0 | 7401.99 | - | 2025-05-23 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
216 | DT-3 | NER | Meghalaya | PMU-Khliehriat | MG-5 | DN/22001/01001/ML | Sanctioned not awarded | Sanctioned not awarded | Shillong - Silchar (High Speed Corridor) Package-4 | Development, Maintenance, Management and Operation of Greenfield High-Speed Corridor from Mawlyngkhung (Near Shillong) in Meghalaya to Panchgram (Near Silchar) in Assam by 4-Laning with Paved Shoulders on Hybrid Annuity Basis (HAM) for Package-4: From Km 133+320 to Km 164+355 (Design Length – 31.035 Km) | NH(O)-NE | NH | 6 | 31.035 | - | 0 | 4687.93 | - | 2025-05-23 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
217 | DT-3 | NER | Meghalaya | PMU-Tura | 155260 | DN/01005/01003/ML | Ongoing | Under Construction (AD issued) | Dainadubi-Darugiri Pkg-1B | Improvement/Widening of National Highway No. 217 (Dainadubi-Darugiri section) to Two lane with paved shoulder in Meghalaya from design Km 0+000 to Km 40+840 (Design Length=40.840Km) (existing Km 8+600 to Km 53+000 of Old NH-62) under BMP (Lot-1) Pkg-1B (Meghalaya portion) | NH(O)-NE | NH | 62/217 | 40.84 | - | 15.08 | 705.83 | 308.92 | 2023-03-22 | 2023-03-31 | 2025-03-20 | 45.1 | 42.77 | 2027-03-20 | 2027-03-19 | - | Allone Infra Pvt. Ltd. -GaneshKartikey Construction Pvt. Ltd. (JV) | singhconst2002@gmail.com | GEO Design and Research Pvt. Ltd. in Association with - JS Environics Consultants Pvt. Ltd. (JV) | Normal Highway/Road Project
218 | DT-3 | NER | Meghalaya | PMU-Tura | 155296 | DN/01005/01002/ML | Ongoing | Under Construction (AD issued) | Darugiri - Songsak - Williamnagar Junction Pkg-1B | Improvement and Widening of National Highway No. 127B (Darugiri - Songsak - Williamnagar Junction Section) to two lane with paved shoulder from design Km 0+000 to Km 36+635 (Design length= 36.635 Km) (existing Km 112+000 to Km 151+060 of NH-1278) under Bharatmala Pariyojana (Lot-1) Pkg-1B (Meghalaya portion) | NH(O)-NE | NH | 127B | 36.64 | - | 10 | 801.07 | 329.29 | 2023-03-31 | 2023-03-31 | 2025-09-27 | 25.99 | 18.83 | 2027-09-26 | 2027-09-26 | - | Shivalaya Construction co. Pvt. Ltd. (SCCPL) | tenders@sccgroup.co.in | GEO Design and Research Pvt. Ltd. in Association with - JS Environics Consultants Pvt. Ltd. (JV) | Normal Highway/Road Project
219 | DT-3 | NER | Meghalaya | PMU-Mylliem | 152814 | DN/14001/02001/ML | Ongoing | Under Construction (AD issued) | Nongstoin-Rambrai-Kyrshai Road upto Meghalaya/Assam border (NRK Pkg-1) | Rehabilitation and up gradation of Nongstoin-Rambrai-Kyrshai road up to Meghalaya-Assam border from Km 0.335 to km 34.039 to 2-Lane under NH(O) - NE in the State of Meghalaya (Package-1) | SARDP-NE | Non NH | - | 33.7 | - | 29.78 | 359.86 | 155.54 | 2021-09-21 | 2022-01-27 | 2022-05-27 | 83.02 | 81.46 | 2024-05-25 | 2026-12-31 | - | SPICA Projects & Infrastructures Pvt. Ltd. | nongstoin.spica@gmail.com | Shrikhande Consultants Pvt. Ltd. in association with Infra Design Studio Pvt. Ltd. | Normal Highway/Road Project
220 | DT-3 | NER | Meghalaya | PMU-Mylliem | 156186 | DN/06004/01009/ML | Completed | Physically Completed & CC Under Issue | Shillong-Dawki Pkg-1 | Improvement/Widening to 2-L with Paved Shoulder/4-L from Km 81+740 to Km 93+490 (design Km 0+000 to Km 10+670) of NH-40 (New NH-106 & 206) section & 4-L from (design Km 0.00 to Km 0.930) of NH-44 section between Shillong-Dawki under JICA ODA Loan assistance (Phase-II) -Balance Work-(Pkg-1) | EAP (JICA) | NH | 40 & 44/ 106 & 206 | 11.6 | - | 10.67 | 351.12 | 166.07 | 2020-07-13 | 2023-07-24 | 2023-10-23 | 100 | 97.21 | 2025-10-22 | 2026-06-15 | - | New India Contractors & Developers Pvt. Ltd. - BCC Buildtech Pvt. Ltd. (JV) | bcc.shillong03@gmail.com, office@nicdpl.com, bcc.shillong2024@gmail.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
221 | DT-3 | NER | Meghalaya | PMU-Mylliem | 156855 | DN/06004/01008/ML | Ongoing | Under Construction (AD issued) | Shillong-Dawki Pkg-2 | Improvement/Widening to 2-Lane with Paved Shoulder between Shillong-Dawki road up to Bangladesh Border from (design Km 10.670 to Km 37.550) under JICA ODA Loan assistance (Phase-II) -Balance Work-(Pkg-2) (with Toll Plaza at Ch. Km 22.850) | EAP (JICA) | NH | 40/206 | 26.55 | - | 18.78 | 525.67 | 200.69 | 2020-07-13 | 2023-10-16 | 2024-02-09 | 51.02 | 45.63 | 2026-08-07 | 2026-12-31 | - | YFC Projects Pvt. Ltd. - ACE Construction (JV) | info@linkcon.in | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
222 | DT-3 | NER | Meghalaya | PMU-Mylliem | 160614 | DN/08023/01002/ML | Awarded, Not Appointed | Awarded, Not Appointed | Shillong-Dawki Pkg-3 (Pynursla Bypass) | lmprovement/Construction to 2-lane with paved shoulders/4-laning of NH-40 (New NH-206) between Shillong to Dawki road upto Bangladesh Border including Dawki Bridge in the State of Meghalaya for execution on EPC Mode under NH (O)-NE from Existing Chainage Km 123.800 to Km 131.820 (design Km 0+000 to 7+760) (Package-III) Pynursla Bypass | NH(O)-NE | NH | 40/206 | 7.76 | - | 0 | 564.07 | 176.44 | 2025-02-17 | 2025-05-22 | To be given | 0 | 0 | - | - | - | Dhar Construction Company-Royal Infraconstruction Ltd. (JV) | dccshg2@gmail.com | M/s Agnitio Infrastructure Projects Pvt. Ltd. | Standalone Bypass Project
223 | DT-3 | NER | Meghalaya | PMU-Mylliem | 157191 | DN/06004/01007/ML | Ongoing | Under Construction (AD issued) | Shillong-Dawki Pkg-4 | Improvement/Widening to 2-Lane with Paved Shoulder from (design Km 45.760 to Km 63.530) between Shillong-Dawki under JICA ODA Loan assistance (Phase-II) -Balance work (Pkg-4) | EAP (JICA) | NH | 40/206 | 17.77 | - | 15.94 | 445.51 | 75.9 | 2020-07-13 | 2024-01-22 | 2024-04-19 | 53.21 | 46.78 | 2026-04-19 | 2026-10-31 | - | ACE Construction-Linkcon Engineering Pvt. Ltd.(LEPL) (JV) | info@linkcon.in | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
224 | DT-3 | NER | Meghalaya | PMU-Mylliem | 157496 | DN/06004/01006/ML | Ongoing | Under Construction (AD issued) | Shillong-Dawki Pkg-5 | Improvement/Widening to 2-L with Paved Shoulder/ 4-Laning of NH-40 section from Km 151+330 to Km 163+400 (design Km 63.530 to Km 71.520) including (Dawki Bridge of length 368 m) between Shillong-Dawki under JICA ODA Loan assistance (Phase-II) (Pkg-5) -Balance work | EAP (JICA) | NH | 40/206 | 7.99 | - | 5.52 | 284.21 | 238 | 2020-07-13 | 2024-03-08 | 2024-05-17 | 41.92 | 40.67 | 2026-11-13 | 2026-11-13 | - | ASC Infratech Pvt. Ltd. | sanjay@ascinfratech.com | URS Scott Wilson India Pvt. Ltd.- Krivam Consultant Pvt. Ltd. (JV) | Normal Highway/Road Project
225 | DT-3 | NER | Meghalaya | PMU-Mylliem | 155169 | DN/15001/01006/ML | Ongoing | Under Construction (AD issued) | Shillong Western Bypass Pkg-1 | Construction of 2-Lane with paved shoulder of Shillong Western Bypass starting from NH-06 near Ladumsaw (Existing km 60.900 of old NH-40) to NH106 (old NH-44E), km 0+000 to km 12+800 (Package-I) under SARDP-NE ‘PHASE A’ in the State of Meghalaya on EPC Mode (Greenfield alignment) | SARDP-NE | Non NH | 06 & 106 | 12.8 | - | 10.03 | 620.3 | 185.49 | 2023-03-07 | 2023-03-24 | 2024-09-02 | 73.13 | 69.36 | 2026-09-01 | 2026-09-02 | - | Anusha Projects Pvt. Ltd.- BKD Infrastructures Pvt. Ltd. (JV) | anushaprojects@gmail.com | Shrikhande Consultants Pvt. Ltd. (SCPL) | Standalone Bypass Project
226 | DT-3 | NER | Meghalaya | PMU-Mylliem | 155171 | DN/15001/01005/ML | Ongoing | Under Construction (AD issued) | Shillong Western Bypass Pkg-2 | Construction of 2 lane with paved shoulder of Shillong Western Bypass starting from NH-06 near Ladumsaw (existing km 60.900 of old NH-40) to NH-106 (old NH-44E), (Package-II) km 12+800 to km 24+700 under SARDP-NE ‘Phase A’ in the State of Meghalaya on EPC Mode | SARDP-NE | Non NH | 06 & 106 | 11.99 | - | 5.06 | 686.03 | 199.89 | 2023-03-16 | 2023-03-24 | 2024-09-02 | 49.82 | 49.18 | 2026-09-01 | 2026-09-02 | - | Narendra Sharma - T.K. Engineering Consortium Pvt. Ltd. (TKECPL) (JV) | nscdholpur@gmail.com | Shrikhande Consultants Pvt. Ltd. (SCPL) | Standalone Bypass Project
227 | DT-3 | NER | Meghalaya | PMU-Mylliem | 155172 | DN/15001/01004/ML | Ongoing | Under Construction (AD issued) | Shillong Western Bypass Pkg-3 | Construction of 2-Lane with paved shoulders of Shillong Western Bypass starting from NH-06 near Ladumsaw (existing Km 60.900 of old NH40) to NH106 (old NH 44E) (Package-III), from km 24+700 to km 38+256 under SARDP-NE PHASE A in the state of Meghalaya on EPC Mode (Greenfield alignment) | SARDP-NE | Non NH | 06 & 106 | 13.556 | 0.19 | 7.92 | 562.48 | 154 | 2023-03-13 | 2023-03-24 | 2024-09-02 | 52 | 49.68 | 2026-09-01 | 2026-09-02 | - | BRN Infrastructures Pvt. Ltd. | brninfrastructure@gmail.com | Shrikhande Consultants Pvt. Ltd. (SCPL) | Standalone Bypass Project
228 | DT-2 | NER | Mizoram | PMU-Seling | 149294 | DN/01020/02001/MZ | Completed | Completed | Seling-Dulte Pkg-1 | Rehabilitation & Up-gradation to 2-Lane with paved shoulders of Seling-Keifang section (Economic corridor) of NH-06 From existing chainage KM 0.000 to KM 15.000(Design chainage KM 0.000 to KM 13.510) (Package 1) In the state of Mizoram Under Bharatmala Pariyojna on EPC Mode | NH(O)-NE | NH | 6 | 13.51 | - | 13.51 | 219.33 | 134.91 | 2020-03-18 | 2020-03-31 | 2020-07-01 | 100 | 94.84 | 2022-06-30 | - | 2024-06-26 | GVV Construction Pvt. Ltd. | pradeepreddygvv@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
229 | DT-2 | NER | Mizoram | PMU-Seling | 149295 | DN/01020/02002/MZ | Completed | Completed | Seling-Dulte Pkg-2 | Rehabilitation and Up gradation to 2-lane with paved shoulder of Keifang Section (Economic Corridor) of NH-06 from Existing Chainage Km 15+000 (Keifang ) to Km 30+050 (Keifang) Design Chainage Km 13+510 to Km 27+400 (Pkg – II ) in the State of Mizoram under Bharatmala Pariyojna on EPC Mode (Seling-Dulte - II) | NH(O)-NE | NH | 6 | 13.89 | - | 13.89 | 216.49 | 138.75 | 2020-03-17 | 2020-03-31 | 2020-07-01 | 100 | 96.27 | 2022-06-30 | - | 2023-03-31 | NG Projects Ltd. | ngplmizoram@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
230 | DT-2 | NER | Mizoram | PMU-Seling | 149296 | DN/01020/02003/MZ | Completed | Completed | Seling-Dulte Pkg-3 | Rehabilitation and Up gradation to 2-lane with paved shoulder of Keifang Section (Economic Corridor) of NH-06 from Existing Chainage Km 30+050 (Keifang) to Km 50+360 (Keifang), Design Chainage Km 27+400 to Km 45+040 ( Pkg – III ) in the State of Mizoram under Bharatmala Pariyojna on EPC Mode (Seling-Dulte - III) | NH(O)-NE | NH | 6 | 17.64 | - | 16.96 | 331.17 | 197.38 | 2020-03-18 | 2020-03-31 | 2020-07-01 | 94.4 | 87.81 | 2022-06-30 | - | 2024-10-10 | NG Projects Ltd. | pradeepreddygvv@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
231 | DT-2 | NER | Mizoram | PMU-Seling | 149297 | DN/01020/02004/MZ | Completed | Completed | Seling-Dulte Pkg-4 | Rehabilitation and Up-gradation to 2-lane with paved shoulders of Rulchawm-Dulte section (Economic Corridor) of NH-6 from Existing chainage Km 50+360 (Rulchawm) to Km 69+015 (Dulte) (Design Chainage Km 45+040 to Km 62+200)(Pkg-IV) in the state of Mizoram under Bharatmala Pariyojna on EPC Mode (Seling-Dulte - IV) | NH(O)-NE | NH | 6 | 17.16 | - | 17.16 | 253.41 | 185.49 | 2020-03-17 | 2020-03-31 | 2020-07-01 | 100 | 96.2 | 2022-06-30 | - | 2024-01-30 | Anusha Projects Pvt. Ltd. | anushaprojects@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
232 | DT-2 | NER | Mizoram | PMU-Seling | 151700 | DN/03002/01005/MZ | Completed | Completed | Dulte-Champhai road Pkg-1 | Rehabilitation and Up-gradation to 2 lane with paved shoulders of Dulte-Kwalkulh road (International Corridor) of NH-6 from Design Chainage Km 54.400 to Km 72.350 (Package-1) in the state of Mizoram under Bharatmala Pariyojna on EPC Mode | NH(O)-NE | NH | 6 | 17.95 | - | 17.95 | 318.92 | 212.37 | 2021-03-31 | 2021-03-31 | 2021-06-25 | 100 | 98 | 2022-12-25 | - | 2024-03-31 | Dhariwal Buildtech Ltd. | skc.hisar@rediffmail.com dbl.hisar@rediffmail.com | CMEC Consulting Engineers Pvt. Ltd. -AICONS Engineering Pvt. Ltd. - KPS Engineers Pvt. Ltd. (JV) | Normal Highway/Road Project
233 | DT-2 | NER | Mizoram | PMU-Seling | 151701 | DN/03002/01006/MZ | Completed | Completed | Dulte-Champhai road Pkg-2 | Rehabilitation and Up-gradation to 2 lane with paved shoulders of Kwalkulh-Khawzawl road (lnternational Corridor) of NH-6 from Design Chainage Km 72.350 to Km 84.800 (Package-2) in the state of Mizoram under Bharatmala Pariyojna on EPC Mode | NH(O)-NE | NH | 6 | 12.45 | - | 12.45 | 233.25 | 121.031 | 2021-03-31 | 2021-03-31 | 2021-06-25 | 100 | 97 | 2022-12-25 | - | 2024-04-18 | Dwarakamai Constructions Pvt. Ltd. | dmcpvtltd.2277@gmail.com | CMEC Consulting Engineers Pvt. Ltd. -AICONS Engineering Pvt. Ltd. - KPS Engineers Pvt. Ltd. (JV) | Normal Highway/Road Project
234 | DT-2 | NER | Mizoram | PMU-Seling | 151702 | DN/03002/01007/MZ | Completed | Completed | Dulte-Champhai road Pkg-3 | Up-gradation to 2 lane with paved shoulders of Khawzawl-Champhai road (lnternational Corridor) of NH-6 from Design Chainage Km 84.800 to Km 111.580 (Package-3) in the state of Mizoram under Bharatmala Pariyojna on EPC Mode | NH(O)-NE | NH | 6 | 26.78 | - | 26.78 | 674.71 | 370.432 | 2021-03-31 | 2021-03-31 | 2021-06-25 | 100 | 99.21 | 2023-06-25 | - | 2024-01-03 | RKC Infrabuilt Pvt. Ltd.(RKCIPL)-Shri Balaji Construction Company(SBCC) (JV) | bd@rkc.co.in | CMEC Consulting Engineers Pvt. Ltd. -AICONS Engineering Pvt. Ltd. - KPS Engineers Pvt. Ltd. (JV) | Normal Highway/Road Project
235 | DT-2 | NER | Mizoram | PMU-Kolasib | 152818 | DN/01012/01009/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte- Sairang Pkg-3 | 4-Laning of Vairengte - Chhimluang section (Package-3) of NH-306 from Existing Chainage km 43+000 to Km 59+700 (Design Chainage km 46+000 to km 60+850) on Silchar - Vairengte- Sairang road in the State of Mizoram under Bharatmala Pariyojna under NH(O)-NE (Package-1&2 in Assam state) | NH(O)-NE | NH | 306 & 6 | 14.85 | - | 0 | 491.39 | 244.68 | 2021-12-03 | 2022-01-27 | 2025-07-08 | 17.86 | 10.03 | 2027-01-07 | 2026-12-30 | - | Dhatarwal Construction Company Pvt. Ltd. | dtw.cons@gmail.com | Dhruv Consultancy services Ltd. in (JV) - Global infra solutions in association with - MS consultants | Normal Highway/Road Project
236 | DT-2 | NER | Mizoram | PMU-Kolasib | 152819 | DN/01012/01010/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte- Sairang Pkg-4 | 4-Laning of chhimluang-Kolasib from section (pkg-4) of NH-306 & NH-6 existing chainage km 59+700 to km 86+000 (design chainage km 61+000 to km 77+500) on Silchar-vairengte-sairang road in the state of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE Vairengte - Sairang Pkg-4 | NH(O)-NE | NH | 306 & 6 | 16.5 | - | 0 | 561.91 | 276.72 | 2021-12-20 | 2022-01-28 | 2025-07-08 | 17.12 | 14.52 | 2027-01-07 | 2026-12-30 | - | Shiwalay Infra Projects Pvt. Ltd. | office@shiwalay.in | Dhruv Consultancy services Ltd. in (JV) - Global infra solutions in association with - MS consultants | Normal Highway/Road Project
237 | DT-2 | NER | Mizoram | PMU-Kolasib | 153039 | DN/01012/01011/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte- Sairang Pkg-5 | 4-Laning of Kolasib - Sethawn section (Package-5) of NH-6 from Existing Chainage km 86+000 to km 107+850 (Design Chainage km 77+500 to km 95+500) on silchar - vairengte - sairang road under Bharatmala Pariyojna on EPC mode under NH(O)-NE (Vairengte - Sairang Pkg-5) | NH(O)-NE | NH | 306 & 6 | 18 | - | 0 | 720.4 | 323.65 | 2021-11-17 | 2022-03-25 | 2025-07-08 | 11.86 | 10.12 | 2027-07-07 | 2027-06-28 | - | Rajendra Singh Kiledar Construction Company (RSK) - MLN Project (JV) | rsk-mln-jv@mlnprojects.in | Dhruv Consultancy services Ltd. in (JV) - Global infra solutions in association with - MS consultants | Normal Highway/Road Project
238 | DT-2 | NER | Mizoram | PMU-Kolasib | 155277 | DN/01012/01012/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte- Sairang Pkg-6 | 4-Laning of Sethawn - N. Kawnpui section (Package-6) of NH-6 from Existing Chainage km 107+850 to km 126+315 (Design Chainage km 95+500 to km 111+850) on Silchar-Vairengte-Sairang road in the State of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE Vairengte - Sairang Pkg-6 | NH(O)-NE | NH | 306 & 6 | 16.35 | - | 0 | 595.65 | 261 | 2021-12-20 | 2023-03-29 | 2025-07-08 | 6.72 | 6.53 | 2027-01-07 | 2026-12-30 | - | Pappu Prasad | pprasad.mizoram@gmail.com | Dhruv Consultancy services Ltd. in (JV) - Global infra solutions in association with - MS consultants | Normal Highway/Road Project
239 | DT-2 | NER | Mizoram | PMU-Kolasib | 159781 | DN/01012/01013/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte - Sairang Pkg-7 | Construction of 4-Laning of N. Kawnpui (N. Mualvum) –Mualkhang via Khamrang Village section (Package-7) of NH-6 from Existing Chainage km 127+200 to km 142+000 (Design Chainage km 111+850 to km 123+400) on Silchar - Vairengte - Sairang road in the State of Mizoram on EPC mode under NH(O)-NE | NH(O)-NE | NH | 6 | 11.55 | - | 1.8 | 866.32 | 359 | 2024-02-12 | 2024-12-16 | 2025-10-28 | 18.9 | 17 | 2028-10-28 | 2028-10-28 | - | Shri Balaji Construction Company (SBCC) | sbc_dungarpur@yahoo.com | Lion Engineering Consultants Private Limited in association with M/s Abhishira Infrastructure Consultants Private Limited | Normal Highway/Road Project
240 | DT-2 | NER | Mizoram | PMU-Kolasib | 159783 | DN/01012/01014/MZ | Ongoing | Under Construction (AD issued) | Silchar - Vairengte - Sairang Pkg-8 | Construction of 4-Laning of West Serawlg-Sairang section of NH-6 from Existing Chainage km 142+000 to km 158+900 (Design Chainage km 123+400 to km 136+260) on Silchar - Vairengte - Sairang road in the State of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE (Package-8) | NH(O)-NE | NH | 6 | 12.86 | - | 0 | 875.79 | 338.12 | 2024-02-12 | 2024-12-05 | 2025-11-01 | 13.95 | 13.55 | 2028-11-01 | 2028-11-01 | - | Dhatarwal Construction Company Pvt. Ltd. | dtw.cons@gmail.com | - | Normal Highway/Road Project
241 | DT-2 | NER | Mizoram | PMU-Kolasib | 155065 | DN/01012/02001/MZ | Awarded, Not Appointed | Awarded, Not Appointed | Aizawl Bypass Pkg-1 | Construction of 2-lane Aizawl Bypass from km 0.000 to km 10.600 (Package-1) on Sairang - Phaibawk section of NH-6 in the State of Mizoram under Bharatmala Pariyojna on EPC Mode under NH(O)-NE | NH(O)-NE | NH | 6 | 10.6 | - | 0 | 329.7 | 127.99 | 2023-02-28 | 2023-03-14 | To be given | 0 | 0 | - | - | - | BRN Infrastructures Pvt. Ltd. | brninfrastructurre@gmail.com | Marc Technocrates Pvt. Ltd | Standalone Bypass Project
242 | DT-2 | NER | Mizoram | PMU-Kolasib | 157530 | DN/01012/02002/MZ | Ongoing | Under Construction (AD issued) | Aizawl Bypas (Tunnel) Pkg-2 | Construction of Twin Tube Uni-directional Aizawl Bypass Tunnel of 2.5 km and its approaches of 2.1 km from km 10.600 to km 15.200 on Sarrang - Phaibawk section of NH-6 in the State of Mizoram on EPC Mode under NH(O)-NE (Package-2) | NH(O)-NE | NH | 6 | 4.6 | - | 0 | 1313.28 | 630.66 | 2024-01-15 | 2024-03-15 | 2025-12-02 | 0 | 0 | 2028-12-02 | 2028-12-02 | - | IRCON International Ltd. | gmbd@ircon.org | Dhruv Consultancy Services Limited in association with M S Consultant | Standalone Tunnel-Bypass Project
243 | DT-2 | NER | Mizoram | PMU-Kolasib | 155031 | DN/01012/02003/MZ | Ongoing | Under Construction (AD issued) | Aizawl Bypas Pkg-3 | Construction of 2-lane Aizawl Bypass from km 15.200 to km 34.500 (Package-3) on Sairang - Phaibawk section of NH-6 in the State of Mizoram under Bharatmala Pariyojna on EPC Mode under NH(O)-NE | NH(O)-NE | NH | 6 | 19.3 | - | 0 | 720.72 | 371 | 2023-02-28 | 2023-03-06 | 2025-11-10 | 15.1 | 14.31 | 2028-11-10 | 2028-11-10 | - | Dhariwal Buildtech Ltd. | skc.hisar@rediffmail.com, dbl.hisar@rediffmail.com | Marc Technocrates Pvt. Ltd | Standalone Bypass Project
244 | DT-2 | NER | Mizoram | PMU-Lunglei | 151698 | DN/03001/02001/MZ | Ongoing | Under Construction (AD issued) | Lunglei to Tlabung Pkg-A | Construction of 2-laning with hard shoulder configuration of Lunglei to Chhumkhum from Design Chainage Km 0.000 to Km 37.420 of NH-302 in Mizoram under Bharatmala Pariyojana on EPC mode [Pkg-A] | NH(O)-NE | NH | 302 | 37.42 | - | 33.73 | 698.45 | 404.59 | 2021-03-30 | 2021-03-30 | 2021-06-30 | 64.78 | 60.61 | 2022-12-30 | 2026-06-30 | - | SRK Constructions and Projects Pvt. Ltd. | srkhyd501@gmail.com | CMEC Consulting Engineers Pvt. Ltd. -AICONS Engineering Pvt. Ltd. - Nexgen (JV) | Normal Highway/Road Project
245 | DT-2 | NER | Mizoram | PMU-Lunglei | 151699 | DN/03001/02002/MZ | Ongoing | Under Construction (AD issued) | Lunglei to Tlabung Pkg-B | Construction of 2-laning with hard shoulder configuration of Chhumkhum to Tlabung from Design Chainage Km 37.420 to Km 74.950 of NH-302 in Mizoram under Bharatmala Pariyojana on EPC mode [Pkg-B] | NH(O)-NE | NH | 302 | 37.53 | - | 32.52 | 740.58 | 435.39 | 2021-06-28 | 2021-03-31 | 2021-07-10 | 61.34 | 53.48 | 2023-01-09 | 2026-12-31 | - | SRK Constructions and Projects Pvt. Ltd. | srkhyd501@gmail.com | CMEC Consulting Engineers Pvt. Ltd. -AICONS Engineering Pvt. Ltd. - Nexgen (JV) | Normal Highway/Road Project
246 | DT-2 | NER | Mizoram | PMU-Seling | 149925 | DN/06007/01010/MZ | Completed | Completed | Aizawl-Tuipang Pkg-1 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 8.00 (Seling) to km 65.00 (Package-1) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 56.96 | - | 56.44 | 1286.35 | 699.3 | 2017-04-20 | 2019-11-25 | 2020-01-24 | 98.9 | 95.48 | 2023-07-25 | - | 2024-05-28 | Gawar Construction Ltd. - Shivalaya Construction co. Pvt. Ltd. (SCCPL) (JV) | gawar.scc@gmail.com | Nippon Koei - STUP Consultants (JV) | Normal Highway/Road Project
247 | DT-2 | NER | Mizoram | PMU-Seling | 60092 | DN/06007/01009/MZ | Completed | Completed | Aizawl-Tuipang Pkg-2 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 65.00 to km 125.00 (Serchhip) (Package-2) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) on EPC Mode | EAP (JICA) | NH | 54/02 | 50.94 | - | 50.34 | 988.23 | 512 | 2017-04-20 | 2019-03-08 | 2019-12-23 | 99.34 | 97.67 | 2023-06-23 | - | 2024-03-31 | Gammon India Ltd. | manigammon@gmail.com arun.dalvi@gammonengineers.com info@kram.co.in | Nippon Koei - STUP Consultants (JV) | Normal Highway/Road Project
248 | DT-2 | NER | Mizoram | PMU-Lunglei | 60091 | DN/06007/01003/MZ | Completed | Physically Completed & CC Under Issue | Aizawl-Tuipang Pkg-3 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 125.00 (Serchhip) to km 166.00 (Package-3) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 40.2 | - | 39.64 | 785.65 | 450.45 | 2017-04-20 | 2019-02-13 | 2019-10-25 | 97.51 | 96.16 | 2023-04-24 | Physically Completed C.C Under Issue | 2025-04-30 | Bhartia Infra Projects Limited(BIPL)-ABCI Infrastructures Pvt. Ltd. (JV) | info@bhartiainfra.com | Rodic-TPF (JV) | Normal Highway/Road Project
249 | DT-2 | NER | Mizoram | PMU-Lunglei | 63336 | DN/06007/01013/MZ | Completed | Completed | Aizawl-Tuipang Pkg-4 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 166.00 to km 208.00 (Package-4) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 42.53 | - | 42.486 | 789.05 | 447.49 | 2017-04-20 | 2019-02-13 | 2019-10-25 | 99.88 | 98.19 | 2023-04-24 | - | 2025-04-20 | ABCI Infrastructures Pvt. Ltd. | klbaid@abciinfra.com | Rodic-TPF (JV) | Normal Highway/Road Project
250 | DT-2 | NER | Mizoram | PMU-Lunglei | 63337 | DN/06007/01002/MZ | Completed | Physically Completed & CC Under Issue | Aizawl-Tuipang Pkg-5 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 208.00 to km 250.00 (Lunglei) (Package-5) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 33.8 | - | 33.26 | 688.25 | 395.37 | 2017-04-20 | 2019-02-13 | 2019-10-25 | 95.35 | 95.05 | 2023-04-24 | Physically Completed C.C Under Issue | 2025-04-30 | ABCI Infrastructures Pvt. Ltd. | silchar@abciinfra.com | Rodic-TPF (JV) | Normal Highway/Road Project
251 | DT-2 | NER | Mizoram | PMU-Lawngtlai | 63338 | DN/06007/01004/MZ | Completed | Completed | Aizawl-Tuipang Pkg-6 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 250.00 (Lunglei) to km 298.00 (Package-6) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 45.56 | - | 44.925 | 906.76 | 546.05 | 2017-04-20 | 2019-03-08 | 2019-12-16 | 98.73 | 97.08 | 2023-06-16 | - | 2025-05-15 | ABCI Infrastructures Pvt. Ltd.-Bhartia Infra Projects Limited(BIPL) (JV) | klbaid@abciinfra.com | Intercontinental Consultants and Technocrats Pvt. Ltd. in association with M/s Padecco Co. Ltd. Japan (IV) | Normal Highway/Road Project
252 | DT-2 | NER | Mizoram | PMU-Lawngtlai | 150754 | DN/06007/01006/MZ | Completed | Completed | Aizawl-Tuipang Pkg-7 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 298.00 to km 339.00 (Package-7) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 39.12 | - | 39.12 | 750.32 | 446.4 | 2017-04-20 | 2020-09-21 | 2020-10-01 | 100 | 98.43 | 2024-04-01 | - | 2025-05-06 | Power Mech Projects Ltd.- SRC Infra Developers Pvt. Ltd. (JV) | muralikrishna@powermech.net | Intercontinental Consultants and Technocrats Pvt. Ltd. in association with M/s Padecco Co. Ltd. Japan (IV) | Normal Highway/Road Project
253 | DT-2 | NER | Mizoram | PMU-Lawngtlai | 63340 | DN/06007/01007/MZ | Completed | Physically Completed & CC Under Issue | Aizawl-Tuipang Pkg-8 | Widening and up-gradation to 2-lane with paved shoulder configuration and geometric improvements from km 339.00 to km 380.00 (Siaha) (Package-8) on Aizawl-Tuipang section under JICA ODA Loan assistance (Phase-I) | EAP (JICA) | NH | 54/02 | 39.94 | - | 39.872 | 637.06 | 443.94 | 2017-04-20 | 2019-02-13 | 2020-03-16 | 99.82 | 94.65 | 2023-09-15 | Physically Completed C.C Under Issue | 2025-06-30 | Bhartia Infra Projects Limited(BIPL)-ABCI Infrastructures Pvt. Ltd. (JV) | info@bhartiainfra.com | Intercontinental Consultants and Technocrats Pvt. Ltd. in association with M/s Padecco Co. Ltd. Japan (IV) | Normal Highway/Road Project
254 | DT-2 | NER | Mizoram | PMU-Seling | 150901 | DN/06007/01008/MZ | Completed | Completed | Chhiathlang bypass & Serchhip Bypass Pkg-1 | Construction of 2nos. bypass as 2-L with hard shoulder of Chhiathlang bypass (of 2.571km) from 89.000 to 91.200 & Serchhip Bypass (of 11.829km) from 96.200 to 105.820 (Pkg-1) on Aizawl-Tuipang section of NH-54 under JICA ODA Loan assistance (Phase-II) on EPC Mode | EAP (JICA) | NH | 54/02 | 14.4 | - | 14.3 | 247.25 | 153.1 | 2020-03-19 | 2020-09-30 | 2020-10-15 | 99.73 | 98.41 | 2022-10-15 | - | 2024-03-30 | Kram Infracon Pvt. Ltd.(KIPL) - Vijay Kumar Mishra Constr. Pvt. Ltd. (VKMCPL) (JV) | info@kram.co.in, navin.mittal@kram.co.in | Nippon Koei - STUP Consultants (JV) | Standalone Bypass Project
255 | DT-2 | NER | Mizoram | PMU-Lunglei | 150867 | DN/06007/01001/MZ | Completed | Physically Completed & CC Under Issue | Hnathial Bypass Pkg-2 | Construction of 2-L with hard shoulder of Hnathial Bypass (Pkg-2) Start near Km.166.965 and End near 174.980 on Aizawl-Tuipang section of NH-54 under JICA ODA Loan assistance (Phase-II) | EAP (JICA) | NH | 54/02 | 6.996 | - | 7 | 113.58 | 60.3 | 2020-03-19 | 2020-07-31 | 2020-10-01 | 94.1 | 91.55 | 2022-04-03 | Physically Completed C.C Under Issue | 2026-01-15 | Mathiyan Construction Pvt. Ltd. | mathiyan_mzn@rediffmail.com | Rodic-TPF (JV) | Standalone Bypass Project
256 | DT-2 | NER | Mizoram | PMU-Lawngtlai | 151025 | DN/06007/01005/MZ | Completed | Completed | Lawngtlai Bypass Pkg-3 | Construction of 2-L with hard shoulder of Lawngtlai Bypass (Pkg-3) on Aizawl-Tuipang section of NH-54 under JICA ODA Loan assistance (Phase-II) | EAP (JICA) | NH | 54/02 | 2.3 | - | 2.27 | 58.84 | 31.14 | 2020-03-19 | 2020-10-29 | 2020-11-20 | 100 | 95.59 | 2022-05-23 | - | 2024-11-20 | David Zohmachhuana | davidzohmachhuana@gmail.com | Intercontinental Consultants and Technocrats Pvt. Ltd. in association with M/s Padecco Co. Ltd. Japan (IV) | Standalone Bypass Project
257 | DT-2 | NER | Mizoram | PMU-Seling | 152296 | DN/01020/01001/MZ | Completed | Completed | Keifang- Tuivai Pkg-1 | Up-gradation to 2-lane with paved shoulders of Khawkawn (from Bridge across River Tuivai) - Ngopa section of NH-102B of Aizawl - Imphal Economic Corridor from Existing Chainage km 0.000 to km 32.796 [Design Chainage km 0.000 to km 31.280] in the State of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE (Package-1) | NH(O)-NE | NH | 102B | 31.28 | - | 27.67 | 492.94 | 492.94 | 2021-09-21 | 2021-09-02 | 2021-11-26 | 90.5 | 83.23 | 2023-05-20 | - | 2024-05-31 | B R Goyal Infrastructure Ltd. | technical@brginfra.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
258 | DT-2 | NER | Mizoram | PMU-Seling | 154987 | DN/01020/01002/MZ | Completed | Completed | Keifang- Tuivai Pkg-2 | Up-gradation to 2-lane with paved shoulders of Ngopa - Pawlrang section of NH 102B of Aizawl - Imphal Economic Corridor from Existing Chainage km 32.796 to km 72.030 [Design Chainage km 31.280 to km 68.170] in the State of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE (Package-2) Keifang- Tuivai Pkg-2 | NH(O)-NE | NH | 102B | 36.89 | - | 36.79 | 523.78 | 523.78 | 2021-09-21 | 2023-02-27 | 2023-09-01 | 95.31 | 84.68 | 2025-02-22 | - | 2025-06-23 | Mehta Construction Co.- Heera Ram Godara (JV) | mehtaconst09@gmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
259 | DT-2 | NER | Mizoram | PMU-Seling | 153022 | DN/01020/01003/MZ | Ongoing | Under Construction (AD issued) | Keifang- Tuivai Pkg-3 | Up-gradation to 2 lane with paved shoutders of Pawlrang - Rulchawm section- of NH-102B of Aizawl - Imphal Economic Corridor from Existing Chainage km 72.030 to km 104.129 including 2.459 km re-alignment section from Tuivai River to Rulchawm connecting km 48.150 of NH-6 [Design Chainage km 68.170 to km 98.579] in the State of Mizoram under Bharatmala Pariyojna on EPC mode under NH(O)-NE (Package-3) (Keifang- Tuivai Pkg-3) | NH(O)-NE | NH | 102B | 30.41 | - | 30.35 | 500.88 | 500.88 | 2021-12-13 | 2022-03-25 | 2023-11-15 | 75.35 | 72.69 | 2025-05-08 | 2026-07-20 | - | Dhariwal Buildtech Ltd. | skc.hisar@rediffmail.com, dbl.hisar@rediffmail.com | L N Malviya lnfra Projects Pvt. Ltd. in Association with Varija Associates (JV) | Normal Highway/Road Project
260 | DT-2 | NER | Mizoram | PMU-Lawngtlai | 154999 | DN/21001/01002/MZ | Ongoing | Under Construction (AD issued) | Zorinpui - Longmasu section (IMBR) | 2-laning of Zorinpui - Longmasu section of NH-502A from km 0.000 to km 28.244 in the State of Mizoram on EPC mode under NH(O)-NE, stretch of IMBR | NH(O)-NE | NH | 502A | 28.244 | - | 0 | 781.85 | 339 | 2023-02-16 | 2023-02-23 | 2024-12-06 | 4.71 | 3.2 | 2026-12-06 | 2027-07-03 | - | RDS Project Ltd | bimal.bhadula@rdsproject.com delhi@rdsproject.com | Infrastructure Development Consultants (IDC) in JV with - Agnitio Infrastructure Projects Pvt. Ltd (JV) | Normal Highway/Road Project
261 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 122656 | DN/16001/02003/NL | Completed | Completed | Pfutsero- Phek (PP)- PKG-1 | Construction of 2-Lane with hard shoulders of Pfutsero- Phek (PP) Road on EPC mode from existing Km. 0.000 to Km. 19.900 (Design Km. 0.000 to Km. 20.000) (Design Length - 20.00 Km) in the State of Nagaland under SARDP-NE Phase-A on EPC mode (Package-I) | SARDP-NE | Non NH | - | 20 | - | 20 | 237.72 | 136.73 | 2018-03-22 | 2018-03-22 | 2018-11-08 | 100 | 100 | 2021-11-08 | - | 2021-11-28 | Kantilal Khimjibhi Bhalala Project Pvt. Ltd. (KKB) | kkbprojects@gmail.com , kkbnagaland@gmail.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
262 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 122657 | DN/16001/02002/NL | Completed | Completed | Pfutsero- Phek (PP)- PKG-2 | Construction of 2-Lane with hard shoulders of Pfutsero- Phek (PP) Road on EPC basis from existing Km 19.900 to Km 40.090 ( Design Km 20.000 to Km 40.000) Design Length 20.000 Km in the state of Nagaland under SARDP-NE Phase-A on EPC mode (Package-II) | SARDP-NE | Non NH | - | 20 | - | 20 | 251.97 | 160.1 | 2018-03-22 | 2018-03-22 | 2018-11-15 | 100 | 100 | 2021-11-14 | - | 2021-10-13 | Madhucon Projects Limited | nseethaiah@madhucon.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
263 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 122658 | DN/16001/02001/NL | Completed | Completed | Pfutsero- Phek (PP)- PKG-3 | Construction of 2-Lane with hard shoulders of Pfutsero- Phek (PP) Road from existing Km 40.090 to Km 65.300 ( Design Km 40.000 to Km 62.558) Design Length 22.558 Km in the state of Nagaland under SARDP-NE Phase-A on EPC mode (Package-III) | SARDP-NE | Non NH | Non NH & 702A | 22.56 | - | 22.56 | 282.98 | 192.6 | 2018-03-22 | 2018-03-22 | 2018-11-15 | 100 | 100 | 2021-11-14 | - | 2022-03-27 | Madhucon Projects Limited | nseethaiah@madhucon.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
264 | DT-2 | NER | Nagaland | PMU-Jakhama | 122646 | DN/16001/01007/NL | Completed | Completed | Chakabama-Zunheboto Pkg-1 | Construction of 2-Lane with Hard shoulders of Chakabama-Zunheboto (C-Z) Road from Existing Km 0.000 to Km 25.760 [Design Km 00.000 to design Km 25.000] (Design Length 25.00Km) in the state of Nagaland under SARDP-NE on EPC Mode (Package-I) | SARDP-NE | Non NH | SH | 25 | - | 24.976 | 339.57 | 233.35 | 2018-03-22 | 2018-03-23 | 2019-07-03 | 99.79 | 99.79 | 2022-07-02 | - | 2022-07-15 | Shivalaya Construction co. Pvt. Ltd. (SCCPL) | sccpl.nagaland@gmail.com | Planning & Infrastructure Development Consultants Pvt. Ltd.(PIDCPL) In Association with - OMS Infra Consultants Pvt. Ltd. | Normal Highway/Road Project
265 | DT-2 | NER | Nagaland | PMU-Jakhama | 122647 | DN/16001/01010/NL | Completed | Completed | Chakabama-Zunheboto Pkg-2 | Construction of 2-Lane with Hard shoulders of Chakabama-Zunheboto (C-Z) Road from existing Km 25.760 to Km 52.370 [Design Km 25.000 to Km 50.000 in the state of Nagaland under SARDP-NE on EPC Mode (Package-II) | SARDP-NE | NH | 702A | 25 | - | 25 | 279.35 | 174.7 | 2018-03-22 | 2018-03-23 | 2019-05-20 | 100 | 100 | 2022-05-19 | - | 2022-11-15 | Shivalaya Construction co. Pvt. Ltd. (SCCPL) | sccpl.nagaland@gmail.com | Planning & Infrastructure Development Consultants Pvt. Ltd.(PIDCPL) In Association with - OMS Infra Consultants Pvt. Ltd. | Normal Highway/Road Project
266 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 122648 | DN/16001/01006/NL | Completed | Completed | Chakabama-Zunheboto Pkg-3 | Construction of 2-Lane with Hard shoulders of Chakabama-Zunheboto (C-Z) Road from Existing Km 52.370 to Km 79.040 (Design Km 50.000 to Km 75.000) in the state of Nagaland under SARDP-NE Phase-A on EPC mode (Package-III) | SARDP-NE | NH | 702A | 25 | - | 25 | 285.68 | 194.1 | 2018-03-22 | 2018-03-23 | 2019-09-05 | 99.9 | 99.9 | 2022-09-03 | - | 2024-07-15 | Madhucon Projects Limited | nseethaiah@madhucon.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
267 | DT-2 | NER | Nagaland | PMU-Jakhama | 122649 | DN/16001/01009/NL | Completed | Completed | Chakabama-Zunheboto Pkg-4 | Construction of 2-Lane with hard shoulders of Chakabama-Zunheboto (C-Z) Road from existing Km.79.040 to Km.100.345 (Design Km.75.000 to Km.95.000) in the state of Nagaland under SARDP-NE Phase-A on EPC Mode (Package - IV) | SARDP-NE | NH | 702A | 20 | - | 20.005 | 315.03 | 213 | 2018-03-22 | 2018-03-28 | 2018-12-13 | 99.79 | 99.79 | 2021-12-12 | - | 2023-03-18 | Madhucon Projects Limited | nseethaiah@madhucon.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
268 | DT-2 | NER | Nagaland | PMU-Jakhama | 122650 | DN/16001/01008/NL | Completed | Completed | Chakabama-Zunheboto Pkg-5 | Construction of 2-Lane with Hard shoulders of Chakabama-Zunheboto (C-Z) Road from existing Km.100.345 to Km.122.250 (Design Km.95.000 to Km.115.534) in the state of Nagaland under SARDP-NE Phase-A on EPC Mode (Package - V) | SARDP-NE | NH | 702A | 20.534 | - | 20.53 | 255.58 | 188.1 | 2018-03-28 | 2018-03-28 | 2018-12-20 | 97.76 | 91.64 | 2021-12-19 | - | 2023-04-30 | Madhucon Projects Limited | nseethaiah@madhucon.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
269 | DT-2 | NER | Nagaland | PMU-Mon | 122651 | DN/16002/01006/NL | Completed | Completed | Merangkong-Tamlu-Mon Pkg-1 | Construction of 2-Lane with Hard Shoulders of Merangkong-Tamlu-Mon Road on EPC basis from Existing km 0+00 to km 20+456 (Design km 0+00 to km 20+00) in the State of Nagaland under SARDP-NE Phase-A (Pkg-1) | SARDP-NE | Non NH | - | 20 | - | 19.861 | 215.12 | 143.65 | 2018-03-22 | 2018-03-23 | 2018-11-18 | 89.02 | 88.9 | 2021-11-17 | - | 2022-04-28 | Keystone Infra Pvt. Ltd. | qsnagaland@keystoneinfra.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
270 | DT-2 | NER | Nagaland | PMU-Mon | 155573 | DN/16002/01007/NL | Completed | Physically Completed & CC Under Issue | Merangkong-Tamlu-Mon Pkg-2 | Construction of 2-Lane with hard shoulders of Merangkong-Tamlu-Mon (MTM) Road from existing Km 20.456 to Km 41.065 (Design Km. 20 to Km. 40.0) (Design Length-20.000 Km) in the State of Nagaland under SARDP-NE Phase-A (Pkg-2) (Balance work) | SARDP-NE | Non NH | - | 20 | - | 19.88 | 215.79 | 42.66 | 2018-03-22 | 2023-06-09 | 2023-08-22 | 100 | 99.92 | 2025-08-21 | Physically Completed & CC Under Issue | 2026-02-15 | A. Pongshi Phom- W. Chingkam Phom (JV) | app.jv.wcp@gmail.com, yalim91@gmail.com, | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
271 | DT-2 | NER | Nagaland | PMU-Mon | 122654 | DN/16002/01008/NL | Completed | Completed | Merangkong-Tamlu-Mon Pkg-3 | Construction of 2-Lane with hard shoulders of Merangkong-Tamlu-Mon (MTM) Road from existing Km 41.065 to Km 60.345 (Design Km. 40.000 to Km. 59.000) (Design Length-19.000 Km) in the State of Nagaland under SARDP-NE Phase-A (Pkg-3) | SARDP-NE | Non NH | - | 19 | - | 19.005 | 272.89 | 187 | 2018-03-22 | 2018-03-28 | 2019-10-24 | 99 | 88.19 | 2022-10-22 | - | 2023-12-31 | SSR Crest Engineers and Constructions Limited | ssrcrest@gmail.com | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
272 | DT-2 | NER | Nagaland | PMU-Mon | 155574 | DN/16002/01009/NL | Ongoing | Under Construction (AD issued) | Merangkong-Tamlu-Mon Pkg-4 | Construction of 2-Lane with hard shoulders of Merangkong- Tamlu-Mon Road on EPC Basis from existing road Km. 76.640 to Km 98.065 (Design chainage Km. 63.800 to Km. 86.835) Design Length-23.035 Km in the state of Nagaland under SARDP-NE (PKG-IV) (Balance work) | SARDP-NE | Non NH | - | 23.035 | - | 22.608 | 323.98 | 84.02 | 2018-03-22 | 2023-06-09 | 2023-09-11 | 75.05 | 74.83 | 2025-09-10 | 2026-12-31 | - | S. S. Infrazone Pvt. Ltd.-Shyama Construction (JV) | mtm4pm.ssiplscjv@gmail.com, mtm4ssiplscjv@gmail.com, shyamaconstruction0005@gmail.com, ssinfrapvtltd@outlook.com, | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
273 | DT-2 | NER | Nagaland | PMU-Mon | 156142 | DN/16002/01005/NL | Ongoing | Under Construction (AD issued) | Merangkong-Tamlu-Mon Pkg-5 | Construction of 2-lane with hard shoulders of Merangkong-Tamlu-Mon road (Wakching Twon portion) on EPC basis from existing Chainage Km 59+000 to Km 73+640 [Design Km. 59+000 to Km, 72+450] (Design length - 13.450 Km) under SARDP-NE (package-V) (Balance work) | SARDP-NE | Non NH | - | 13.45 | - | 13.38 | 161.73 | 52.63 | 2021-03-31 | 2023-07-19 | 2023-09-08 | 99.5 | 99.43 | 2025-09-07 | 2026-07-31 | - | Jayzee Constructions | jayzeeconstructiondmp@gmail.com, jayzeeconstruction.dmp@gmail.com, | Almonds Global Infra consultant - Mangalam Associate (JV) | Normal Highway/Road Project
274 | DT-2 | NER | Nagaland | PMU-Mon | 149363 | DN/09025/02002/NL | Completed | Completed | Changtongya - Longleng Pkg-1 | Construction of 2-lane with hard shoulder of Changtongya - Longleng Road on EPC basis from existing Km0.00 to Km16.592 [Design Km 0.00 to Km.18.779 ] in the State of Nagaland under NH(O) (Pkg-1) | NH(O) | NH | 702 | 17.68 | - | 17.683 | 278.95 | 177.11 | 2020-01-07 | 2020-03-02 | 2020-07-01 | 99.04 | 99.04 | 2022-06-30 | - | 2023-07-22 | RK Infracorp Pvt. Ltd.(RKIPL)-Nithin Sai Construction (NSC) (JV) | nitinsaicons@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
275 | DT-2 | NER | Nagaland | PMU-Mon | 156857 | DN/09025/02001/NL | Completed | Completed | Changtongya - Longleng Pkg-2 | Balance work of Construction of 2-lane with hard shoulder of Changtongya - Longleng Road on EPC basis from existing Km16.592 to Km29.530 [Design Km.18.779 to Km 33.428] (Design Length-14.649 km) in the State of Nagaland under NH(O) (Pkg-2) | NH(O) | NH | 702 | 13 | - | 13.004 | 184.74 | 20.97 | 2020-02-27 | 2023-11-02 | 2024-01-25 | 99.4 | 98.52 | 2025-01-24 | - | 2024-12-27 | Shankar Agarwal | shankaragarwaloffice@gmail.com | Techcracrats Advisory Services Pvt. Ltd. (TASPL) - Jagadambika Infrasolution Pvt. Ltd (JV) | Normal Highway/Road Project
276 | DT-2 | NER | Nagaland | PMU-Dimapur | 63745 | DN/01017/02004/AS | Completed | Completed | Dimapur Bypass (Assam Portion) | Construction of 4/6 Laning from existing Km 159.400 of NH-36 to existing Km 102.500 of NH-39 and upto end point of Assam portion [Design Km 118.050 to design Km 132.375] (Total New Alignment length of 14.325 Km ) of Daboka -Dimapur Section (Dimapur Bypass) (Assam Portion) in the state of Assam under SARDP-NE 'Phase-A' on EPC mode [1 No. Toll Plaza at ( Km 118+770 to Km 119+000)] | SARDP-NE | Non NH | Connecting NH-39/29 & NH-36 | 14.33 | - | 14.3 | 698.81 | 349.31 | 2018-03-09 | 2018-03-19 | 2019-11-26 | 100 | 99.2 | 2022-11-25 | - | 2025-11-10 | Gawar Construction Ltd. - Singh Construction Co. (JV) | singhconst2002@gmail.com | Yongma Engineering Corporation Ltd.- Sterling Indo Tech Corporation Pvt. Ltd. (JV) | Standalone Bypass Project
277 | DT-2 | NER | Nagaland | PMU-Dimapur | 60097 | DN/01017/02003/NL | Completed | Completed | Dimapur Bypass (Nagaland Portion) | Construction of 4/6 Laning from Km 132.375 to Km 153.058 (Total New Alignment length of 20.683 Km ) of Daboka-Dimapur Section (Dimapur Bypass) (Nagaland Portion) of NH-36 & 39 in the State of Nagaland on EPC basis under Phase –A of SARDP-NE | SARDP-NE | Non NH | Connecting NH-39/29 & NH-36 | 20.65 | - | 20.612 | 688.12 | 387 | 2017-02-16 | 2017-03-28 | 2017-09-05 | 100 | 99.81 | 2020-09-04 | - | 2025-09-20 | Simplex Infrastructures Ltd. | simplexkolkata@simplexinfra.net | Yongma Engineering Corporation Ltd.- Sterling Indo Tech Corporation Pvt. Ltd.(JV) | Standalone Bypass Project
277 | DT-2 | NER | Nagaland | PMU-Dimapur | 60094 | DN/01017/02005/NL | Terminated- To be Reawarded | Terminated- To be Reawarded | Dimapur Kohima Pkg-1 | 4 Laning of Dimapur Kohima Road from Design Km 123.840 to Km 138.775 (Existing Km 124.100 to Km 140.000) excluding Dimapur Kohima Bypass in the state of Nagaland under SARDP-NE on EPC basis (Package - I) 1 No. Toll at Design Km.130.500 | SARDP-NE | NH | 39/29 | 14.935 | - | 14.935 | 534.41 | - | 2016-03-31 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | Technocrats Advisory Services Pvt. Ltd. (TASPL)- Agnitio Infrastructure Projects Pvt. Ltd. (JV) | Normal Highway/Road Project
278 | DT-2 | NER | Nagaland | PMU-Dimapur | 60095 | DN/01017/02001/NL | Completed | Completed | Dimapur Kohima Pkg-2 | 4 Laning of Dimapur Kohima Road from Design Km 138.775 to Km 152.490 (Existing Km 140.000 to Km 156.000) in state of Nagaland under SARDP-NE on EPC basis (Package - II) | SARDP-NE | NH | 39/29 | 13.715 | - | 13.685 | 486.19 | 337.07 | 2016-03-31 | 2016-03-31 | 2016-08-03 | 99.81 | 98.53 | 2019-08-02 | - | 2023-06-10 | Ramky Infratructure Ltd. - ECI Engineering & Constr. Co. Ltd. (JV) | ramkyecinh39nagaland@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL)- Agnitio Infrastructure Projects Pvt. Ltd. (JV) | Normal Highway/Road Project
279 | DT-2 | NER | Nagaland | PMU-Dimapur | 156307 | DN/01017/02002/NL | Ongoing | Under Construction (AD issued) | Dimapur Kohima Pkg-3 | 4 Laning of Balance work of Dimapur — Kohima Road from design km 152.490 to km 166.700 (Existing km 156.000 to km 172.900) of NH-39 (new NH-29) Excluding Dimapur & Kohima Bypass on EPC mode under SARDP-NE (Package - III) | SARDP-NE | NH | 39/29 | 14.21 | - | 13.2285 | 794.74 | 111 | 2016-03-31 | 2023-08-04 | 2023-09-29 | 84.32 | 79.74 | 2025-09-28 | 2026-07-30 | - | Brand Eagles | brandeagles.nagaland@gmail.com | Technocrats Advisory Services Pvt. Ltd. (TASPL)- Agnitio Infrastructure Projects Pvt. Ltd. (JV) | Normal Highway/Road Project
279 | DT-2 | NER | Nagaland | PMU-Jakhama | 150841 | DN/01006/01002/NL | Terminated- To be Reawarded | Terminated- To be Reawarded | Kohima to Mao | Upgradation of existing road to 2-lane with paved shoulder from Kohima to Mao from km 185.540 to km 211.709 under Bharatmala- NH(O)-TSP | NH(O)-TSP | NH | 39/ 02 | 26.249 | - | 17.56 | 315.63 | - | 2020-10-01 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | CEMOSA-Pioneer Infra Consultants Pvt. Ltd. - Nexgen Infra Solutions (JV) | Normal Highway/Road Project
280 | DT-2 | NER | Nagaland | PMU-Jakhama | 156423 | DN/01003/01008/NL | Ongoing | Under Construction (AD issued) | Kohima-Bypass Pkg-1 | Construction of 2-Lane with paved shoulder of Kohima-Bypass Road connecting NH-39(New NH-02), NH-150(New NH-02), NH-61(New NH-29) and NH-39(New NH-02) from design Km 0.00 to Km 10.500 in the State of Nagaland under SARDP-NE on EPC Mode (Pkg.- 1)-Balance work | SARDP-NE | Non NH | Connecting NHs-39/02, 150/02, 61/29, 39/02 | 10.5 | - | 3.58 | 350.88 | 216 | 2022-12-16 | 2023-09-05 | 2023-11-09 | 25.61 | 24.14 | 2026-11-08 | 2026-11-08 | - | Brand Eagles | brandeaglestawang@gmail.com | CEMOSA - Pioneer Infra Consultants Pvt. Ltd. (PCPL) - Design Line Consultancy Services (JV) | Standalone Bypass Project
281 | DT-2 | NER | Nagaland | PMU-Jakhama | 150878 | DN/01003/01007/NL | Ongoing | Under Construction (AD issued) | Kohima-Bypass (including 0.5Km Tunnel) Pkg-2 | Construction of 2-Lane with paved shoulder of Kohima-Bypass Road connecting New NH-02 and New NH-29 from Design Km 10.500 to design Km 21.000 [Design Length- 10.500 km] including (TUNNEL of 500m at Ch. 11.000Km) in the state of Nagaland Under SARDP-NE on EPC Mode (Pkg.- 2) | SARDP-NE | Non NH | Connecting NHs-29 & 02 | 10.5 | - | 8.42 | 277.44 | 177 | 2020-07-07 | 2020-09-25 | 2020-10-15 | 69.82 | 68.64 | 2022-10-15 | 2026-06-30 | - | Bharat Constructions (India) Pvt. Ltd. | bciplkohima@gmail.com | CEMOSA - Pioneer Infra Consultants Pvt. Ltd. (PCPL) - Design Line Consultancy Services (JV) | Standalone Tunnel-Bypass Project
282 | DT-2 | NER | Nagaland | PMU-Jakhama | 154901 | DN/01003/01006/NL | Ongoing | Under Construction (AD issued) | Kohima-Bypass Pkg-3 | Construction of 2-lane with Paved shoulder of Kohima-Bypass Road connecting NH- 39 (New NH-02), NH150(New NH-02), NH7-61 (New NH-29) and NH-39 (New NH-02) from Design km 21.000 to km 32.268 [Design length=11.268 km] in the state of Nagaland Under SARDP-NE on EPC Mode (Pkg.- 3) | SARDP-NE | Non NH | Connecting NHs-39/02, 150/02, 61/29, 39/02 | 11.26 | - | 4.93 | 342.29 | 186.56 | 2022-12-16 | 2023-01-18 | 2023-06-16 | 37.38 | 35.16 | 2025-06-15 | 2026-12-31 | - | Niraj Cement Structurals Ltd. | projectkohima.niraj@gmail.com | CEMOSA - Pioneer Infra Consultants Pvt. Ltd. (PCPL) - Design Line Consultancy Services (JV) | Standalone Bypass Project
283 | DT-2 | NER | Nagaland | PMU-Jakhama | 150880 | DN/01003/01005/NL | Ongoing | Under Construction (AD issued) | Kohima-Bypass Pkg-4 | Construction of 2-lane with Paved shoulder of Kohima- Bypass Road Connecting NH-39(New NH-02), NH-150(New NH-02), NH-61(New NH-29), NH-39(New NH-02) from Design Km 32.00 to Design Km 43.454(Design Length-11.454 Km) in the State of Nagaland under SARDP-NE on EPC Mode(Package-IV) | SARDP-NE | Non NH | Connecting NHs-39/02, 150/02, 61/29, 39/02 | 11.45 | - | 3.95 | 202.36 | 118.56 | 2020-07-31 | 2020-08-14 | 2020-10-15 | 45.55 | 45.27 | 2022-04-17 | 2026-12-31 | - | Pele Khezhie | pelekhezhie.p4@gmail.com | CEMOSA-Pioneer Infra Consultants Pvt. Ltd. - Nexgen Infra Solutions (JV) | Standalone Bypass Project
284 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 149309 | DN/01007/01008/NL | Completed | Completed | Kohima - Jessami Pkg-1 | Construction of 2- lane with hard shoulder of Kohima-Jessami Road on NH-29 (Old NH-150) from existing Km 7.880 (near chedama Junction) to existing km 30.474 (Near Chakahabama) (Design km 7.88 to km 29.60) (Design length - 21.72 km) in the state of Nagaland Under Bharatmala Pariyojna on EPC Mode under NH(O) (Package -I) | NH(O) | NH | 150 / 29 | 21.72 | - | 21.435 | 320.97 | 193.79 | 2020-03-11 | 2020-03-17 | 2020-07-01 | 94.95 | 94.02 | 2022-06-30 | - | 2023-09-04 | RK Infracorp Pvt. Ltd.(RKIPL)-Nithin Sai Construction (NSC) (JV) | kj.rkipl.nsc@gmail.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
285 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 156782 | DN/01007/01010/NL | Ongoing | Under Construction (AD issued) | Kohima - Jessami Pkg-2 | Construction of 2-lane with hard shoulder of Kohima - Jessami road on NH-29 (Old NH-150) from existing Km 30.474 (Near Kidwema road Chakahabama) to existing Km 53.220 (Near Kikruma Village) (Design Km 29.60 to Km 51.50) (Design length-21.90 Km) in the state of Nagaland Under Bharatmala Pariyojna on EPC Mode under NH(O) (Package-II) -Balance work | NH(O) | NH | 150 / 29 | 21.9 | 0.7 | 11.46 | 355.79 | 69 | 2020-03-11 | 2023-10-10 | 2024-01-05 | 43.47 | 42.46 | 2026-01-04 | 2026-12-31 | - | Ratna Infrastructure Projects Pvt. Ltd. | ho@ratnainfra.in | GEO Designs and Research Private Limited | Normal Highway/Road Project
286 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 149347 | DN/01007/01007/NL | Completed | Completed | Kohima - Jessami Pkg-3 | Construction of 2-lane with hard shoulder of Kohima - Jessami road on NH-29 (Old NH-150) from existing Km53.220 (Near Kikruma Village) to existing Km 76.320 (Near Mesulumi Village) (Design Km51.50 to Km74.20) (Design length-22.70 Km) in the state of Nagaland Under Bharatmala Pariyojna on EPC Mode under NH(O) (Package-III) | NH(O) | NH | 150 / 29 | 22.7 | - | 22.7 | 365.42 | 206.26 | 2020-03-15 | 2020-03-23 | 2020-07-01 | 97.42 | 97.07 | 2022-06-30 | - | 2024-06-10 | Sudhakara Infratech Pvt. Ltd. (SIPL) - R. Maheswara Naidu (RMN) infrastructures Ltd. (JV) | sudhakarainfratech.kohima@gmail.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
287 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 149927 | DN/01007/01006/NL | Completed | Completed | Kohima - Jessami Pkg-4 | Construction of 2-lane with hard shoulder of Kohima - Jessami road on NH 29 (old NH 150) from existing km 76.320 (near Mesulumi Vill.) to existing Km98.380 (near Chizami Vill.) [ Design Km 74.200 to design Km 95.700][Design Length= 21.50 km] in the state of Nagaland Under Bharatmala Pariyojna on EPC Mode (Package IV) | NH(O) | NH | 150 / 29 | 21.5 | - | 21.26 | 330.78 | 205.26 | 2020-03-30 | 2020-03-30 | 2020-07-01 | 99.51 | 99.51 | 2021-12-31 | - | 2023-03-19 | Keystone Infra Pvt. Ltd. | kohima-jessami@keystoneinfra.com | Planning & Infrastructural Development Consultants Pvt. Ltd. (PIDCPL) | Normal Highway/Road Project
288 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 156685 | DN/01007/01009/NL | Ongoing | Under Construction (AD issued) | Kohima - Jessami Pkg-5 | Balance work of Construction of 2-lane with hard shoulder of Kohima - Jessami road on NH-29 (old NH-150) from existing km 98.380 (near Chizami vill.) to km120.367 (Nagaland/Manipur Border) [Design km 95.700 to design km 117.200] [Design Length= 21.500 km] in the state of Nagaland Under Bharatmala Pariyojna on EPC Mode (Package-V) under NH(O) | NH(O) | NH | 150 / 29 | 21.5 | - | 19.25 | 330.8 | 110.73 | 2020-03-30 | 2023-09-22 | 2023-11-23 | 93.04 | 90.88 | 2025-11-21 | 2026-06-30 | - | Kaushal Sharma - Prachi Infra & Roads Pvt. Ltd. (JV) | ks.jessami@gmail.com | Planning & Infrastructural Development Consultants Pvt. Ltd. (PIDCPL) | Normal Highway/Road Project
289 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 153084 | DN/03003/02001/NL | Completed | Completed | Akegwo-Akash bridge - Jessami section Pkg-1 [Nagaland Portion] | Construction of 2 lane with Hard shoulder from Design Chainage Km 283.000 to Km 325.440 (5- legged junction at Old Akegwo) to (Akash Bridge) of Akegwo- Jessami section of NH-202 in the State of Nagaland on EPC mode under NH(O)-NE (Package-I) [Nagaland Portion] | NH(O)-NE | NH | 202 | 42.44 | - | 42.44 | 605.36 | 275 | 2022-03-25 | 2022-03-30 | 2022-06-23 | 100 | 99.35 | 2024-12-20 | - | 2025-01-17 | Kantilal Khimjibhi Bhalala Project Pvt. Ltd. (KKB) - Y. N. Dhanani (YND) (JV) | kkbnagaland@gmail.com | Artefact Project Ltd. - MS Consultants | Normal Highway/Road Project
290 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 155138 | DN/03003/01001/NL | Ongoing | Under Construction (AD issued) | Akegwo-Avangkhu Pkg-1 | Widening to 2 Lane with Hard shoulder of Akegwo-Avangkhu section of NH-202K for Package-I (Design Chainage 0+000 Km to 34+795 Km) in the State of Nagaland on EPC mode under NH(O)-NE | NH(O)-NE | NH | 202K | 34.97 | - | 33.75 | 430.24 | 187.89 | 2022-12-16 | 2023-03-23 | 2023-08-24 | 87 | 80.62 | 2026-02-23 | 2026-09-30 | - | Mayasheel Construction- JSP Projects Pvt. Ltd. (JV) | mayasheelconstruction@gmail.com | Armenge Engg. & Management Consultants Pvt. Ltd. - AICONS Engineering Pvt. Ltd. (JV) | Normal Highway/Road Project
291 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 154866 | DN/03003/01003/NL | Ongoing | Under Construction (AD issued) | Akegwo-Avangkhu Pkg-2 | Widening to 2 Lane with Hard shoulder of Akegwo-Avangkhu section of NH-202K for Package-II (Design Chainage 34+795 Km to 69+875 Km) in the State of Nagaland on EPC mode under NH(O)-NE | NH(O)-NE | NH | 202K | 35.08 | - | 20.5 | 442.54 | 220.79 | 2022-12-16 | 2023-02-08 | 2023-08-24 | 70.01 | 62 | 2026-02-23 | 2027-03-31 | - | Kantilal Khimjibhi Bhalala Project Pvt. Ltd. (KKB) | kkbnagaland@gmail.com | Armenge Engg. & Management Consultants Pvt. Ltd. - AICONS Engineering Pvt. Ltd. (JV) | Normal Highway/Road Project
292 | DT-2 | NER | Nagaland | PMU-Meluri (Pfutsero) | 154863 | DN/03003/01002/NL | Ongoing | Under Construction (AD issued) | Akegwo-Avangkhu Pkg-3 | Widening to 2 Lane with Hard shoulder of Akegwo-Avangkhu section of NH-202K for Package-III (Design Chainage 69+875 Km to 106+816 Km) in the State of Nagaland on EPC mode under NH(O)-NE | NH(O)-NE | NH | 202K | 36.941 | - | 32.11 | 497.18 | 272.59 | 2022-12-16 | 2023-02-08 | 2023-08-26 | 85.67 | 84 | 2026-02-25 | 2026-11-30 | - | New India Contractors & Developers Pvt. Ltd. - Bharat Construction Co. (JV) | office@bcc-buildtech.com | Armenge Engg. & Management Consultants Pvt. Ltd. - AICONS Engineering Pvt. Ltd. (JV) | Normal Highway/Road Project
293 | DT-2 | NER | Nagaland | PMU-Dimapur | 150988 | DN/09024/01002/NL | Completed | Completed | Peren- Dimapur Pkg-1 | Construction of 2-lane with hard shoulder of Peren-Dimapur section on NH-129A from design Km109.494 to Km126.775 (Length=17.281) in the state of Nagaland on EPC mode under NH(O)-TSP (Pkg-1) | NH(O)-TSP | NH | 129A | 14.7 | - | 14.4 | 257.15 | 121.49 | 2020-08-10 | 2020-09-10 | 2020-10-20 | 100 | 99.92 | 2022-04-22 | - | 2023-07-02 | Mayasheel Construction- JSP Projects Pvt. Ltd. (JV) | mayasheelconstruction.nagaland@gmail.com | CEMOSA-Pioneer Infra Consultants Pvt. Ltd.(PCPL) - Introsoft Solutions (JV) | Normal Highway/Road Project
294 | DT-2 | NER | Nagaland | PMU-Dimapur | 160120 | DN/09024/01003/NL | Ongoing | Under Construction (AD issued) | Peren - Dimapur Pkg-1A | Construction of 2-laning with Paved/Hard Shoulder of Peren-Dimapur road section on NH-129A from design km 120.320 to design km 123.200 (Design length: 2.88 km in Peren town) in the State Of Nagaland on EPC Mode under NH(O) (Package-1A) | NH(O) | NH | 129A | 2.88 | - | 0 | 106.32 | 28.99 | 2025-01-07 | 2025-03-28 | 2025-06-07 | 35.9 | 35.08 | 2026-12-07 | 2026-12-07 | - | Affluent Enterprises & Services | affluententerprise13@gmail.com | CEMOSA-Pioneer Infra Consultants Pvt. Ltd.(PCPL) - Introsoft Solutions (JV) | Normal Highway/Road Project
295 | DT-2 | NER | Nagaland | PMU-Dimapur | 155563 | DN/09024/01006/NL | Ongoing | Under Construction (AD issued) | Peren- Dimapur Pkg-2 | Balance work for 2-lane with hard shoulder of Peren- Dimapur section on NH-129A from Design Km 126.775 to Km 146.208 (Length 19.433 Km) in the state of Nagaland on EPC mode under NH(O)-TSP (Pkg-2) | NH(O)-TSP | NH | 129A | 19.433 | - | 19.43 | 258.52 | 56.79 | 2021-01-18 | 2023-05-31 | 2023-09-10 | 96.53 | 94.84 | 2025-09-09 | 2026-07-10 | - | AM Infrastructure Projects Pvt. Ltd.- RN Infra Projects Ltd. (JV) | amiprojects16@gmail.com | CEMOSA-Pioneer Infra Consultants Pvt. Ltd.(PCPL) - Introsoft Solutions (JV) | Normal Highway/Road Project
296 | DT-2 | NER | Nagaland | PMU-Dimapur | 155125 | DN/09024/01005/NL | Ongoing | Under Construction (AD issued) | Peren- Dimapur Pkg-3 | Construction of 2 laning with Hard shoulder of Peren-Dimapur section on NH-129A from Design Km 146.208 to Km 163.592 (Length- 17.384 km) in the state of Nagaland on EPC mode under NH(O) (Pkg - 3) | NH(O) | NH | 129A | 17.384 | - | 17.38 | 199.02 | 79 | 2021-02-11 | 2023-03-20 | 2023-06-07 | 95.62 | 94.49 | 2025-06-06 | 2026-06-06 | - | AM Infrastructure Projects Pvt. Ltd.- RN Infra Projects Ltd. (JV) | amiprojects16@gmail.com | Agnitio Infrastructure Project Pvt. Ltd. (AIPPL) in JV with - Infrastructure Development Consultants (IDC) (JV) | Normal Highway/Road Project
297 | DT-2 | NER | Nagaland | PMU-Dimapur | 157172 | DN/09024/01004/NL | Ongoing | Under Construction (AD issued) | Peren- Dimapur Pkg-4 | Construction of 2 Laning with Hard Shoulder of Peren - Dimapur section on NH-129A from Design Km 163.592 to Km 173.850 (Length - 10.258 km) in the state of Nagaland on EPC mode under NH(O)-TSP (Pkg - 4) | NH(O)-TSP | NH | 129A | 10.258 | - | 10.26 | 116.54 | 45.49 | 2021-03-30 | 2024-01-04 | 2024-02-24 | 93.45 | 91.88 | 2026-02-23 | 2026-08-30 | - | Vertex Construction | vertexinfra417@gmail.com | Agnitio Infrastructure Project Pvt. Ltd. (AIPPL) in JV with - Infrastructure Development Consultants (IDC) (JV) | Normal Highway/Road Project
298 | DT-2 | NER | Nagaland | PMU-Dimapur | 151438 | DN/09024/01014/NL | Awarded, Not Appointed | Awarded, Not Appointed | Peren- Dimapur Pkg-5 | Construction of 2 laning with Hard shoulder of Peren-Dimapur section on NH 129A from Design Km 173.850 to Km 190.850 (Length - 17.000 Km) in the state of Nagaland on EPC mode under NH(O)-TSP (Package-5) -Balance work | NH(O)-TSP | NH | 129A | 17 | - | 0 | 207.33 | 99.24 | 2021-02-11 | 2026-03-30 | To be given | 0 | 0 | - | - | - | Shivalik Buildtech Pvt. Ltd. | - | Agnitio Infrastructure Project Pvt. Ltd. (AIPPL) in JV with - Infrastructure Development Consultants (IDC) (JV) | Normal Highway/Road Project
299 | DT-1 | NER | Sikkim | PMU-Ranipool | 66756 | DN/09021/03001/SK | Completed | Completed | Chisopani Traffic Tunnel | Construction of 2-lane Chisopani Traffic Tunnel of length 250 m including approaches from Km 67+080 to Km 67+500 on NH-10 in East District of Sikkim on EPC basis. | NH(O) | NH | 31A/10 | 0.42 | - | 0 | 35.69 | 29 | 2019-02-11 | 2019-03-05 | 2019-09-09 | 99.75 | 95.75 | 2021-09-08 | - | 2022-05-22 | Nagyan Construction Pvt. Ltd. (NCPL) | - | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Standalone Tunnel Project
300 | DT-1 | NER | Sikkim | PMU-Ranipool | 148751 | DN/09021/03002/SK | Completed | Completed | Chuba Khola Bridge | Construction of 48m Bridge over Chuba Khola at Km 75+300 to Km 75+800 on NH-10 on EPC Mode in Sikkim | NH(O) | NH | 31A/10 | 0.48 | - | 0 | 8.93 | 7.46 | 2019-01-16 | 2019-05-21 | 2019-09-16 | 100 | 80.19 | 2021-09-15 | - | 2022-09-14 | Mohan Bajaj | mohanbajajconstt@gmail.com | ALTINOK Consulting Engineer - SATRA Infrastructure Management Services Pvt. Ltd. in Ass. with MaRs planning & Engg. Services Pvt.Ltd (JV) | Standalone Bridge Project
301 | DT-1 | NER | Sikkim | PMU-Ranipool | 147008 | DN/19015/01012/SK | Completed | Completed | Singtam - Tarku Pkg-1 | Construction of 2-lane with paved shoulder including geometric improvement from Km 0.000 to Km 16.000 of stretch Singtam- Tarku of NH 510 on EPC basis under SARDP-NE Phase ‘A’ in the state of Sikkim (Pkg- I) | SARDP-NE | NH | 510 | 16 | - | 14.19 | 375.8 | 163 | 2017-03-30 | 2019-02-26 | 2019-10-05 | 96.55 | 94.97 | 2022-04-05 | - | 2025-09-09 | Vinod Kumar Jain (VKJ)-N Siva Prakash Reddy (NSPR) Constr. (I) Pvt. Ltd. (JV) | vkjnsprjv@gmail.com | Technocrats Advisory Services Pvt Ltd (TASPL) | Normal Highway/Road Project
302 | DT-1 | NER | Sikkim | PMU-Gyalshing | 60105 | DN/19015/01011/SK | Completed | Completed | Tarku - Rabangla Pkg-2 | Construction and up-gradation of existing road to 2 - lane with paved shoulder including geometric improvement of NH-510 from km 16.000 to km 32.500 (Tarku - Rabongla) on EPC basic under SARDP-NE Phase ‘A’ in the state of Sikkim (Pkg- II) | SARDP-NE | NH | 510 | 16.5 | - | 16.501 | 290.05 | 171.53 | 2017-03-30 | 2017-03-31 | 2017-11-01 | 100 | 97.15 | 2020-10-31 | - | 2024-04-29 | S&P lnfrastructure Developers Pvt. Ltd. | snp.sikkim510@gmail.com info@spinfra.in | Technocrats Advisory Services Pvt Ltd (TASPL) | Normal Highway/Road Project
302 | DT-1 | NER | Sikkim | PMU-Rhenock | SK-1 | DN/19002/01021/SK | Sanctioned not awarded | Sanctioned not awarded | Reshi (Km 96.254) to Rhenock (Km 101.554) along NH-717A | Widening and Up-gradation of existing carriageway into 2-lane with paved shoutder configuration from Reshi to Rhenock from Ch.96.254 to Ch. 101.554 along NH-717A in the State of Sikkim on EPC mode | NH(O)-NE | NH | 717A | 5.3 | - | 0 | 161.2365 | - | 2025-03-31 | - | - | - | - | - | - | - | - | - | - | Normal Highway/Road Project
303 | DT-1 | NER | Sikkim | PMU-Rhenock | 60101 | DN/19002/01015/SK | Completed | Completed | Rhenock-Rorathang-Pakyong | Constuction/Upgradation of existing road to 2 lane with paved shoulder from Km. 0.000 to Km. 26.706 in Rhenok-Rorathang-Pakyong as Alternate Highway to Gangtok on NH-717A on EPC Mode under SARDP-NE Phase-A in Sikkim | SARDP-NE | NH | 717A | 26.7 | - | 26.7 | 530.67 | 318.42 | 2017-01-25 | 2017-03-31 | 2017-11-01 | 99.6 | 99.69 | 2020-10-31 | - | 2022-05-24 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | draplanning.sikkim@gmail.com | Technocrats Advisory Services Pvt Ltd (TASPL) | Normal Highway/Road Project
304 | DT-1 | NER | Sikkim | PMU-Ranipool | 151436 | DN/19002/01012/SK | Completed | Physically Completed & CC Under Issue | Major Bridge (viaduct) on Ranipool to Pakyong road | Realignment of NH717A from Design CH: 0.00 (Km 77.800 of NH-10) to Design CH:2.00 (Km 3.100 of NH-717A) with 2-lane paved shoulder including Major Bridge (viaduct) of 680 m on Ranipool to Pakyong road (Surrendered & CoS work) | SARDP-NE | NH | 717A | 2 | - | 2 | 0 | 50 | 2018-03-22 | 2021-02-04 | 2021-04-10 | 100 | 98.18 | 2023-04-10 | Physically Completed & CC Under Issue | 2026-05-21 | Suryodaya Infra Projects Pvt Ltd (SIPL) | sipl.ranipool@gmail.com | ALTINOK Consulting Engineer - SATRA Infrastructure Management Services Pvt. Ltd. in Ass. with MaRs planning & Engg. Services Pvt.Ltd (JV) | Standalone MJB(Major Bridge) Project
305 | DT-1 | NER | Sikkim | PMU-Ranipool | 154527 | DN/19002/01009/SK | Ongoing | Under Construction (AD issued) | Ranipool to Pakyong | Construction/Upgradation of Existing road to 2 lane with paved shoulder including Geometric Improvement from Ranipool to Pakyong from km 2.000 to km 16.167 (Balance Work) under SARDP-NE 'A'” | SARDP-NE | NH | 717A | 14.167 | - | 13.84 | 380.94 | 81.27 | 2018-03-22 | 2022-11-02 | 2023-01-05 | 86.04 | 84.8 | 2024-07-06 | 2026-12-31 | - | Bhavya Construction | bhavya.silchar@gmail.com bhavya.sikkim@gmail.com | ALTINOK Consulting Engineer - SATRA Infrastructure Management Services Pvt. Ltd. in Ass. with MaRs planning & Engg. Services Pvt.Ltd (JV) | Normal Highway/Road Project
305 | DT-1 | NER | Sikkim | PMU-Rhenock | 151402 | DN/19013/01006/SK | Terminated- To be Reawarded | Terminated- To be Reawarded | Rhenok - Menla spur Pkg-2A | Construction and upgradation of existing road to 2-lane with Paved shoulder from km. 20.340 (Rongli Bazzar) to km. 26.588 (Rongli Bypass End) and upgradation of existing road at km 20.600 & km 26.400 for length of 0.520 km & 0.554 km of Rhenok - Menla spur NH-717B (Pkg-II A) under SARDP-NE | SARDP-NE | NH | 717B | 7.322 | - | 2.14 | 348.92 | - | 2021-02-11 | Terminated (To be Re-awarded-1) | - | - | - | - | - | - | To be Re-awarded | - | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Normal Highway/Road Project
306 | DT-1 | NER | Sikkim | PMU-Rhenock | 151060 | DN/19013/01010/SK | Ongoing | Under Construction (AD issued) | Rhenok - Menla spur Pkg-2B | Construction & Upgradation of existing road to 2-lane with paved shoulder from km27.200 (End of Rongli bypass) to km37.600(New Rolep Bridge) of Rhenok-Menla spur (NH-717B) on EPC Mode under SARDP-NE Phase-A in Sikkim (Pkg-II B) | SARDP-NE | NH | 717B | 10.4 | - | 9.9 | 244.91 | 100.95 | 2020-07-09 | 2020-08-31 | 2020-10-15 | 86.19 | 85.45 | 2023-04-15 | 2026-09-30 | - | J.K. Associates - A.K. Builders (JV) | akjksiteoffice@gmail.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Normal Highway/Road Project
307 | DT-1 | NER | Sikkim | PMU-Rhenock | 151061 | DN/19013/01007/SK | Ongoing | Under Construction (AD issued) | Rongli to Chochenpheri Pkg-2C | Construction & Upgradation of existing road to 2-lane with paved shoulder from New Rolep Bridge at km 37.600 to Chochenpheri at km 52.00 in the section of Rongli to Chochenpheri of NH 717B (Pkg-II C) | SARDP-NE | NH | 717B | 14.4 | - | 13.7 | 478.79 | 236.12 | 2020-10-07 | 2021-03-16 | 2021-05-25 | 79.13 | 77.15 | 2024-05-23 | 2026-09-30 | - | Nalanda Engicon Pvt. Ltd.- Ujjain Engicon Pvt. Ltd. (JV) | Pkg2c@nalandaengicon.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Normal Highway/Road Project
308 | DT-1 | NER | Sikkim | PMU-Rhenock | 151063 | DN/19013/01009/SK | Ongoing | Under Construction (AD issued) | Rhenok - Menla spur Pkg-3A | Construction of 2-laning with Paved Shoulder of New Greenfield alignment from Chochenpheri at Km 52+000 to Helipad near Menla at Km 82+000 of Rhenock- Menla Spur under SARDP-NE Phase 'A' on NH-717B (Pkg-III A) | SARDP-NE | NH | 717B | 30 | 0.08 | 25.94 | 786.6 | 532.52 | 2020-10-07 | 2020-10-28 | 2020-12-10 | 64.31 | 61.97 | 2023-12-09 | 2027-05-19 | - | U.P. State Bridge Corporation Ltd. | bcusikkimupsbc@gmail.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Normal Highway/Road Project
309 | DT-1 | NER | Sikkim | PMU-Rhenock | 151347 | DN/19013/01008/SK | Ongoing | Under Construction (AD issued) | Rhenok - Menla spur Pkg-3B | Construction of 2-lane with paved shoulder of new green field alignment from Helipad at Menla at km 82.00 to Menla at Km 94.030 of Rhenok-Menla Spur under SARDP-NE Phase 'A' on NH-717B (Pkg-III B) | SARDP-NE | NH | 717B | 12.03 | 0.02 | 11.33 | 379.3 | 260.52 | 2021-01-18 | 2020-12-28 | 2021-02-25 | 82.64 | 79.45 | 2024-02-24 | 2027-05-31 | - | A. G. Construction | agconstruction.rhenok@gmail.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | Normal Highway/Road Project
310 | DT-1 | NER | Sikkim | PMU-Gyalshing | 150788 | DN/19015/01010/SK | Completed | Physically Completed & CC Under Issue | Singtam-Tarku-Rabangla-Legship-Gyalshing (including Tunnel) Pkg-3 | Construction of 2-lane specification road with paved shoulder including Tunnel (300m) at Rabangla on NH-510 (Singtam-Tarku-Rabangla-Legship-Gyalshing) Pkg-III (Design Ch.: 32.500 km to 33.600 km) under SARDP-NE (Pkg- III) | SARDP-NE | NH | 510 | 1.1 | - | 1.1 | 79.21 | 50.6 | 2020-09-09 | 2020-09-22 | 2020-10-15 | 100 | 98.43 | 2022-10-15 | Physically Completed C.C Under Issue | 2024-03-26 | Nagyan Construction Pvt. Ltd. (NCPL) | ncplsikkim@gmail.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Standalone Tunnel Project
311 | DT-1 | NER | Sikkim | PMU-Gyalshing | 150789 | DN/19015/01007/SK | Ongoing | Under Construction (AD issued) | Start of Rabangla km33.600 to km58.840 Pkg-4 | Rehabilitation & Upgradation of existing road to 2-lane with paved shoulder including geometric improvement of section from start of Rabangla km33.600 to km58.840 under SARDP-NE Phase “A” (Pkg- IV) | SARDP-NE | NH | 510 | 25.24 | - | 25.24 | 292.8 | 144.9 | 2020-07-09 | 2020-08-31 | 2020-10-31 | 65.12 | 63.39 | 2022-05-01 | 2026-12-30 | - | Shivam Condev Pvt. Ltd. | shivamsikkimpkgivnh510@gmail.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
311 | DT-1 | NER | Sikkim | PMU-Gyalshing | 150790 | DN/19015/01009/SK | Under Termination | Under Termination | Legship - Gyalshing Pkg-5 | Construction of 2-lane specification road with paved shoulder as realignment (Greenfield alignment) of existing stretch on NH-510 between Legship - Gyalshing from km58.840 to km75.00 under SARDP-NE Phase “A” on EPC mode (Pkg- V) | SARDP-NE | NH | 510 | 16.16 | - | 9.44 | 414.2 | 132.3 | 2020-07-31 | 2020-09-14 | 2020-11-10 | 49.2 | 46.07 | 2023-05-09 | Under Termination | - | JRA Infrastructure Ltd. (JRAIPL) | jra.ahmedabad@gmail.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
311 | DT-1 | NER | Sikkim | PMU-Gyalshing | 150791 | DN/19015/01008/SK | Under Termination | Under Termination | Legship - Gyalshing Pkg-6 | Construction of 2-lane road with paved shoulder (Greenfield alignment) of existing stretch between Legship - Gyalshing from km75.00 to km 90.210 under SARDP-NE Phase “A” on EPC Mode (Pkg- VI) | SARDP-NE | NH | 510 | 15.21 | - | 8.55 | 439.56 | 89.57 | 2020-09-01 | 2020-09-14 | 2020-11-10 | 51.85 | 48.33 | 2022-05-10 | Under Termination | - | JRA Infrastructure Ltd. (JRAIPL) | jra.ahmedabad@gmail.com | ALTINOK Consulting Engineering lnc - EDMAC Engineering Consultant (l) Pvt. Ltd. - DSD lnfratech Management Pvt. Ltd. | Normal Highway/Road Project
312 | DT-3 | NER | Tripura | PMU-Teliamura | 150663 | DN/01021/03001/TR | Completed | Completed | Strengthening of Churaibari - Agartala section | Strengthening of Churaibari - Agartala section of NH-08 (74.876 Km) in Tripura on EPC basis under NH(O) | NH(O) | NH | 44/08 | 74.876 | - | 74.856 | 257.96 | 202 | 2020-03-17 | 2020-06-03 | 2020-07-24 | 100 | 99.65 | 2022-01-15 | - | 2021-12-31 | Shiv Build India Pvt. Ltd. | sbilcharubariagartalanh8@gmail.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
313 | DT-3 | NER | Tripura | PMU-Udaipur | 60107 | DN/03005/01003/TR | Completed | Completed | Agartala- Udaipur Section | Improvement/ Widening to 2-laning with Paved shoulder of Agartala- Udaipur Section of NH-44 (New NH-08) from Km 6.800 to km 55.00 in the state of Tripura under SARDP-NE Phase ‘A’ on EPC basis | SARDP-NE | NH | 44/08 | 48.2 | - | 47.532 | 770.82 | 369 | 2014-10-31 | 2014-10-31 | 2015-09-15 | 100 | 97.23 | 2018-03-14 | - | 2021-11-30 | Krishna Mohan Construction (KMC) | kmc_qs@rediffmail.com | Rodic Consultants Pvt.Ltd | Normal Highway/Road Project
314 | DT-3 | NER | Tripura | PMU-Udaipur | 63065 | DN/03005/01001/TR | Completed | Completed | Feni Bridge at Sabroom on Indo-Bangladesh Border (Maitri Setu) | Construction of Extra-dosed RCC Bridge (412 m) including viaduct and approaches over river Feni at Sabroom on Indo-Bangladesh Border on NH-8 (old NH-44) "Maitri Setu" | NH(O) | NH | 44/08 | 1.888 | - | 1.468 | 128.69 | 82.57 | 2017-01-12 | 2017-03-22 | 2017-10-27 | 99.5 | 93.13 | 2020-04-26 | - | 2021-03-04 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | extradosed.dra@gmail.com | Rodic Consultants Pvt. Ltd | Standalone Bridge Project
315 | DT-3 | NER | Tripura | PMU-Udaipur | 60108 | DN/03005/01002/TR | Completed | Completed | Udaipur– Sabroom Section | Improvement/Widening to 2-Laning with paved shoulder of Udaipur– Sabroom Section from Km 55.000 to Km 128.712 of NH-44 (New NH-08) in the State of Tripura under SARDP-NE Phase “A’’ on EPC Basis | SARDP-NE | NH | 44/08 | 73.712 | - | 72.71 | 504.679 | 497.89 | 2014-05-02 | 2014-05-02 | 2015-10-31 | 100 | 97 | 2018-04-30 | - | 2018-05-25 | Oriental Structural Engineers Pvt. Ltd | - | Feedback Infra Pvt. Ltd. | Normal Highway/Road Project
316 | DT-3 | NER | Tripura | PMU-Udaipur | 151212 | DN/03005/01004/TR | Ongoing | Under Construction (AD issued) | Gomati and Muhuri Bridge | Construction of 2 RCC Bridges over river Gomati at Km 49.800 and Muhuri at Km 93.775 including approach road to the bridge on Agartala to Sabroom Road section of NH-08 on EPC basis | NH(O) | NH | 44/ 08 | 1.877 | - | 1.81 | 86.54 | 49.8 | 2020-07-09 | 2020-08-13 | 2020-09-23 | 79.1 | 77.78 | 2022-03-23 | 2026-07-31 | - | Brijesh Agarwal | erbrijesh123@yahoo.com | PMU act as AE | Standalone MJB(Major Bridge) Project
317 | DT-3 | NER | Tripura | PMU-Udaipur | TR-1 | DI/09001/01003/TR | Awarded, Not Appointed | Awarded, Not Appointed | Strengthening from Udaipur to Sabroom section of NH-08 | Strengthening of NH 08 section from Udaipur to Sabroom from Km 55.000 to km 127.372 of NH-08 and (ii) Raising and drainage provision in selected stretches of Agartala-Udaipur section of NH-08 in Tripura on EPC mode | NH(O) | NH | 44/08 | 72.472 | - | 0 | 198.51 | 102.907 | 2026-03-05 | 2026-03-30 | To be given | 0 | 0 | - | - | - | Mohan Lal Jain - Stone Concern Infrastructure Development Private Limited (JV) | - | - | Normal Highway/Road Project
318 | DT-3 | NER | Tripura | PMU-Udaipur | 155061 | DN/09019/01002/TR | Ongoing | Under Construction (AD issued) | Udaipur to Srimantapur section | Improvement and Widening to 2-lane with earthen/paved shoulder from Km 23 to Km 34.500 (11.5 Km) and overlay from Km 20.30 to Km 22.00 (1.7 Km) (Total Length = 13.2 Km) on Udaipur to Srimantapur section on NH-08 on EPC basis under NH(O)-NE | NH(O)-NE | NH | 44/08 | 13.2 | - | 13.1 | 195.95 | 111.11 | 2023-01-05 | 2023-03-03 | 2023-05-29 | 72.48 | 71.17 | 2024-11-27 | 2026-08-31 | - | Satish Prasad | spc.srimantapur@gmail.com | PMU act as AE | Normal Highway/Road Project
319 | DT-3 | NER | Tripura | PMU-Teliamura | 157537 | DN/01021/02001/TR | Ongoing | Under Construction (AD issued) | Champak Nagar to Khayerpur section (design Km 242+500 to Km 261+610) | Improvement & widening of existing NH-08 to 4-lane with Paved Shoulder from Champak Nagar to Khayerpur section (design Km 242+500 to Km 261+610) in the state of Tripura on EPC basis under NH(O)-NE | NH(O)-NE | NH | 44/08 | 19.11 | - | 12.66 | 920.66 | 359.13 | 2023-12-21 | 2024-03-15 | 2024-09-28 | 48.3 | 47.66 | 2026-09-28 | 2027-03-31 | - | New India Contractors & Developers Pvt. Ltd. | tripuranh8@nicdpl.com | GEO Designs and Research Private Limited | Normal Highway/Road Project
320 | DT-3 | NER | Tripura | PMU-Teliamura | 149305 | DN/01021/01001/TR | Completed | Completed | Khayerpur-Amtali (Agartala) section from Ch. 0.00 to 12.900 - [Agartala Bypass] | Improvement/strengthening to 2-lane with hard shoulder of Khayerpur-Amtali (Agartala) section from Ch. 0.00 Km to 12.900 Km of NH-8 in Tripura on EPC basis under NH(O) [Agartala Bypass] | NH(O) | NH | 44/08 | 12.9 | - | 12.68 | 147.06 | 97.07 | 2020-02-17 | 2020-03-20 | 2020-07-01 | 100 | 97.07 | 2022-07-01 | - | 2022-06-02 | Civtect India Pvt. Ltd. | civtectkhowai@gmail.com | Lion Engg. Consultants Pvt. Ltd. | Standalone Bypass Project
321 | DT-3 | NER | Tripura | PMU-Udaipur | 149368 | DN/11005/01001/TR | Completed | Physically Completed & CC Under Issue | Jolaibari - Belonia | Improvement and Widening to 2 lanes with paved shoulders of Jolaibari - Belonia (from km 0.000 to km 21.412) section of NH-108A in Tripura on EPC Mode under NH(O) | NH(O) | NH | 108A | 21.412 | - | 21.41 | 287.47 | 141.45 | 2020-02-26 | 2020-06-03 | 2020-07-15 | 100 | 98.82 | 2022-01-06 | Physically Completed C.C Under Issue | 2025-04-30 | Satish Prasad | spc.jolaibari@gmail.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
322 | DT-3 | NER | Tripura | PMU-Kumarghat | 149273 | DN/08008/01004/TR | Completed | Completed | Kailashahar-Kurti Bridge PKG-1 | Rehabilitation & Upgradation of Road from design Km 0.00 to Km 11.800 (Total length-11.800 km) of Kailashahar-Kurti Bridge section on NH-208A to 2-lane with Paved shoulder on EPC basis in Tripura under NH(O) (Package-I) | NH(O) | NH | 208A | 11.8 | - | 11.802 | 154.51 | 84.9 | 2020-02-26 | 2020-03-20 | 2020-07-15 | 100 | 98.9 | 2022-07-14 | - | 2023-08-15 | ASC Infratech Pvt. Ltd. | dkthakur@ascinfratech.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
323 | DT-3 | NER | Tripura | PMU-Dharmanagar | 149759 | DN/08008/01006/TR | Completed | Completed | Kailashahar-Kurti Bridge PKG-2 | Rehabilitation and up-gradation of road from design km 11.800 to km 25.250 (Total length: 13.450km) of Kailashahar-Kurti Bridge section on NH-208A to 2- lane with paved shoulder on EPC basis under NH(O) (Package-II) | NH(O) | NH | 208A | 13.45 | - | 13.45 | 208.7378 | 88.9 | 2020-03-03 | 2020-03-30 | 2020-07-15 | 100 | 97.59 | 2022-07-14 | - | 2023-10-15 | ASC Infratech Pvt. Ltd. | kbplanning@ascinfratech.com; | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
324 | DT-3 | NER | Tripura | PMU-Dharmanagar | 157575 | DN/08008/01005/TR | Ongoing | Under Construction (AD issued) | Kailashahar-Kurti Bridge PKG-3 | Rehabilitation and up-gradation of road from design km 25.250 to km 36.460 (Total lengh: 11.210 km) of Kailashahar-Kurti Bridge section on NH-208A to 2-lane with paved shoulder on EPC basis under NH(O) (Package-III)- Balance Work | NH(O) | NH | 208A | 11.21 | - | 8.46 | 174.434 | 59.85 | 2020-02-26 | 2024-03-15 | 2024-09-01 | 41.9 | 35.35 | 2026-03-02 | 2026-12-31 | - | Brahmaputra Infrastructures Pvt. Ltd. | guwahati@brahmaputragroup.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
325 | DT-3 | NER | Tripura | PMU-Kumarghat | 150648 | DN/08009/01002/TR | Completed | Completed | Kumarghat-Kailashahar section | Rehabilitation & Upgradation of Road from Km 0.00 to Km 18.600 (Total length-18.600 km) of Kumarghat-Kailashahar section on NH-208 to 2-lane with Paved shoulder on EPC bais under NH(O) | NH(O) | NH | 208 | 18.6 | - | 18.57 | 302.03 | 121.68 | 2020-02-20 | 2020-06-03 | 2020-07-15 | 99.94 | 99.26 | 2022-01-13 | - | 2024-12-03 | Satish Prasad | spc.kumarghat@gmail.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
326 | DT-3 | NER | Tripura | PMU-Kumarghat | 151213 | DN/05002/01010/TR | Ongoing | Under Construction (AD issued) | Kailashahar - Fultali (Kailashahar-Khowai) Pkg-1 | Improvement & widening to 2-lane with paved shoulder of road Kailashahar - Fultali section from Km 21.100 to Km 29.200 (Km 18.600 to Km 26.700) on NH-208 under JICA ODA Loan assistance (Phase-IV) (Pkg-1) | EAP (JICA) | NH | 208 | 8.1 | - | 8.1 | 105.27 | 62.24 | 2020-07-06 | 2020-11-24 | 2020-12-29 | 97.89 | 95.64 | 2022-06-30 | 2026-07-15 | - | Sahu Construction | spc.fultali@gmail.com | URS Scott-Mayrush Engineering (JV) | Normal Highway/Road Project
327 | DT-3 | NER | Tripura | PMU-Kumarghat | 151214 | DN/05002/01013/TR | Completed | Completed | Fultali - Jurichhara (Kailashahar-Khowai) Pkg-2 | Improvement & widening to 2-lane with paved shoulder of road Fultali - Jurichhara section from Km 29.200 to Km 49.200 under JICA ODA Loan assistance (Phase-IV) (Pkg-2) | EAP (JICA) | NH | 208 | 20 | - | 19.77 | 218.23 | 121 | 2020-07-06 | 2020-11-24 | 2020-12-31 | 100 | 99.64 | 2022-07-01 | - | 2023-02-02 | Narendra Builders - Jeet Construction Co. (JV) | nbjeetkumarghat@gmail.com | URS Scott-Mayrush Engineering (JV) | Normal Highway/Road Project
328 | DT-3 | NER | Tripura | PMU-Kumarghat | 151215 | DN/05002/01012/TR | Completed | Completed | Jurichhara - Bamanchara section (Kailashahar-Khowai) (Pkg-3) | Improvement & widening to 2-lane with paved shoulder of road Jurichhara - Bamanchara section from Km 49.200 to Km 63.700 under JICA ODA Loan assistance (Phase-IV) (Pkg-3) | EAP (JICA) | NH | 208 | 14.5 | - | 14.5 | 296.48 | 199.49 | 2020-07-06 | 2020-11-24 | 2021-01-01 | 100 | 96.89 | 2022-07-02 | - | 2023-05-26 | J Infratech Limited (JIL)- Maan Builders (JV) | jcipl.tripura@gmail.com | URS Scott-Mayrush Engineering (JV) | Normal Highway/Road Project
329 | DT-3 | NER | Tripura | PMU-Kumarghat | 151216 | DN/05002/01011/TR | Completed | Physically Completed & CC Under Issue | Bamanchara - Srirampur section (Kailashahar-Khowai) Pkg-4 | Improvement & widening to 2-lane with paved shoulder of road Bamanchara - Srirampur section from Km 63.700 to Km 75.700 under JICA ODA Loan assistance (Phase-IV) (Pkg-4) | EAP (JICA) | NH | 208 | 12 | - | 12 | 171.5 | 84.47 | 2020-07-06 | 2020-11-24 | 2020-12-29 | 100 | 99.35 | 2022-06-30 | Physically Completed C.C Under Issue | 2024-11-21 | Sahu Construction | spc.bamancherra@gmail.com | URS Scott-Mayrush Engineering (JV) | Normal Highway/Road Project
330 | DT-3 | NER | Tripura | PMU-Teliamura | 151217 | DN/05002/01014/TR | Completed | Completed | Srirampur - Khowai section (Kailashahar-Khowai) (Pkg-5) | Improvement & widening to 2-lane with paved shoulder of road Srirampur - Khowai section from Km 75.700 to Km 101.300 under JICA ODA Loan assistance (Phase-IV) (Pkg-5) | EAP (JICA) | NH | 208 | 25.6 | - | 25.6 | 317.96 | 149.92 | 2020-07-06 | 2020-11-24 | 2020-12-30 | 100 | 98.77 | 2022-07-01 | - | 2023-04-17 | Civtect India Pvt. Ltd. | civtectkhowai@gmail.com | URS Scott-Mayrush Engineering (JV) | Normal Highway/Road Project
331 | DT-3 | NER | Tripura | PMU-Teliamura | 157289 | DN/05002/01009/TR | Ongoing | Under Construction (AD issued) | Khowai –Teliamura-Amarpur-Harina-Sabroom section Pkg-1 | Improvement and Widening to 2-lane with paved shoulder of road from Km 101.300 to km 127.319 (Total Length 26.019 Km) i.e. the Khowai –Teliamura-Amarpur-Harina-Sabroom section of NH 208 in the state of Tripura on EPC under JICA ODA Loan Phase –VI (Package-1) | EAP (JICA) | NH | 208 | 26.019 | - | 13.95 | 431.78 | 189.14 | 2024-01-09 | 2024-02-12 | 2024-07-18 | 63.15 | 54.52 | 2026-07-17 | 2027-04-17 | - | Civtect India Pvt. Ltd. | civtect@gmail.com | Dhruv Consultancy Services Limited in association with M S Consultant | Normal Highway/Road Project
332 | DT-3 | NER | Tripura | PMU-Udaipur | 157290 | DN/05002/01008/TR | Ongoing | Under Construction (AD issued) | Khowai –Teliamura-Amarpur-Harina-Sabroom section Pkg-2 | Improvement and Widening to 2-lane with paved shoulder of road from existing Km 438.170 (Khowai Chowmuhani) to existing Km 439.410 (South Pulinpur) of NH-08 and from design Km 0.000 (South Pulinpur) to design Km 36.00 (near Rangamati) of NH 208 on Khowai – Teliamura- Harina section (Total length 37.24) in the state of Tripura on EPC mode under JICA ODA Loan Phase –VI (Package-2) | EAP (JICA) | NH | 208 | 37.24 | - | 12.95 | 657.21 | 260.14 | 2024-01-09 | 2024-02-12 | 2024-09-02 | 60.5 | 58.25 | 2026-09-02 | 2027-03-31 | - | Anupam Nirman Pvt. Ltd.- Bhavya Construction (JV) | bhavya.telimura@gmail.com | PMU act as AE | Normal Highway/Road Project
333 | DT-3 | NER | Tripura | PMU-Udaipur | 157291 | DN/05002/01007/TR | Ongoing | Under Construction (AD issued) | Khowai –Teliamura-Amarpur-Harina-Sabroom section Pkg-3 | Improvement and Widening to 2-lane with paved shoulder of road from design Km 36.000 (Rangamati) to design Km 72.000 (Pati Chhari) (Total length 36.000 Km) on Teliamura to Harina section of NH 208 in the state of Tripura on EPC mode under JICA ODA Loan Phase –VI (Package-3) | EAP (JICA) | NH | 208 | 36 | - | 0 | 670.9 | 245.1 | 2024-01-09 | 2024-02-12 | 2024-09-02 | 14.5 | 14.03 | 2026-09-02 | 2027-05-31 | - | Rani Constructions Pvt. Ltd. | hyd@ranigroup.com, nh208.p3@ranigroup.com | PMU act as AE | Normal Highway/Road Project
334 | DT-3 | NER | Tripura | PMU-Udaipur | 157292 | DN/05002/01006/TR | Ongoing | Under Construction (AD issued) | Khowai-Teliamura-Amarpur-Harina-Sabroom section Pkg-4 | Improvement and Widening to 2-lane with paved shoulder of road from design Km 72.000 (Pati Chhari) to design Km 107.654 (Harina) (Total length 35.654 Km) on Teliamura to Harina section of NH 208 in the state of Tripura on EPC mode under JICA ODA Loan Phase –VI (Package-4) | EAP (JICA) | NH | 208 | 35.654 | - | 0 | 726.9 | 301.62 | 2024-01-09 | 2024-02-12 | 2024-12-20 | 9.33 | 7.27 | 2026-12-20 | 2027-06-30 | - | Bhartia Infra Projects Limited(BIPL) | info@bhartiainfra.com, bipltrp.pkg4@gmail.com | PMU act as AE | Normal Highway/Road Project
335 | DT-3 | NER | Tripura | PMU-Teliamura | 149267 | DN/25002/01001/TR | Completed | Completed | Agartala - Khowai Pkg-1 | Rehabilitation and up-gradation of road from design km 6.500 to km 19.300 (Total lengh: 12.800 Km) of Agartala - Khowai section on NH-108B to 2- lane with paved shoulder on EPC basis under NH(O) (Package-I) | NH(O) | NH | 208A/ NH-108B | 12.8 | - | 12.805 | 210.54 | 86.47 | 2020-02-26 | 2020-03-30 | 2020-07-15 | 100 | 98.33 | 2022-07-15 | - | 2023-04-22 | Shiva Buildtech Pvt. Ltd. | shivabuildtech@gmail.com/shivabuildtech.tripura@gmail.com | Lion Engg. Consultants Pvt. Ltd. | Normal Highway/Road Project
336 | DT-3 | NER | Tripura | PMU-Teliamura | 157131 | DN/25002/01004/TR | Ongoing | Under Construction (AD issued) | Agartala - Khowai Pkg-2 | Rehabilitation and up-gradation of road from km 19.300 to km 31.300 (Total length: 12.000km) of Agartala-Khowai section on NH-108B to 2- lane with paved shoulder on EPC basis under NH(O) (Package-II)-Balance work | NH(O) | NH | 208A/ 108B | 12 | - | 2.25 | 141.48 | 70.11 | 2020-03-03 | 2023-12-18 | 2024-03-01 | 51.01 | 47.34 | 2025-08-31 | 2026-12-31 | - | Sahu Construction | sahu1222construction@gmail.com | Lion Engg. Consultants Pvt. Ltd. | Normal Highway/Road Project
337 | DT-3 | NER | Tripura | PMU-Teliamura | 150808 | DN/25002/01002/TR | Completed | Completed | Agartala - Khowai Pkg-3 | Rehabilitation and up-gradation of raod from design km 31.300 to km 45.300 (Total length: 14.000km) of Agartala-Khowai section on NH-108B to 2- lane with paved shoulder on EPC basis under NH(O) (Package-III) | NH(O) | NH | 208A/ NH-108B | 14 | - | 14 | 188 | 96 | 2020-03-03 | 2020-09-21 | 2020-10-22 | 100 | 97.26 | 2022-04-15 | - | 2024-05-30 | A K Construction Co. | akccagartalakhowai@gmail.com/akconstruction1@rediffmail.com | Lion Engg. Consultants Pvt. Ltd. | Normal Highway/Road Project
337 | DT-3 | NER | Tripura | PMU-Teliamura | 155176 | DN/12001/01002/TR | Under Termination | Under Termination | Agartala Western Bypass | Construction of 4-Lane with paved shoulder Agartala bypass (Western side, length – 25.402 km) connecting NH-8 (near Amtali) to NH-108B (near Lembuchhera) in the state of Tripura on EPC basis under NH(O)-NE | NH(O)-NE | NH | Connecting NH-08 & 108B | 25.402 | - | 0 | 2026.05 | 828.45 | 2023-03-22 | 2023-03-27 | 2024-03-09 | 9.2 | 5.27 | 2027-03-09 | Under Termination | - | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | dra.agartala@draipl.com | Almondz Global Infra consultant Ltd. | Standalone Bypass Project
338 | DT-3 | NER | Tripura | PMU-Kumarghat | 150640 | DN/01008/01008/TR | Completed | Completed | Manu-Simlung Pkg-1 | Rehabilitation and up-gradation of road from km 0.000 to km 16.29 of Manu-Lalchara Section on NH-44A to 2- lane with paved shoulder on EPC Mode (Pkg-1) (Manu-Simlung -I) | NH(O)-NE | NH | 108 / 44A | 16.077 | - | 16.08 | 251.89 | 166.94 | 2020-03-13 | 2020-03-30 | 2020-07-15 | 100 | 98.97 | 2022-01-14 | - | 2023-08-27 | Engineering Projects (INDIA) Ltd. (EPIL) | epilmanupkg1@gmail.com | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
339 | DT-3 | NER | Tripura | PMU-Dharmanagar | 153005 | DN/01008/01005/TR | Ongoing | Under Construction (AD issued) | Manu-Simlung Pkg-2 | Rehabilitation and up-gradation of road from km 16.077 to km 43.935 (total length 27.858 km) of Lalchara-Kanchanpur section via Shivbari on NH-44A to 2 lane with paved shoulder in the state of Tripura on EPC Mode (Pkg-2) under BharatMala Pariyojana (Manu-Simlung -2) | NH(O)-NE | NH | 108 / 44A | 27.858 | - | 16.23 | 456.88 | 257.51 | 2022-02-24 | 2022-03-23 | 2023-01-10 | 54.56 | 53.34 | 2025-01-09 | 2026-07-31 | - | Jugal Kishore Mahanta Infra works (JKM)-Keti Constructions Limited (KCL) (JV) | jkmho@jkminfra.net | Sterling Indo Tech Consultants Pvt.Ltd. | Normal Highway/Road Project
340 | DT-3 | NER | Tripura | PMU-Dharmanagar | 150642 | DN/01008/01006/TR | Completed | Completed | Manu-Simlung Pkg-3 | Rehabilitation & Upgradation of Road from Km 46.597 to Km 66.845 (Total length= 20.248 km) of Kanchanpur-Vanghmun section(PKG-3) on NH-44A to 2 -lane with Paved shoulder in the state of Tripura on EPC Mode under BharatMala Pariyojana (Manu-Simlung -3) | NH(O)-NE | NH | 108 / 44A | 20.248 | - | 20.245 | 347.36 | 225.09 | 2020-03-13 | 2020-06-03 | 2020-07-20 | 100 | 99.73 | 2022-01-19 | - | 2023-07-06 | Rajendra Singh Bhamboo Infra Pvt. Ltd. | rsbipltripura@gmail.com; | Arkitechno Consultants (I) Pvt. Ltd. - G Eng Advisory Services Pvt. Ltd. (JV) | Normal Highway/Road Project
340 | DT-3 | NER | Tripura | PMU-Dharmanagar | 151713 | DN/01008/01007/TR | Under Termination | Under Termination | Manu-Simlung Pkg-4 | Rehabilitation and up-gradation of road from Km 66.845 to 85.125 (Total length: 18.280 Km) of Vanghmun-simlung section on NH-44A (PKG-4) on NH-44A to 2 -lane with Paved shoulder in the state of Tripura on EPC Mode under BharatMala Pariyojana (Manu-Simlung -4) | NH(O)-NE | NH | 108 / 44A | 6.47 | - | 0 | 354.79 | 220.87 | 2021-03-31 | 2021-03-27 | 2021-06-25 | 59.09 | 15.06 | 2022-12-24 | Under Termination | - | JSR Constructions Pvt Ltd - PRN Infratech, Engineers & Contractors (JV) | admin@jsr.co.in | Sterling Indo Tech Consultants Pvt.Ltd. | Normal Highway/Road Project
341 | DT-3 | Non-NER | Uttarakhand | PMU-Barkot | 151224 | DN/09007/01006/UK | Completed | Completed | Protection work at Nalupani | Protection works at Nalupani Landslide (Ex. Km 123.080 to km 123.480, Km. 123.665 to Km. 123.740 and Km. 123.770 to Km. 123.970) Section of NH-34 in the State of Uttarakhand | NH(O) | NH | 34 | 0.735 | - | 0.735 | 47.13 | 34.9 | 2017-03-17 | 2017-06-16 | 2017-09-11 | 0 | 100 | 2019-03-15 | - | 2020-01-15 | KCC Buildcon Pvt. Ltd. | kcc.dharsu@gmail.com | Magot Eng. Consultant. | Slope Protection Work
342 | DT-3 | Non-NER | Uttarakhand | PMU-Barkot | 60113 | DN/09007/01005/UK | Completed | Completed | Protection works at Barethi | Construction of Road, Bridge and Slope Protection Gallery works of Landslide at Barethi (Ex. Km. 100.300 to km 101.060) of Section NH-34 in the State of Uttarakhand on EPC | NH(O) | NH | 34 | 0.76 | - | 0.27 | 40.89 | 28 | 2017-03-17 | 2017-09-18 | 2018-01-04 | 100 | 100 | 2020-01-03 | - | 2021-04-30 | Bharat Constructions (India) Pvt. Ltd. | bharatconstruction248@gmail.com | Magot Eng. Consultant. | Slope Protection Work
343 | DT-3 | Non-NER | Uttarakhand | PMU-Barkot | 149200 | DN/09007/01007/UK | Completed | Completed | Protection work at Dharasu- Gangotri road | Construction of valley side slope stabilization treatment including drainage, cross drainage work and pavement in Dharasu- Gangotri road from km. 123.080 to km 123.970 of NH-34 and stabilization of dumping zone | NH(O) | NH | 34 | 0.89 | - | 0.89 | 23.51 | 18 | 2019-10-11 | 2019-11-22 | 2020-01-08 | 97.7 | 92.81 | 2020-07-05 | - | 2020-08-09 | Chaudhary Construction Company Pvt Ltd. | ccc.nhidcldharasupm@gmail.com | PMU act as AE | Slope Protection Work
344 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 50299 | DN/09006/02014/UK | Completed | Completed | Protection work at Nandprayag, Maithana, Birahi & Gulabkoti | Rehabilitation/ treatment of landslide location with slope protection work and drainage improvement at Nandprayag (Km 420.400), Maithana (km 423.500), Birahi (km 437.400) & Gulabkoti (Km 464.400) on NH-58 with proposed length of 200m, 350m, 100m & 125m respectively in Chamoli district | NH(O) | NH | 58/07 | 0.775 | - | 0.65 | 57.66 | 44.92 | 2015-10-16 | 2016-04-06 | 2016-11-04 | 100 | 99.84 | 2018-05-06 | - | 2021-05-31 | R.G. Buildwell Engineers LTD. | uk.package@gmail.com | Magot Eng. Consultant. | Slope Protection Work
345 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 151306 | DN/09006/02012/UK | Completed | Completed | Protection work at Helang, and Govindghat | Rehabilitation/ Treatment of Landslide location with slope protection and Drainage improvement at Helang (Km 468.200), Govindghat-II (Km 497.000) and Govindghat-III (km 500.000) on Rudraprayag-Mana section on NH-58 (New NH 07) with proposed length of 275m, 150m & 150m respectively in Chamoli District | NH(O) | NH | 58/07 | 0.575 | - | 0.575 | 45.09 | 34.52 | 2015-10-19 | 2016-04-06 | 2016-11-04 | 100 | 100 | 2020-01-31 | - | 2020-01-31 | R.G. Buildwell Engineers LTD. | uk.package@gmail.com | Magot Eng. Consultant. | Slope Protection Work
346 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 123225 | DN/09006/02013/UK | Completed | Completed | Strengthening & Protection work at Gholteer Landslide | Construction of Road and Slope Protection works at Gholteer Landslide from km. 379.100 to km. 380.275 of NH-07 under “Chardham Pariyojna” | NH(O) | NH | 58/07 | 1.175 | - | 1.175 | 89.27 | 65 | 2018-10-22 | 2018-12-10 | 2019-05-03 | 100 | 99.17 | 2020-05-02 | - | 2020-08-25 | Bharat Constructions (India) Pvt. Ltd. | bharatconstruction248@gmail.com | Highway Engineering Consultant - L Telford Consulting Engg Ltd. (LTCE) (JV) | Slope Protection Work
347 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 123224 | DN/09006/02020/UK | Completed | Completed | Strengthening & Protection work at Patalganga Tunnel | Construction and Upgradation of existing road to 2-lane with paved shoulder and Slope Protection Work (450m) & Patalganga Tunnel of (150 m) from existing Km. 458.900 to Km. 459.475 (Design Ch. 456.200 to Ch. 456.800) of Patalganga Landslide of NH-07 under “Chardham Pariyojna” on EPC basis in the state Uttarakhand | NH(O) | NH | 58/07 | 0.6 | - | 0.45 | 45.37 | 37 | 2018-10-22 | 2018-12-10 | 2019-05-03 | 100 | 99.95 | 2020-05-02 | - | 2021-01-31 | Bharat Constructions (India) Pvt. Ltd. | bharatconstruction248@gmail.com | Highway Engg. Consultant (HEC) in association with L Telford Consulting Engg Ltd. (LTCE) | Normal Highway/Road Project
348 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 102034 | DN/09006/02017/UK | Completed | Completed | Rudraprayag to Josimath Pkg-1 | Construction and upgradation of existing road to 2-lane with paved shoulder from Km 368.000 to Km 399.000 of Lameri to Karanprayag (Excluding km 379.000 to km 380.275) of NH-07 under Chardham Pariyojana on EPC basis under NH(O) (Package-I) | NH(O) | NH | 58/07 | 29.125 | - | 28.849 | 274.31 | 163.35 | 2018-03-22 | 2018-03-26 | 2018-05-23 | 97.31 | 97.06 | 2020-11-20 | - | 2024-02-29 | RCC Developers ltd | rccd109@gmail.com | Highway Engineering Consultant - L Telford Consulting Engg Ltd. (LTCE) (JV) | Normal Highway/Road Project
349 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 102035 | DN/09006/02016/UK | Completed | Completed | Rudraprayag to Josimath Pkg-2 | Construction and upgradation of existing road to 2-lane with paved shoulder from km 399.000 to km 430.000 of karanprayag to chamoli (excluding km 420.250 to km 420.500 and km 423.300 to 423.650) of NH-07 under Chardham Pariyojana on EPC basis under NH(O) (Package-2) | NH(O) | NH | 58/07 | 28.8 | - | 28.472 | 403.36 | 258.26 | 2018-03-22 | 2018-03-26 | 2018-05-24 | 98.93 | 98.46 | 2020-11-21 | - | 2024-02-29 | Shivalaya Construction co. Pvt. Ltd. (SCCPL) - Hillways Construction Company Pvt. Ltd. (HCCPL) (JV) | scclhccpljv@rediffmail.com | Highway Engineering Consultant - L Telford Consulting Engg Ltd. (LTCE) (JV) | Normal Highway/Road Project
350 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 102036 | DN/09006/02015/UK | Completed | Completed | Rudraprayag to Josimath Pkg-3 | Construction and Upgradation of existing road to 2-lane with paved shoulder from Km 430.000 to Km 468.000 of Chamoli to Paini (excluding Km 437.625 to Km 437.775, Km 458.900 to Km 459.475 and Km 464.425 to Km 464.525) of NH-07 under Chardham Pariyojana on EPC basis under NH(O) (Package-3) | NH(O) | NH | 58/07 | 36.675 | - | 36.161 | 417.24 | 307.28 | 2018-03-22 | 2018-03-26 | 2018-05-23 | 99.88 | 98.88 | 2020-11-20 | - | 2024-03-31 | Naresh Kumar Garg Infrastructure Ltd. (NKG) | nkg@nkgindia.com | Highway Engineering Consultant - L Telford Consulting Engg Ltd. (LTCE) (JV) | Normal Highway/Road Project
351 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 157531 | DN/09006/02011/UK | Ongoing | Under Construction (AD issued) | Construction for Mitigation Measures Pkg-1 | Construction for Mitigation Measures of 10 Nos. Landslides, 01 No. Sinking Zones and 1 No. of Minor Bridge in between at Ch. Km 368.00 to Km 433.00 on NH-07 on EPC (Package-1) | NH(O) | NH | 58/07 | 1.69 | - | 0.27 | 216.68 | 93 | 2023-12-07 | 2024-03-15 | 2024-06-14 | 98.61 | 95.71 | 2025-12-14 | 2026-07-18 | - | Bharat Constructions (India) Pvt. Ltd. | bciplnhidclpkg01kpg@gmail.com | URS Scott Wilson India Private Limited in JV with Aecom India Pvt Ltd. in association with Shweta Technophile Consultants Pvt Ltd. | Slope Protection Work
352 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 157525 | DN/09006/02010/UK | Ongoing | Under Construction (AD issued) | Construction for Mitigation Measures Pkg-2 | Construction for Mitigation Measures of 5 Nos. Landslides, 5 Nos. Sinking Zones in between Ch. 433.00 to 450.00 (BANERPANI VILLAGE) on NH-07 on EPC mode in the state of Uttarakhand (Package-2) | NH(O) | NH | 58/07 | 1.99 | - | 0.27 | 259.64 | 102 | 2023-12-07 | 2024-03-15 | 2024-12-16 | 64.23 | 58.18 | 2026-06-15 | 2027-01-03 | - | SRM (Shri Ram Mehta) Contractors Pvt. Ltd. | srmcontractors@gmail.com srmslope@gmail.com | URS Scott Wilson India Private Limited in JV with Aecom India Pvt Ltd. in association with Shweta Technophile Consultants Pvt Ltd. | Slope Protection Work
353 | DT-3 | Non-NER | Uttarakhand | PMU-Chamoli | 157526 | DN/09006/02009/UK | Ongoing | Under Construction (AD issued) | Construction for Mitigation Measures Pkg-3 | Construction for Mitigation Measures of 5 Nos. Landslides, 5 Nos. Sinking Zones and 1 No. of Minor Bridge in between at Ch. Km 450.00 to Km 468.00 on NH-07 on EPC (Package-3) | NH(O) | NH | 58/07 | 1.4615 | - | 0.14 | 250.33 | 104.28 | 2023-12-07 | 2024-03-15 | 2024-06-14 | 87.57 | 71.73 | 2025-12-14 | 2027-02-24 | - | RSB Projects Pvt. Ltd.-SRM (Shri Ram Mehta) Contractors Pvt. Ltd. (JV) | srmcontractors@gmail.com srmslope@gmail.com | URS Scott Wilson India Private Limited in JV with Aecom India Pvt Ltd. in association with Shweta Technophile Consultants Pvt Ltd. | Slope Protection Work
354 | DT-3 | Non-NER | Uttarakhand | PMU-Barkot | 68016 | DN/09005/01002/UK | Ongoing | Under Construction (AD issued) | Silkyara Bend- Barkot Tunnel | Construction, Operation & Maintenance of 2-L Bi-directional Silkyara Bend- Barkot Tunnel with escape passage including approaches (Tunnel-4.531 & Approach road- 0.328) on Dharasu-Yamunotri section b/w Chainage 25.400km and 51.00km falling along NH-134 (Old NH-94) on EPC mode Silkyara Side (South Portal) & Barkot Site (North Portal) | NH(O) | NH | 94/134 | 4.859 | - | 0.51 | 1383.78 | 853.79 | 2018-03-09 | 2018-05-31 | 2018-07-09 | 73.5 | 72.48 | 2022-07-08 | 2027-03-31 | - | Navayuga Engineering Company Limited (NEC) | necdocumentcontroller@gmail.com nec@navayuga.com | TPF Getinsa Euroestudios S.L in association with Rodic Consultant Pvt. Ltd. | Standalone Tunnel Project
355 | DT-1 | Non-NER | West Bengal | PMU-Kalimpong | 148459 | DI/06002/01002/WB | Completed | Completed | Mechi Bridge | Construction of Mechi bridge (of 675m) and Approaches of 2/4-Lane with paved shoulder on NH-327B across Indo-Nepal border on Asian Highway (AH -02) by ADB fund under SASEC Tranche-2 on EPC mode | EAP (ADB) | NH | 327B | 1.5 | - | 1.405 | 158.65 | 103.78 | 2017-03-23 | 2017-11-23 | 2018-02-01 | 100 | 97.52 | 2021-01-30 | - | 2020-09-05 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | draiplmechi@gmail.com | Yongma Engg. - Redecon India Pvt. Ltd. With Cho & Kim Engg. (JV) | Standalone Bridge Project
356 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 60102 | DN/09021/03003/WB | Completed | Completed | Rangpo-Viaduct (Atal Setu) | Construction of Rangpo-Viaduct of 826 m Viaduct Bridge at Rangpo between km 51.100 to 53.900 along with approaches with total project length of 1.123 Km on Sevoke – Gangtok road (NH-10) in the State of West Bengal and Sikkim under SARDP-NE Phase-A on EPC mode (Atal Setu) | SARDP-NE | NH | 31A/10 | 1.123 | - | 0 | 133.49 | 55.79 | 2016-11-08 | 2016-12-16 | 2017-02-20 | 92.84 | 80.82 | 2020-02-20 | - | 2022-06-08 | Dineshchandra R. Agarwal Infracon Pvt. Ltd. (DRAIPL) | - | Technocrats Advisory Services Pvt Ltd (TASPL) | Standalone Bridge Project
357 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 145870 | DN/19002/01013/WB | Completed | Physically Completed & CC Under Issue | Bagrakot-Kafer IV A | Construction of alternative highway to Gangtok in Sikkim via Bagrakot -Chuikhim-Nimbong -Kafer-Bakhim-Algarah-Rhenock in the State of West Bengal and from Rhenok-Rorathang-Pakyong along with spur from Aritar-Rolep-Menla in the State of Sikkim (from Km 0.00 to Km 13.00 of Bagrakot -Kafer section of NH 717A on EPC Mode under Phase-A of SARDP-NE in the State of West Bengal) PKG- IVA | SARDP-NE | NH | 717A | 15.24 | - | 15.24 | 402.94 | 261 | 2018-03-22 | 2019-03-01 | 2019-10-04 | 99.23 | 75.04 | 2022-04-03 | 2026-08-30 | - | N Siva Prakash Reddy (NSPR) Constr. (I) Pvt. Ltd. - Vinod Kumar Jain (VKJ) (JV) | nsprvkj.bagrakot@gmail.com | Yongma Engineering Pvt Ltd in JV with Redecon India Pvt Ltd in ass. with CHO & KIM Ltd | Normal Highway/Road Project
358 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 150915 | DN/19002/01014/WB | Ongoing | Under Construction (AD issued) | Bagrakot-Kafer IV B | Construction of alternative highway to Gangtok in Sikkim via Bagrakot -Chuikhim-Nimbong -Kafer-Bakhim-Algarah-Rhenock in the State of West Bengal and from Rhenock-Rorathang-Pakyong along with spur from Aritar-Rolep-Menla in the State of Sikkim (from Km 13.00 to Km 25.60 of Bagrakot -Kafer section of NH 717A on EPC Mode under Phase-A of SARDP-NE in the State of West Bengal) PKG- IVB | SARDP-NE | NH | 717A | 12.6 | - | 12.32 | 295.97 | 184.46 | 2018-03-22 | 2020-08-19 | 2020-10-05 | 97.73 | 95.42 | 2023-04-05 | 2026-07-30 | - | Rani Constructions Pvt. Ltd. - Sri Satya Sai Infrastructrue Pvt. Ltd. (JV) | nh717a.4b@ranigroup.com> | Yongma Engineering Pvt Ltd in JV with Redecon India Pvt Ltd in ass. with CHO & KIM Ltd | Normal Highway/Road Project
358 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | WB-1 | DN/19002/01020/WB | Sanctioned not awarded | Sanctioned not awarded | Slope Protection work on Bagrakot-Kafer IVC | Specialised Slope Protection Work of section from Km 25.60 to Km 26.10 of Bagrakot-Kafer of NH-717A in the state of West Bengal (Package-IV C) | NH(O) | NH | 717A | 0.5 | - | 0 | 86.664 | 0 | 2025-03-31 | - | - | 0 | 0 | - | - | - | - | - | - | Slope Protection Work
359 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 149354 | DN/19002/01010/WB | Completed | Completed | Bagrakot-Kafer IV D | Construction of alternative highway to Gangtok in Sikkim via Bagrakot -Chuikhim-Nimbong -Kafer-Bakhim-Algarah-Rhenock in the State of West Bengal and from Rhenock-Rorathang-Pakyong along with spur from Aritar-Rolep-Menla in the State of Sikkim (Package No. IVD from Km 26.10 to 40.00 of Bagrakot - Kafer section of NH 717A on EPC Mode under Phase A of SARDP-NE in the State of West Bengal) PKG- IVD | SARDP-NE | NH | 717A | 13.9 | - | 13.902 | 242.97 | 177.99 | 2018-03-22 | 2020-03-20 | 2020-06-11 | 100 | 99.42 | 2022-06-10 | - | 2024-01-02 | Ketan Construction Ltd.(KCL)-Bhutan Builders Pvt. Ltd.(BBPL) (JV) | kclbbpl2020@gmail.com | Yongma Engineering Pvt Ltd in JV with Redecon India Pvt Ltd in ass. with CHO & KIM Ltd | Normal Highway/Road Project
360 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 150916 | DN/19002/01011/WB | Ongoing | Under Construction (AD issued) | Kafer- Lava More (Pkg-VA) | Construction & upgradation of existing road to 2-lane with paved shoulder including geometric improvement of Kafer- Lava More section from km 40.00 to km 61.100 of NH717-A on EPC under SARDP-NE A in state of West Bengal (Pkg-VA) | SARDP-NE | NH | 717A | 21.1 | - | 20.81 | 273.78 | 189.26 | 2020-06-25 | 2020-08-21 | 2020-10-05 | 95.98 | 94.17 | 2023-04-05 | 2026-07-30 | - | Rani Constructions Pvt. Ltd. - Sri Satya Sai Infrastructrue Pvt. Ltd. (JV) | nh717a.5a@ranigroup.com | Chaitanya Projects Consultancy Pvt. Ltd. - MPG Engineering Consultancy Pvt. Ltd. (JV) | Normal Highway/Road Project
360 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | WB-2 | DN/19002/01019/WB | Sanctioned not awarded | Sanctioned not awarded | Lavamore (Km 61.10) to Start of Pedong Bypass (Km 79.700) (NH-717A) | Widening and Up-gradation of existing carriageway into 2-lane with paved shoulder from LavaMore (Km 61.100) to Start of Pedong Bypass (Km 79.700) (NH-717A) in the State of West Bengal on EPC Mode | NH(O) | NH | 717A | 18.6 | - | 0 | 522.346 | - | 2025-03-31 | - | - | 0 | 0 | - | - | - | - | - | - | Normal Highway/Road Project
361 | DT-1 | Non-NER | West Bengal | PMU-kalimpong | 150917 | DN/19002/01012/WB | Completed | Physically Completed & CC Under Issue | Pedong bypas-Reshi Border Pkg-VB (Bypass) | Construction & upgradation of existing road to 2-lane with paved shoulder including geometric improvement of sect. from Pedong bypass to Reshi Border km 79.700 to km 96.254 of NH-717A under SARDP-NE-A on EPC (Lava More-Reshi Border ) Pkg-VB as part of Alternate connectivity to Gangtok | SARDP-NE | NH | 717A | 16.554 | - | 16.19 | 395.59 | 240.3 | 2020-06-29 | 2020-07-24 | 2020-10-20 | 97.2 | 91.28 | 2022-04-17 | 2026-08-31 | - | TTC Infra India- Suryodaya Infra Projects Pvt Ltd (SIPL) (JV) | ttc.prpkgvb@gmail.com | Chaitanya Projects Consultancy Pvt. Ltd. - MPG Engineering Consultancy Pvt. Ltd. (JV) | Standalone Bypass Project
362 | DT-1 | Non-NER | West Bengal | PMU-Siliguri | WB/PWD/2 | DN/09021/03008/WB | Ongoing | Under Construction (AD issued) | Slope protection and landslide mitigation at 4 vulnerable locations (km 1.950 to Km 2.100, km 11.100 to 11.450, km 22.435 to km 22.485 and km 22.610 to km 22.680) on NH-10 | Slope protection and landslide mitigation at 4 vulnerable locations (km 1.950 to Km 2.100, km 11.100 to 11.450, km 22.435 to km 22.485 and km 22.610 to km 22.680) within Sevoke-Rangpo section of NH-10 (old NH-31A) in Darjeeling & Kalimpong district in the State of West Bengal on EPC mode | NH(O) | NH | 31A/10 | 0.62 | - | 0 | 152.27 | 91.3 | 2024-02-05 | 2025-01-10 | 2025-06-26 | 31.29 | 23.04 | 2027-06-26 | 2027-06-26 | - | Geo-spar Infra Pvt. Ltd.- SVS Mookambika Construction Pvt. Ltd.(SVSMC) (JV) | info@spargrp.com | Lea Associates South Asia Pvt. Ltd. | Slope Protection Work
363 | DT-1 | Non-NER | West Bengal | PMU-Siliguri | WB-3 | DN/09021/03007/WB | Awarded, Not Appointed | Awarded, Not Appointed | Slope Protection work at 3 Vulnerable Locations on Sevoke-Rangpo NH-10 | Slope Protection and Landslide Mitigation at 3 Vulnerable Locations (from actual chainages 6.50 to Ch. 6.705, Ch. 7.17 to Ch. 7.25 and Ch. 22.800 to Ch. 22.950) within Sevoke -Rangpo section of NH-10 (old NH 31A) in the district of Kalimpong in west Bengal | NH(O) | NH | 31A/10 | 0 | - | 0 | 57.21 | 28 | 2025-03-27 | 2026-02-03 | To be given | 0 | 0 | - | - | - | Bharat Constructions (India) Pvt. Ltd. | - | Dhruv Consultancy Services Limited in association with M S Consultant | Slope Protection Work
364 | DT-1 | Non-NER | West Bengal | PMU-Siliguri | WB/PWD/1 | DN/09021/03009/WB | Ongoing | Under Construction (AD issued) | Slope Protection and Landslide Mitigation work at 2 Vulnerable Locations on Sevoke-Rangpo NH-10 | Slope Protection and Landslide Mitigation at 2 Vulnerable locations viz. Km 23.200 to 23.960, Km 26.530 to Km 26.580 within Sevoke-Rangpo section of NH-10 (old NH-31A) in Kalimpong district in the State of West Bengal on EPC mode | NH(O) | NH | 31A/10 | 0.81 | - | 0 | 68.49 | 49 | 2023-09-25 | 2024-07-12 | 2024-09-06 | 5 | 0 | 2026-03-08 | 2026-11-08 | - | Nagyan Construction Pvt. Ltd. (NCPL) | - | Lea Associates South Asia Pvt. Ltd. | Slope Protection Work
365 | DT-1 | Non-NER | West Bengal | PMU-Siliguri | WB/PWD/4 | DN/09021/04002/WB | Awarded, Not Appointed | Awarded, Not Appointed | Widening of culverts & Valley side protection works at 13 locations on NH-10 | Widening of Valley side at 3 locations viz. Km 20.900, Km 35.500 and Km 36.700 and culvert at 13 locations viz. Km 17.600, Km 17.800, Km 18.300, Km 20.200, Km 21.500, Km 21.650, Km 21.850, Km 32.800, Km 33.100, Km 38.300, Km 40.300, Km 43.700, Km 47.300 on NH-10 (old NH-31A)on EPC mode in the State of West Bengal | NH(O) | NH | 31A/10 | 2.2 | - | 0 | 75.85 | 38.246 | 2024-06-04 | 2026-02-12 | To be given | 0 | 0 | - | - | - | Tvastar Infratech Pvt. Ltd. | - | - | Slope Protection Work
365 | DT-1 | Non-NER | West Bengal | PMU-Siliguri | WB/PWD/3 | DN/09021/04003/WB | Sanctioned not awarded | Sanctioned not awarded | Valley side protection works to restore damages by flash flood on NH-10 | Valley side protection works from km. 25.80 to km 26.65, km 26.75 to km 27.20 & km 27.41 to km 27.48 to restore damages by flash flood in 2023 of NH-10 in the District of Kalimpong during the year 2024-25 on EPC mode | NH(O) | NH | 31A/10 | 1.37 | - | 0 | 49.22 | 0 | 2024-06-04 | To be Re-Tendered along with revised design | To be given | - | - | - | - | - | To be Re-Tendered along with revised design | - | - | Slope Protection Work
366 | DT-2 | Non-NER | West Bengal | PMU-Darjeeling | WB/PWD/5 | DN/09028/01001/WB | Ongoing | Under Construction (AD issued) | Reconstruction & widening of 08 nos. Culverts & Repair of old parapets on Darjeeling - Siliguri section on NH-110 | Reconstruction and widening of 08 nos. narrow culvert at km 22.445, km 22.450, km 22.840, km 27.565, km 29.000 ( half portion), km 29.500, km 30.650, km 38.290 & spot improvement from km 22.397 to km 22.442, km 22.445 to km 22.450, km 22.453 to km 22.493, km 26.855 to km 26.935, km 27.125 to km 27.175, km 27.492 to km 27.562, km 27.565 to km 27.710, km 29.487 to km 29.502, km 29.506 to km 29.513, km 32.710 to km 32.750, km 32.885 to km 32.910, km 38.185 to km 38.285, km 38.290 to km 38.330 & Repair of old parapets, construction of new parapet, road signage such as Median Marker, Road Marking etc. in selected stretches from km 20.00 to km 40.00 of NH-110 ( Old NH-55) in the district of Darjeeling under Annual Plan 2022-23 | NH(O) | NH | 55/110 | 0.662 | - | 0 | 13.49 | 12.767 | 2023-01-04 | 2024-01-25 | 2024-03-01 | 94 | 92.4 | 2025-02-28 | 2026-08-15 | - | DDSD Construction Co. | ddsdcc12@gmail.com | - | Standalone Structure Project
367 | DT-3 | Non-NER | West Bengal | PMU-Darjeeling | WB/PWD/6 | DN/09028/01005/WB | Ongoing | Under Construction (AD issued) | Slope Stabilization Scheme at location of landslide at km 52.240 km & km 42.800 on Darjeeling - Siliguri section on NH-110 | Slope Stabilization Scheme at location of landslide at km 52.240 km & Km 42.800 of NH-110 at Tindharia, West Bengal & Permanent Restoration of damaged Road under NH Division-IX in the district of Darjeeling, West Bengal during the year 2022-23 | NH(O) | NH | 55/110 | 0.134 | - | 0 | 24.52 | 15.08 | 2023-03-22 | - | 2024-09-06 | 77 | 75.11 | 2026-03-09 | 2026-11-30 | - | Pavai Infra Geotech, Coimbatore, Tamilnadu. | info@pavaigeotech.com | - | Slope Protection Work
368 | DT-4 | Non-NER | West Bengal | PMU-Darjeeling | WB/PWD/7 | DN/09028/01003/WB | Ongoing | Under Construction (AD issued) | Improvement of Spots Including widening of culvert, drops & guide in between km 0.00 to km 20.00 on Darjeeling - Siliguri section on NH-110 | Improvement of Spots (Including widening of culvert, drops & guide) from km 4.390 to km 4.585, km 5.328 to km 5.430, km 8.520 to km 9.075 (At 02 nos. of locations), km 9.335 to km 9.520 and km 12.060 to 12.235 on NH-110 (Old NH-55) in between km 0.00 to km 20.00 of NH-110 under NH Division-IX in the District of Darjeeling, West Bengal [2023-24/RSEC-15] | NH(O) | NH | 55/110 | 1.212 | - | 0 | 15.02 | 13.08 | 2024-03-01 | - | 2025-03-17 | 52 | 25.84 | 2026-03-16 | 2026-08-31 | - | Sun Shine Overseas Pvt. Ltd. | sopl.ebp@gmail.com | - | Standalone Structure Project
369 | DT-5 | Non-NER | West Bengal | PMU-Darjeeling | WB/PWD/8 | DN/09028/01004/WB | Ongoing | Under Construction (AD issued) | Improvement of Spots including reconstruction and widening of Culverts in between km 20.00 to km 40.00 on Darjeeling - Siliguri section on NH-110 | Improvement of Spots from 21.710 km to 21.838 km (including reconstruction & culvert widening), 21.921 km to 22.000 km (including drop & guides), 23.760 km to 23.800 km, 26.597 km to 26.705 km (including drop & Guides), 28.270 km to 28.340 km, 35.878 km to 35.980 km, 36.025 km to 36.135 km, 36.245 km to 36.400 km (including reconstruction & culvert widening) on NH-110 (old NH-55) in between km 20.00 to km 40.00 of Nh-110 (old NH-55) under NH Division No.-IX in the dist. of Darjeeling | NH(O) | NH | 55/110 | 0.792 | - | 0 | 14.48 | 13.19 | 2024-03-06 | - | 2024-09-11 | 97 | 94.01 | 2025-09-11 | 2026-08-15 | - | Kundan Tamang | kundantamangslg@rediffmall.com | - | Standalone Structure Project
370 | DT-6 | Non-NER | West Bengal | PMU-Darjeeling | WB/PWD/9 | DN/09028/01002/WB | Ongoing | Under Construction (AD issued) | Improvement of Spots including reconstruction and widening of Culverts in between km 40.000 to km 65.000 on Darjeeling - Siliguri section on NH-110 | Improvement of Spots including reconstruction and widening of Culverts in between Ch. km 40.000 to km 65.000 of NH-55 (New NH-110) under NH Division – IX (I) in the District of Darjeeling, West Bengal in the FY 2024-25 | NH(O) | NH | 55/110 | 2.847 | - | 0 | 32.35 | 31.18 | 2024-12-23 | 2025-04-23 | 2025-04-23 | 66 | 57.13 | 2026-04-21 | 2026-08-31 | - | Daljyor Unemployed Engineer’s Co-operative Society Ltd. | daljyor2008@gmail.com | - | Standalone Structure Project
371 | DT-1 | NER | Assam (MMLP) | PMU-Bongaigaon | 151165 | DN/26001/01003/AS | Completed | Physically Completed & CC Under Issue | MMLP Pkg-1 | INFRASTRUCTURE WORK: MMLP (Package-I: Road and Utility Works) | NHLML | - | 17 | 4.25 | - | 4.25 | 693.97 | 165.94 | 2020-02-03 | 2020-06-05 | 2020-09-30 | 100 | 95.8 | 2022-04-01 | Physically Completed C.C Under Issue | 2024-09-30 | RAM CHANDRA PAUL | ram_chandrapaul@yahoo.in | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | INFRASTRUCTURE WORK: MMLP
372 | DT-1 | NER | Assam (MMLP) | PMU-Bongaigaon | 151166 | DN/26001/01002/AS | Completed | Completed | MMLP Pkg-2 | INFRASTRUCTURE WORK: MMLP (Package-II: Building and Infrastructure works) | NHLML | - | 17 | - | - | 0 | 0 | 80.08 | 2020-02-03 | 2020-08-05 | 2020-09-30 | 98.28 | 95.51 | 2022-04-03 | - | 2023-12-25 | Credible Engineering Construction Pvt. Ltd. | credibleengineering@gmail.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | INFRASTRUCTURE WORK: MMLP
373 | DT-1 | NER | Assam (MMLP) | PMU-Bongaigaon | 151167 | DN/26001/01001/AS | Completed | Physically Completed & CC Under Issue | MMLP Pkg-3 | INFRASTRUCTURE WORK: MMLP (Pkg.-III : External Rail Connectivity) | NHLML | - | Not Applicable | 3.76 | - | 0 | 0 | 21.85 | 2020-02-03 | 2020-10-09 | 2020-12-01 | 93.23 | 90.27 | 2022-06-01 | Physically Completed C.C Under Issue | 2024-09-20 | Sumcon Infraventures LLP | gunjan@sumconinfraventures.com | AECOM (Asia Company Limited) - Krivam Consultant Private Limited (JV) | INFRASTRUCTURE WORK: MMLP
374 | DT-1 | NER | Assam (MMLP) | PMU-Bongaigaon | 153343 | DN/26001/02001/AS | Completed | Physically Completed & CC Under Issue | IWT Terminal at MMLP | INFRASTRUCTURE WORK: Deveopment of Inland Water Transport (IWT) Terminal at MMLP Jogighopa | NHLML | - | NW-2 | - | - | 0 | 70.92 | 63.9 | 2021-06-07 | 2021-10-06 | 2022-04-22 | 98.74 | 98.43 | 2023-10-14 | Physically Completed C.C Under Issue | 2024-07-31 | DVP Infra Projects Pvt. Ltd. | info@dvpinfra.com | Arkitechno Consultant (I) Pvt. Ltd. | INFRASTRUCTURE WORK: MMLP
[10 empty] | 1 | [19 empty] | 0

## Sheet1 (hidden)
NH/ NON-NH | NH
Sum of Project Length | Column Labels
Row Labels | Awarded, Not Appointed | Completed | Ongoing | Sanctioned not awarded | Terminated | Under Termination | Grand Total
Andaman & Nicobar |  | 142.781 | 90.005 |  |  | 88.865 | 321.651
4 |  | 142.781 | 90.005 |  |  | 88.865 | 321.651
Arunachal Pradesh | 79.959 | 582.538 | 353.693 |  |  |  | 1016.19
13 |  | 65.85 | 18.464 |  |  |  | 84.314
113 |  | 88.963 |  |  |  |  | 88.963
313 |  | 130.3 | 75.236 |  |  |  | 205.536
513 |  | 23.38 |  |  |  |  | 23.38
713 |  | 118.36 |  |  |  |  | 118.36
913 | 55.14 |  | 224.927 |  |  |  | 280.067
13 & 15 | 24.819 | [5 empty] | 24.819
215 |  | 155.685 |  |  |  |  | 155.685
15 |  |  | 35.066 |  |  |  | 35.066
Assam | 33.622 | 621.056 | 683.817 | 33.7 | 24.25 |  | 1396.445
8 |  |  | 43.7 |  |  |  | 43.7
17 |  | 42.58 | 153.686 |  |  |  | 196.266
29 |  | 95 | 23.249 |  |  |  | 118.249
37 | 13.09 | 7.65 | 50.33 |  |  |  | 71.07
137 |  |  | 79.61 |  |  |  | 79.61
306 |  |  | 29.36 |  |  |  | 29.36
127B |  | 26.504 | 46.932 |  |  |  | 73.436
208A |  | 17.95 |  |  |  |  | 17.95
37 & 306 |  |  | 20 |  |  |  | 20
37 & 8 |  |  | 24.2 |  |  |  | 24.2
6 & 37 |  |  | 22.9 |  |  |  | 22.9
15 |  | 143.277 |  |  |  |  | 143.277
315 | 20.532 | 33 |  |  | 10.25 |  | 63.782
127 |  | 18.4 | 18.315 |  |  |  | 36.715
715 |  | 69.568 | 42.057 |  | 14 |  | 125.625
715 & 15 |  | 16.862 |  | 33.7 |  |  | 50.562
415 |  | 10.08 |  |  |  |  | 10.08
2 |  | 46.075 | 52.223 |  |  |  | 98.298
27 |  | 25.25 |  |  |  |  | 25.25
117 |  | 14.66 |  |  |  |  | 14.66
15 & 315 |  |  | 41.32 |  |  |  | 41.32
217 |  |  | 8.415 |  |  |  | 8.415
515 |  | 54.2 | 27.52 |  |  |  | 81.72
Jammu & Kashmir (RO-Jammu) | 4.037 | 119.16 | 67.49 |  | 1.269 |  | 191.956
244 | 4.037 | 113.96 | 41.98 |  | 1.269 |  | 161.246
144A |  | 5.2 | 25.51 |  |  |  | 30.71
Jammu & Kashmir (RO-Srinagar) |  | 91.213 | 30.893 | 9.866 |  |  | 131.972
1 |  | 11.98 | 30.893 |  |  |  | 42.873
244 |  | 27.943 |  | 9.866 |  |  | 37.809
701A |  | 42.82 |  |  |  |  | 42.82
Connecting NH-244 & NH-44 |  | 8.47 |  |  |  |  | 8.47
Ladakh |  | 98.935 | 102.25 |  | 24.04 |  | 225.225
301 |  | 98.935 | 102.25 |  | 24.04 |  | 225.225
Manipur | 21.201 | 382.923 | 668.43 | 51.985 |  |  | 1124.539
29 |  |  | 11.009 |  |  |  | 11.009
37 |  | 47.835 | 157.044 |  |  |  | 204.879
137 |  | 70.724 | 64.12 |  |  |  | 134.844
202 | 14.63 | 14.72 | 126.652 |  |  |  | 156.002
102A |  |  | 96.38 |  |  |  | 96.38
102B |  | 48.587 | 95.35 |  |  |  | 143.937
102C |  | 18 |  |  |  |  | 18
129A |  | 87.154 | 22.34 |  |  |  | 109.494
Connecting NH-202 & NH-102A | 6.571 | [5 empty] | 6.571
2 |  |  | 95.535 | 51.985 |  |  | 147.52
102 |  | 95.903 |  |  |  |  | 95.903
Meghalaya | 36.79 | 51.536 | 141.39 | 164.355 |  |  | 394.071
6 |  |  |  | 164.355 |  |  | 164.355
127B |  |  | 36.64 |  |  |  | 36.64
Connecting NH-127B & NH-217 | 29.03 | [5 empty] | 29.03
217 |  | 51.536 | 40.84 |  |  |  | 92.376
106 & 206 |  |  | 11.6 |  |  |  | 11.6
206 | 7.76 |  | 52.31 |  |  |  | 60.07
Mizoram | 10.6 | 560.296 | 247.614 |  |  |  | 818.51
6 | 10.6 | 119.38 | 48.31 |  |  |  | 178.29
302 |  |  | 74.95 |  |  |  | 74.95
102B |  | 68.17 | 30.41 |  |  |  | 98.58
306 & 6 |  |  | 65.7 |  |  |  | 65.7
502A |  |  | 28.244 |  |  |  | 28.244
2 |  | 372.746 |  |  |  |  | 372.746
Nagaland | 17 | 257.989 | 214.556 |  | 41.184 |  | 530.729
29 |  | 79.635 | 57.61 |  | 14.935 |  | 152.18
202 |  | 42.44 |  |  |  |  | 42.44
702 |  | 30.68 |  |  |  |  | 30.68
129A | 17 | 14.7 | 49.955 |  |  |  | 81.655
202K |  |  | 106.991 |  |  |  | 106.991
702A |  | 90.534 |  |  |  |  | 90.534
2 |  |  |  |  | 26.249 |  | 26.249
Sikkim |  | 61.2 | 108.237 | 5.3 | 7.322 | 31.37 | 213.429
510 |  | 33.6 | 25.24 |  |  | 31.37 | 90.21
717A |  | 26.7 | 16.167 | 5.3 |  |  | 48.167
717B |  |  | 66.83 |  | 7.322 |  | 74.152
10 |  | 0.9 |  |  |  |  | 0.9
Tripura | 72.472 | 412.063 | 228.268 |  |  | 31.872 | 744.675
8 | 72.472 | 211.576 | 34.187 |  |  |  | 318.235
208 |  | 90.7 | 143.013 |  |  |  | 233.713
108A |  | 21.412 |  |  |  |  | 21.412
208A |  | 25.25 | 11.21 |  |  |  | 36.46
Connecting NH-08 & 108B | [5 empty] | 25.402 | 25.402
108B |  | 26.8 | 12 |  |  |  | 38.8
44A |  | 36.325 | 27.858 |  |  | 6.47 | 70.653
Uttarakhand |  | 100.11 | 10.0005 |  |  |  | 110.1105
34 |  | 2.385 |  |  |  |  | 2.385
7 |  | 97.725 | 5.1415 |  |  |  | 102.8665
134 |  |  | 4.859 |  |  |  | 4.859
West Bengal | 2.2 | 16.523 | 66.924 | 20.47 |  |  | 106.117
327B |  | 1.5 |  |  |  |  | 1.5
717A |  | 13.9 | 65.494 | 19.1 |  |  | 98.494
10 | 2.2 | 1.123 | 1.43 | 1.37 |  |  | 6.123
Grand Total | 277.881 | 3498.323 | 3013.5675 | 285.676 | 98.065 | 152.107 | 7325.6195