## Sheet1 (2)
Pre-bid clarifications for Zozila tunnel work held on 25.04.2016
Sl. No | Reference Clause No. | Description / Existing Clause | Clarification sought | Reply
1 | Schedule-A Annex-1, 1.1 | The site: The Project Highway aims at construction of tunnels and approaches in general area between km 95 & km 119 of the Srinagar - Leh section of NH-1 as per following details: 14.150 km long two lane bidirectional single tube tunnel with a parallel 14.200 km long egress tunnel on new alignment between Baltal & Minamarg along the existing NH-1 in J&K. | Being DBFOT project, can the Concessionaire, without increase in cost and time, be allowed to follow the international practice and design and adopt alternative section like twin tube unidirectional layout instead of one bidrectional traffic tunnel and one egress tunnel, both tubes having same c/s ,i.e. a clear width of 6.5m and height of 5.5m in addition to the 1.0m wide maintenance walkways at both sides. this arrangement will be efficient in accident prevention, no chance of head on collission and allow smooth movement of traffic. The approach shall be modified accordingly with both roads converging at a small distance from portal face as per design requirements. | As per RFP
2 | General |  | The requirement of ventiliation systems shall be allowed to be provided based on design requirements. The number of ventilation shafts can be reduced to two, considering reduction of tunnel height. Whether it will be permitted if alternate design is adopted by the Concessionnaire. | The numbers for ventilation design & shafts are as per RFP.

## Sheet1
Pre-Bid Clarifications for the Zozila Tunnel work held on 07.09.15 and 26.11.2015
Sl. No | Reference Clause No. | Description / Existing Clause | Clarification sought | Reply
1 | Clause 2.20 Bid Security RFP Vol. I (ITB) | “The Bidder shall furnish as part of its Bid, a Bid Security referred to in Clauses 2.1.7 and 2.1.8 hereinabove in the form of a bank guarantee issued by a nationalised bank, or a Scheduled Bank in India" | With reference to the submission of Bank Guarantee as Bid Security, kindly clarify the followings: i) In case of a consortium, whether the Bid Security is to be submitted by the Lead Member only or can be submitted by all the members of the Consortium for an aggregate amount of Rs.90.90 Crores? ii) In case the Bank Guarantee is allowed to be submitted by all the members of the Consortium for an aggregate amount of Rs.90.90 Crores, whether the same is to be submitted in their proportion in the Consortium or can be submitted for any amount aggregating to Rs. 90.90 Crores? iii) Whether the Bank Guarantee can be submitted from more than one bank by any member of the consortium/Bidder? If yes, is there any limit on the number of Bank Guarantees aggregating to Rs.90.90 Crores? | As per RFP documents.
2 | Recital F RFP Vol. II (DCA) | “The selected bidder/Consortium has since promoted and incorporated the Concessionaire as a limited liability company under the Companies Act 1956… … …” | The erstwhile Companies Act 1956 has been replaced by Companies Act 2013. In this regard, it is kindly requested to modify the concerned clauses accordingly. | As per RFP documents. For avoidance of doubt, it is clarfied that Companies Act, 2013 is mentioned in Recital F of RFP Vol. I (DCA).
3 | Recital F RFP Vol. II (DCA) | “The selected bidder/Consortium has since promoted and incorporated the Concessionaire as a limited liability company under the Companies Act 1956… … …” | Kindly clarify whether an existing company can assume the role and responsibilities of the Concessionaire, if allowed under its Memorandum of Association/Article of Association? | As per RFP documents.
4 | Appendix A2 | Detailed Geological Report | Request you to provide available Borelog details for the project | Could be collected from MORT&H. High volume data could not be uploaded.
5 | Appendix B1 Typical Drawings | Ventlation Cavern Drawing Drg No - 8482B_II-ZOT_GEN-04-12-00 | Request you to provide the cross section for Ventilation Cavern | Attached (Ref Annexure-1)
6 | Schedule - B Cl. 1.16 | Muck Dump Disposal. | It has been mentioned that permission shall be obtained from the Local authorities (Civil Administration/Wild life / Forest). We presume that all the permissions will be obtained by Authority. Authority also has to provide the access route for the Muck disposal Yard. | Wildlife/Forest permission- Not required. Muck disposal areas are accessible (Ref-Annexure-2).- Route to be developed by concessionaire
7 | Schedule - B Cl. 5.4 | Proposed ROW for Approaches | Width of ROW is varying due to site condition. The Details of Proposed ROW to be ascertained form local BRO. Authority shall be single point contract for Concessionaire. Authority has to coordinate with BRO & provide ROW details immediately to calculate the cost before bid. Please clarify. | ROW is available. If required additional land will be acquired for the approach road. Authority will help and facilitate with local Govt. Details of Approach rods, culverts, bridges, snow gallery, avalanche central structure, requirement of Amarnath Shrine Board and status of LA are at Annexure-3.
8 | Schedule - B Cl. 1.1 | Bypasses for traffic. | It is well known that execution of tunnel along with approach road itself is big challenge therefore the scope of bypasses for traffic shall be omitted from the COD. | As per RFP.
9 | Schedule - B Cl. 1.16 | Site Installation | Connectivity from the project corridor to area proposed for site installation shall be provided by Authority. Proposed area for site installation shall be free from all encumbrances. | Connectivity to site installations to be developed by concessionaire
10 | Appendix -D2 4.1.1.1 & 4.2.1 | Technical Specifications Fixed Operating Equipment | Clause 4.1.1.1 States "Oil-filled transformers are not permitted for subsurface usage during Construction. Transformers shall be air-cooled and of dry type." However Clause 4.2.1 states "The transformers to lower the voltage from 11kV to 690V or 400V shall be situated in the OMCs, in the ventilation caverns and special power supply niches. The transformers have to be oil-filled." Please clarify | It is correct that air cooled transformers have been recommended during construction phase on account of technical/safety reasons. During Operation and Maintenance phase Oil filled transformers have been recommended.
11 | Phase II: Detailed Project Report - Preliminary Tunnel Design 4.2.1 | Technical Specifications Fixed Operating Equipment | Variation in "%" for Voltage & frequency may be given. | The variation in permitted in the voltages and frequencies of the high and low voltage electric supplies shall be guided by provisions contained in Indian Electricity Rules 1956(Chapter V)/ IE Rules 2005, The IS/CPWD codes on the subject or the state of the art in consonance with the Employers Rep(The Indep Engr) at the time of instalation.
12 | Appendix -D2 | Technical Specifications Fixed Operating Equipment | Request you to provide "List of Approved Vendor for Electrical . Illumination & Ventilation system" if any. | No such list of approved vendors to be provided by MoRT&H.
13 | Appendix -D2 | Hydrants with fire-fighting water shall be installed on both portals and in the hydrant niches in the tunnel. | We presume that Water Supply at Each portal for Fire fighting and other purposes shall be provided by Client | Concessionaire has to arrange.
14 | Appendix -D2 | - | We presume that Liasioning for Power Supply / Radio Frequency etc. shall be in Client’s Scope. | Concessionaire has to arranged.
15 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | The Scheduled Two-Laning Date shall occur on the 2555th (two thousand five hundred and fifty fifth) day from the Appointed Date. | The scope of work includes construction of 14 Km mined tunnel;Shaft 1& 2 (Construction cum Ventilation Shafts) of 14m dia and depth 484m and 365 m respectively and shaft no 3 (Ventilation Shaft) of 6m dia and 208m depth.The work is to be executed at an elevation more than 3000m with net working period of about 7 months a year due to exteme weather conditions and closure of NH1 D from November to March. Therefore the construction period of 7 years provided in the tender documents seems to be highly optimistic and request you to provide rational & realistic construction period of 10 yrs. | Construction schedule has been developed after incorporating all contingencies. As Per RFP
16 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | In view of sr.no.1) above, request you to modify following Physical project Milestones, Financial Milestones shall be modified accordingly: | As per RFP
17 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-I to be modified from 365th day to 1095th day | As per RFP
18 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-II to be modified from 730th day to 1460th day | As per RFP
19 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-III to be modified from 1095th day to 2190th day | As per RFP
20 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-IV to be modified from 1460th day to 2555th day | As per RFP
21 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-V to be modified from 1825th day to 2920th day | As per RFP
22 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Project Milestone-VI to be modified from 2190th day to 3285th day | As per RFP
23 | Schedule G Scheduled Completion Date RFP Vol. III (Schedules) | Project Milestones | Scheduled Project Completion Date to be modified from 2555h day to 3650th day | As per RFP
24 | Schedule G Scheduled Completion Date | Project Milestones | Construction of Access shaft-1 to be modified to excavation of Access shaft-1 | As per RFP
25 | Schedule G Scheduled Completion Date | Project Milestones | Construction of Access shaft-2 to be modified to excavation of Access shaft-2 | As per RFP
26 | General | Maps | Concessionaire need to carry Geological mapping along with the Geotechnical investigation to minimize the risk in cost estimation. Geological maps can be only obtained from Defence Research Development Organization (DRDO) office which Government officials may get the maps easily than any private body. We request you to kindly provide the same either through DRDO or BRO. | Geological maps may be available with Geological Survey of India(GSI) / DRDO/BRO. Any interested party can obtain the same from either of them.
27 | General | Environmental Clearance | Please provide the status of Environmental clearances for Project, Environment Impact Assessment (EIA) & Rehabilitation & resettlement plan. | Not required
28 | General | Utility Shifting | Please provide the status of utility shifting. | Utility shifting, if any, shall be done before appointed date.
29 | General | Forest land and clearance | Kindly clarify whether any part of the project highway or any project facilities comes under the Forest Department / Wild life sanctuary / Reserve Forest / Protected forest & status of the clearance for the same. | Not required
30 | General | Details of Land acquisition. | As per Schedule “A” Existing ROW is varying in between 10 to 15M. Schedule “B” is silent on proposed ROW. Requesting you kindly provide the Details of Land acquisition. | Land will be acquired before Appointed date. (Ref Annexure-3 for LA).
31 | General | Drawing | We presume that the proposed drawings are for guideline only. Concessionaire may design & prepare the drawings based on project requirement. Please clarify. | YES. Subject to approval by IE
32 | General | Material obtained from Tunnel Excavation. | We presume that materials obtained from tunnel excavation can be used in construction activities for free of cost. Please clarify. | May be used with prior permission of IE/ Authority.
33 | General | Report/Documents/details Requires | for Z morth these docuemnts were provided but this time this all are mising:- 1.Executive Summary, 2. Tunnel Design Report. 3. Portal Design report 4. Geotechnical Tunnel Design Report, 5.Primary lining Analysis Report 6. Analytical analysis result. Result structural analysis 7. Cost estimation & BOQ 8. Preliminary Ventilation Design Report 9. Guidiline inner lining concret, 10. Ventilation Equipment | Already provided as Amendments on tender portal. Please download all the relevant Amendments.
34 | General | Bid Submission related | If applicant has already paid the fees in Previous RFQ stage announced by BRO, will he be still required to pay the fees again ? | As per RFP documents. For avoidance of doubt, it is clarfied that RFQ and RFP are being invited at single stage and the cost of RFQ and RFP of Rs. 27,30,000 (9,10,000 + 18,20,000)/- (Rupees twenty seven lakh thirty thousand only) is being charged at the same time.
35 | General | Bid Submission related | Kindly change the timing of Bid and RFQ documents submission to 3 :00 PM instead on 11:00 AM on due date . | No change. As per RFP documents.
36 | General | Bid Submission related | For e-tendering, it has been mentioned that payment has to be made via online portal of MORTH only, although at e-portal, the option mentioned for payment is Demand Draft. (Please clarify whether we have to deposit DD or online payment via Net banking or credit card). | By DD only.
37 | General | Bid Submission related | Submission of physical copy should be allowed till next day of Online submission as it will ease the process for both the parties involved. | Both at same day.
38 | General | Due date | Kindly extend the Due date of project by 30 days | No change. As per RFP documents.
39 | Instruction to Bidders: Volume I Clause 1.2.3 | The Feasibility Report prepared by the Authority/ consultants of the Authority (the “Feasibility Report”) is also enclosed." whereas Clause 2.1.3 states that "The Feasibility Report of the Project is being provided only as a preliminary reference document by way of assistance to the Bidders .." | Request Authority to kindly provide all the volumes of the Feasibility report as mentioned. It is understood that Feasibility report doesnot form part of the RFP documents and "Technical Specifications" as given in Schedule D only are binding part of the RFP. | All relevant volumes except the BOQ have already been provided.(Being a DBFOT project BOQ is NOT to be provided) It is confirmed that the feasibility report does not form part of the RFP. The technical specification as per schedule only are binding.
40 | RFP- Volume I, Section 1.1 Estimated Project Cost | The Estimated Total Project Cost (TPC) is provided as Rs. 9090 crore in the RFQ cum RFP reinvited in July 2015. The same TPC was provided in the RFQ dated May 2013 and RFP issued in Nov 2014 | No revision in the Total Project Cost has been made despite lapse of twenty four months. We request the Authority to revise the same considering escalation for this period. Further, it is observed that the TPC derived by the Concessionaire, is genenrally more than the TPC considered by the Authority and the lenders raise queries with regards to such difference in TPC during the financial closure. Hence, it is suggested that the (a) capital cost of the Project, as set forth in the Financial Package or (b) the actual capital cost of the Project upon completion should only be considered. | As per RFP
41 | RFP- Volume I, Section 1.2 .4 | Bid Security | As the TPC is very high, Bid Security of 1% of TPC is a very high amount. Request Authority to reduce the same. | As per RFP
42 | RFP-Volume I, Section 2.20 Bid Security | “The Bidder shall furnish as part of its Bid, a Bid Security referred to in Clauses 2.1.7 and 2.1.8 hereinabove in the form of a bank guarantee issued by a nationalised bank, or a Scheduled Bank in India … … … “ | With reference to the submission of Bank Guarantee as Bid Security, kindly clarify the followings: i) In case of a consortium, whether the Bid Security is to be submitted by the Lead Member only or can be submitted by all the members of the Consortium for an aggregate amount of Rs.90.90 Crores? ii) In case the Bank Guarantee is allowed to be submitted by all the members of the Consortium for an aggregate amount of Rs.90.90 Crores, whether the same is to be submitted in their proportion in the Consortium or can be submitted for any amount aggregating to Rs. 90.90 Crores? iii) Whether the Bank Guarantee can be submitted from more than one bank by any member of the consortium/Bidder? If yes, is there any limit on the number of Bank Guarantees aggregating to Rs.90.90 Crores? | As per RFP
43 | RFP-Volume I, Appendix – I | “31 a) The EPC contractor/s who would be executing EPC works of the Project are …………, …………, …………. and it is confirmed that these contractors meet the minimum criterion set out in our RFQ for this Project. b) It is irrevocably agreed that the value of any contract for the EPC works awarded shall not be less than 20% of the TPC or 500 crore, whichever is less. c) It is also agreed that any change in the name (s) of the EPC contractor(s) would be with prior consent of Authority. We agree that Authority shall grant such permission only and only if the substitute proposed is of the required technical capability as applicable.” | As per clause 2.25 of the RFQ document and clause 2.1.18 of the Vol. I of the RFP document, The Bidder is required to provide an undertaking to Authority that EPC works of the project would be executed only by such EPC Contractors who have completed at least a single package of more than 20% of the TPC or Rs.500 Cr, whichever is less. Please clarify that if the undertaking for the EPC works is being provided as per the above mentioned clauses, whether the paragraph 31 of the Appendix-I can be deleted. | As per RFP
44 | DCA, Article 9 | Performance Security | As the TPC is very high, Performance Security of 5% of TPC is a very high amount. Request Authority to reduce the same. | As per RFP.
45 | DCA, Clause 4.2 | In the event that (i) the Authority does not procure fulfilment of any or all of the Conditions Precedent set forth in Clause 4.1.2 within the period specified in respect thereof, and (ii) the delay has not occurred as a result of breach of this Agreement by the Concessionaire or due to Force Majeure, the Authority shall pay to the Concessionaire Damages in an amount calculated at the rate of 0.1% (zero point one per cent) of the Performance Security for each day’s delay until the fulfilment of such Conditions Precedent, subject to a maximum of 20% (twenty percent) of the Performance Security. | Damage for delay in fulfilment of Condition Precedent by Authority i.e. 0.1% of performance security for each day of delay is not sufficient considering that any delay in commencement of Construction activities have direct bearing on IDC as well as escalation of material which may be huge in comparison to the damage payable by Authority. | As per RFP.
46 | DCA, Clause 5.1.4 Obligations of the Concessionaire | The Concessionaire shall, at its own cost and expense, in addition to and not in derogation of its obligations set out in this Agreement: (e) make reasonable efforts to facilitate the acquisition of land required for the purposes of the Agreement; | Request Authority to provide current land acquisition status for the Project Highway. | Land is available and status is also enclosed. (Ref Annexure-3).
47 | DCA, Clause 11.3.2 | The Authority may, by notice require the Concessionaire to connect any adjoining road to the Project Highway. Upon receipt of a notice hereunder, the connecting portion thereof falling within the Site shall be constructed by the Concessionaire at the Authority’s cost in accordance with Article 16, and the maintenance thereof shall be undertaken by the Concessionaire in accordance with the provisions of Clause 17.1.3. | We presume that the cost of maintenance of any such connecting road shall be reimbursed by the Authority in accodrance with Article 16. Please confirm. | Concessionaire is to maintain the connecting roads which are to be constructed by them for approach to their sites.
48 | DCA, Clause 10.3.4 | "The Authority shall make best efforts to procure and grant, no later than 90 (ninety) days from the Appointed Date, the Right of Way to the Concessionaire in respect of all land included in the Appendix, and in the event of delay for any reason other than Force Majeure or breach of this Agreement by the Concessionaire, it shall pay to the Concessionaire Damages in a sum calculated at the rate of Rs. 50 (Rupees fifty) per day for every 1,000 (one thousand) square metres or part thereof, commencing from the 91st (ninety first) day of the Appointed Date and until such Right of Way is procured." | Damages for force majeure events should also be compensated separately. Compensations mentioned is not sufficient enough to meet the losses concessionaire will have to bear, due to increase in IDC and escalation of prices of material we request you to compensate suitably and also provide time extension, apart from the compensation as mentioned in the Concession Agreement. | As per RFP
49 | DCA, Cl. 10.3.2, Procurement of the Site | Without prejudice to the provisions of Clause 10.3.1, the Parties hereto agree that on or prior to the Appointed Date, the Authority shall have granted vacant access and Right of Way such that the Appendix shall not include more than 20% (twenty per cent) of the total area of the Site required and necessary for the Two-Lane Project Highway, and in the event Financial Close is delayed solely on account of delay in grant of such vacant access and Right of Way, the Authority shall be liable to payment of Damages under and in accordance with the provisions of Clause 4.2 | The Authority shall have granted vacant access and Right of Way such that Portals and Shaft locations facility set up can be taken up without impediments. Please Clarify | Depends upon the site conditions and could be used.
50 | DCA, Cl. 10.4, Site to be free from Encumbrances | Subject to the provisions of Clause 10.3, the Site shall be made available by the Authority to the Concessionaire pursuant hereto free from all Encumbrances and occupations and without the Concessionaire being required to make any payment to the Authority on account of any costs, compensation, expenses and charges for the acquisition and use of such Site for the duration of the Concession Period, except insofar as otherwise expressly provided in this Agreement. For the avoidance of doubt, it is agreed that existing rights of way, easements, privileges, liberties and appurtenances to the Licensed Premises shall not be deemed to be Encumbrances. It is further agreed that the Concessionaire accepts and undertakes to bear any and all risks arising out of the inadequacy or physical condition of the Site. | Any and all risks arising out of the inadequacy or Physical condition of the Site shall be compensated by the Authority to the Concessionaire | As per RFP
51 | DCA, Clause 11.1 Existing utilities and roads | "Notwithstanding anything to the contrary ……. Authority shall, upon written request from the Concessionaire, initiate and undertake at the Concessionaire’s cost, legal proceedings for acquisition of any right of way necessary for such diversion." | Concessionaire shall assist the agency for construction of temporary or permanent diversion by deploying their resources. Since such diversion shall be needed for the shifting of utilities, which is the responsibility of Authority only, the cost of diversion/land acquisition including legal proceedings should be borne by Authority. Accordingly, The Cost of providing suitable Temporary or Permanent diversions for Existing Utilities and Roads, acquisition of any right of way necessary for such diversion shall be compensated. | As per RFP.
52 | DCA, Clause 11.4 | The Authority shall assist the Concessionaire in obtaining the Applicable Permits for felling of trees to be identified by the Authority_________________on the construction, operation or maintenance of the Project Highway. The cost of such felling shall be borne by the Authority, and in the event of any ___________ felling of trees. For the avoidance of doubt, the Parties hereto agree that the felled trees shall be deemed to be owned by the Authority and shall be disposed in such manner and subject to such conditions as the Authority may in its sole discretion deem appropriate. | Authority is in better position to obtain the necessary approval being a Govt. Organization. However Concessionaire can assist the Authority in all possible manners for the same. We presume that the cost of felling of trees shall include disposal of the same and handing over of the trees to forest department/ Authority and cost of the same shall be borne by Authority. Please Clarify | Cost of cutting of trees is submitted to Forest deptt. For needful action at their end.
53 | DCA, Clause 12.1 (d), | Obligations prior to commencement of Construction | Request to indicate the probable / possible locations for Quarry. Please also specify any locations where quarrying is restricted. | Concessionaire to carry out survey on their own.
54 | DCA, Clasue 12.2 Construction of Project Highway. | During the Construction Period, the Concessionaire shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 7 (seven) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Concessionaire may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary for the efficient progress of Construction Works and conforms to Good Industry Practice; provided further that such interruption and diversion shall be undertaken by the Concessionaire only with the prior written approval of the Independent Engineer for which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Concessionaire shall at all times be responsible for ensuring safe operation of the Project Highway | Since, the site is a green field alignment and existing highway is presently being maintained by BRO, please confirm that the maintenance of the existing NH-1 from existing chainage of approximately km 94.000 on NH-1 and meeting the NH-1 at existing chainage of approximately km 119.000 shall not be obligation of Concessionaire during the Construction Period | As per RFP.
55 | DCA, Clause 12.3 (e) | No review and/or observation of the Independent Engineer and /or its failure to review and/or convey its observations on any Drawings shall relieve the Concessionaire of its obligations and liabilities under this Agreement in any manner nor shall the Independent Engineer or the Authority be liable for the same in any manner; | In case of any modification suggested by Independent Engineer on the design and drawing submitted by Concessionaire resulting into design related defects/ damage the liability and obligation of the concessionaire should be relaxed, and if any defects observed due to the above suggestion; the concessionaire shall not be made solely responsible. | As per RFP.
56 | DCA, Article 24 | Financial Close | Considering the high TPC of the Project and the current situation of financial sector, it is envisaged that achieving financial closure may require additional time and it will be difficult to achieve financial close within 180 days of signing of the Concession Agreement. Hence, it is requested to provide time of at least 365 days for achievement of Financial Closure. | As per RFP
57 | DCA Clause 28.1.1. | In case the Concessionaire achieves COD prior to the Scheduled Two Laning Date then shall it shall be entitled to receive from the Authority a bonus for early completion of the Project (the “Bonus”). Such Bonus shall be paid alongwith the first Annuity payment on the first Annuity Payment Date. | Can we get bonus paid on achievement of COD instead of 6 months after Scheduled Two laning date | As per RFP
58 | DCA, Clause 28.1.2 Bonus on account of early completion | The Bonus for such early completion shall be the product of Average Daily Annuity and the number of days by which the COD preceded the Scheduled Two Laning Date or six months, whichever is lesser. | Request Authority that the bonus for early completion should be calculated on the basis of actual completion of the project and shall not be capped to a maximum of 6 months. | As per RFP
59 | DCA, Cl. 28.2.4, Reduction in Annuity on account of delayed Project Completion | The number of days of delays caused due to the reasons provided in the Clause 28.2.3 shall only be excluded for computation of Reduction only in case such delays occurred after the successful completion of first Project Milestone, as certified by the Independent Engineer, in accordance with the Project Completion Schedule at Schedule-G | The number of days of delays caused due to the reasons provided in the Clause 28.2.3 shall be excluded for computation of Reduction for the delays occurred from the Appointed Date. | As per RFP
60 | DCA, Clause 34.2 | Non-Political Event | The landslides are being considered as a Non-Political Event. Please confirm whether avalanches shall also be considered as a Non-Political Event. | Agreed, But as per the site conditions to be approved by IE/Authority.
61 | DCA, Clause 37.3.1 | Upon Termination on account of a Concessionaire Default during the Operation Period, the Authority shall pay to the Concessionaire, by way of Termination Payment, an amount equal to 90% of the debt due less Insurance Cover; provided that if any insurance claims forming part of the Insurance Cover are not admitted and paid, then 80% (eighty per cent) of such unpaid claims shall be included in the computation of Debt Due. For the avoidance of doubt, the Concessionaire hereby acknowledges that no Termination Payment shall be due or payable on account of a Concessionaire Default occurring prior to COD. | Request Authority to include Termination payment on account of Concessionaire Event of Default during the Construction Period as part or substantial part of the Project Assets shall be created based on the funding provided by the Lenders. This is more critical considering the longer Construction Period of 7 years. Such provisions shall provide more comfort to the lenders and would ease the achivement of financial closure. | As per RFP
62 | DCA, Clause 47.3 State Support Agreement | The Concessionaire acknowledges that it has received from the Authority a certified true copy of the agreement executed between MORTH and the State Government for providing the support and services specified therein (the “State Support Agreement”), and the Parties hereto agree to make their best endeavours to procure the support of the State Government. | Kindly provide a copy of the State Support Agreement. | State support agreement is already in practice. Copy enclosed. (ref Annexure-4)
63 | DCA, Article 48 Definitions | “Project Highway” means the Site taking off from existing chainage of approximately km_94.000 on NH-1 (considering Srinagar at 0.000 km) and meeting the NH-1 at existing chainage of approximately km 119.000 and broadly comprises two lane approach road of approximately 10.820 km length, 60 m span Major Pmt Bridge and 700 m Snow Gallery), two lane Zozila tunnel (approximately 14.083 km long) Single tube bidirectional with parallel egress tunnel and all Project Assets, and its subsequent development and augmentation in accordance with this Agreement; | Article 48 definitions: Project Highway definition (pg 143 of DCA) Project Road ends at Km 119 while as per the Clause 1.1.2 of Annex-I of schedule B Project ends at Km 118. Please clarify the same. | Project road end to be taken as KM 119.
64 | Wildlife Clearance |  | What is the status of Wildlife Clearance for the Project? Please clarify and provide a copy if obtained | Not Required.
65 | Reserve Forest |  | What is the status of Forest/Reserved Forest Clearance for the Project? Please clarify and provide a copy if obtained | Not Required.
66 | Blasting Permission |  | Kindly confirm whether permission for blasting is obtained and available, please provide a copy if obtained | As per RFP, Concessioanre has to arrange blasting permission from the concerned authority.
67 | Sources of Power Supply |  | We understand that cost of the construction of complete Switch Yard at Portal location shall be borne by the Authority. Concessonaire shall only be responsible for connecting to the 11 KV supply from the outgoing breaker of the Switch Yard. We also understand that Switch Yard shall be near the Portal location. Please Clarify. | Nearest power station is in upper Sindh Project Phase-I at Sumbal at km 57.0 on Srinager Sonmarg Gumri road. Cost for transmission link shall be borne by concessioanre.
68 | Sources of Power Supply |  | We presume that land for electric sub station and connections shall be provided by the Authority and the Authority shall bear the cost for the same. | Concessioanre has to arrange at it own cost.
69 | Details of Consultants |  | Kindly provide details of Legal, Technical and Financial Consultant | No need to provide these details during bidding.
70 | Extension in Construction Period |  | In case of delay caused due to the occurrence of an unexpected or unavoidable geological/natural event/occurance of water bodies, time extension shall be provided. Please clarify | Geological risk is with concessioanaire.
71 | Schedule B, 1.14 Construction Concept, Clause 27, Clause 28 of DCA |  | In the event that work is not possible for the minimum duration specified in Schedule B, damages for delay, either during Construction period or O&M period, shall not be imposed on the Concessionaire, and such delay will not be considered in reduction of annuity and milestones shall be revised accordingly. Instead if the Concessionaire suffers any losses due to the above, the Concessionaire shall be suitably compensated. | As per RFP.
72 | Schedule A, Annex -1 Cl. 1.1 Site of Project Highway . | • Bypasses for Traffic - Following byepasses will be required to be constructed in the above project site, as per two lane highway specifications for smooth unhindered flow of traffic :- o Bypass For Amarnath Yatra - 4.9km. This byepass is required for use during construction period only. o Bypass for eastern portal:- 1.1 KM. This bye pass will be used during construction and operation periods both | Please provide Proposed ROW for Bypasses and also provide the details of structures (No of structures,length, width, span arrangement, foundation type, superstructure type etc) and protection works to be provided along the bypasses Also Request Authority to provide Plan and Profile for both bypasses. | Provided and enclosed. (ref-Annexure-3)
73 | Schedule A, Annex -1 Cl. 1.1 Site of Project Highway | • Bypasses for Traffic - Following byepasses will be required to be constructed in the above project site, as per two lane highway specifications for smooth unhindered flow of traffic :- o Bypass For Amarnath Yatra - 4.9km. This byepass is required for use during construction period only. | We presume that no hindrance shall be posed by pilgrims after the construction of the Amarnath bypass as they shall use the 4.9 km long bypass. In case of any such hindrance which affects the milestone completion, the Concessionaire shall not be held responsible for such delays. The Concessionaire shall be suitable compensated in the event of such delays. | The same will be as per RFP and further, if any requirement of local Govt, the same has to be followed by the concessionaire.
74 | Schedule A Annexure - I, Cl. 1.1 The Site |  | Request Authority to clarify the Length of Main Tunnel 1) as per schedule A - 14.150 Km 2) as per ITB Cl 1.1.1 - 14.083 Km | The total length of the tunnel including the cut and cover portions is 14.150 KM
75 | Schedule A Annexure - I, Cl. 1.1 The Site |  | Request Authority to clarify the Length of Approach Roads 1) As per Schedule A - 5.025 Kms +0.803 Kms = 5.828 Kms 2) As per ITB Cl 1.1.1 - 10.82 Kms | Details are Annexure-3.
76 | Schedule A, Cl. 1.2 Project Area |  | Request Authority to clarify the status of land acquisition and cost responsibility for following 1) Amarnath Bypass 2) Base camp land at two portal locations and at two construction shaft locations 3) Dump yards | Details are Annexure-3.
77 | Schedule A, Annex - I Cl. 1.7 Land |  | Request the Authority to provide the details of available ROW. (Only information given) 1) Approach Roads and at Junctions 2) For Amarnath Bypasss and Eastern Portal Bypass 3) Access Roads | Details are Annexure-3.
78 | Schedule A, Detailed Geological Report. |  | Geological Section & Plan are not available with the documents. Permeability data is not available with the documents. Request to provide the same. Request to provide available Borelog details for the project | All the data have been provided. Detail report could not be uploaded due to very huge data, same could be personally collected from MoRT&H.
79 | Schedule A, 1.5 Geology | Geological L-section Drawing and Geological Cross section Drawings | The drawing provided for Geological L-section is not indicating any Chainage. The geological cross-sections given do not indicate the chainage. Request you to provide the Chainages for these sections. Request you to provide the drawing with Chainage in AutoCAD Format. | To the scale Geological L Section drawing has now been provided in the CAD format. The chainage can be easily marked on this drawing by the concessionaire.
80 | Schedule A, 1.5 Geology | Rock Mass Classification | Request you to provide the Rock Classification percentages for Main Tunnel & Egress Tunnel | Complete details of the anticipated Rock Classifications percentages have been provided in the Vol 4 of the DPR Geotechnical Design Report(Chapter 7). Same can also be found included in the DPR Vol 1 Executive Summary (Chapter 10). The percentages for the Egress tunnel are anticipated to be same. However the concessionaire must keep in mind that these details are being provided by way of assistance only, and any variations from the stated percentages during acual execution has no bearing on the concession agreement.
81 | Schedule B, Annex - I Cl. 1.1.1 Ventilation Building |  | Is it mandatory to construct the Ventilation building above cut and cover tunnel? Please confirm | The concessionaire may develop own ventilation building design and may construct accordingly after approval by the IE. (From technical point of view the ventilation building can be designed separated from the cut and cover tunnel. In The DPR the ventilation building has been designed above the C&C tunnel to minimize construction effort. Of course design alternatives are possible and can be adopted on approval by the IE. In schedule B location of Ventilation buildings has not been fixed, therefore the flexibility rests with the concessionaire.)
82 | Schedule B, Annex - I Cl. 1.1.1 Service and Control Buildings |  | We presume that the Authority will provide sufficient land for the construction of Service and Control Buildings | Included in the LA plan.
83 | Schedule B, Annex - I Cl. 1.1.1 Western Tunnel Portal Approach Road to Portal |  | Request Authority to clarify the type of Bridge 1) As per the ITB - 60 m span pmt Major Bridge 2) As per Clause no. 1.1.2 of Schedule B 60m Minor Bridge 3) As per Clause no. 5.6 of schedule B 60m Major Bridge | Details are Annexure-3.
84 | Schedule B, Annex - I Cl. 1.1.1 Western Tunnel Portal Approach Road to Portal |  | Only one culvert is proposed as per clause 5.7 of schedule B. Please provide the schedule of Culverts for Approach roads (Western and Eastern), Amarnath Bypass (4.9 Kms) and Eastern Portal Bypass (1.1 km). | Details are Annexure-3.
85 | Schedule B, Annex - I Cl. 1.1.1 Eastern Tunnel Portal Final Portal Elevation |  | Request Authority to clarify the Portal Elevation 1) As per the Schedule B - 3310 m 2) As per the DPR genenral longitudinal Layout - 3300 m Please confirm the final elevation | The Eastern Portal elevation is 3310m.
86 | Schedule B, Annex - I Cl. 1.4.2 Ventilation Cavern |  | Request authority to provide the Cross section details for Ventilation Cavern and sectional elevation of proposed buidings for more clarity and also confirm that total thre no. of ventilation cavern are to be provided as per clause 1.4.1 of Schedule B. At given locations distance between the axes of main and egress tunnel length is increaseas as per the reference drawing and if length of cavern increases from 30m depending on site condition, then additional length shall be considered as change of scope of work. Please Confirm | The Spatial(dimensional) requirements for the ventilation caverns have been given in the schedule B clause 1.4.2. Typical layout of the caverns have also been provided in the drawings mentioned therein. Concessionaire are requested to develop their own cross sectional drawings based on the data provided. Additional design inputs may be found in the relevant DPR vols. Similarly the sectional elevation drawings of the ventilation buildings may please be developed by the concessionaire, based on the floor area requirements that have been specified. It is hereby confirmed that three ventilation caverns will be required. (Increase in length as pointed out in the query is part of geotechnical risk and is to be assessed and borne by the concessionaire. )
87 | Schedule B, Annex - I Cl. 1.4.3 Ventilation Shaft |  | Request authority to confirm the portal elevation of Main and Egress tunnel for both east and west side, it is required due to variation of same shall affect the depth of shafts. Additional depths of shafts shall be considered as a change of scope of work. Please Confirm | Portal elevations of West and East sides are hereby confirmed as 2900 m and 3310 m respectively.
88 | Schedule B, Annex - I Cl. 1.4.4 Access Roads to Ventilation Shafts |  | Request Authority to provide proposed road length of and Typical cross section for Access road and provide the plan and profile drawings, and road protection scheme for construction of the same | To be developed by the concessionare as per RFP. Details are at Annexure-3.
89 | Schedule B, Annex - I Cl. 1.4.5 Ventilation Shaft Terminal buildings |  | Request authority to provide the land area available near shaft locations. Additinal land if required for Terminal buildings, then Authority shall provide with no cost to the Concessionaire please confirm | Adequate land areas are available near the shaft locations and for Terminal buildings.
90 | Schedule B, Annex - I Cl. 1.4.6 Separate Parallel Egress Tunnel and Cross passages |  | Request Authority to provide the Final Portal elevation of egress tunnel at Western Portal side and Eastern Portal side Please confim that if distance between axes of the Main and Egress tunnel if increases from 25m at detail design stage looking to the actual ground conditions then additional cost implications for construction of passenger cross passages/drivable cross passages/ lay by cabinets shall be treated as per the change of scope and considered as per the CA provisions. | Final Portal elevation of the Egress Tunnel on the West side is 2900m and that on the East side is 3310 m.(+ 5m) It is taken as part of the geotechnical risk and borne by the concessionaire.
91 | Schedule B, Annex-I, Cl 1.1. The SIte | Approach to Western Portal and Approach to Eastern Portal | Request Authority to provide the General Layout drawing for Approach Roads indicating the proposed location of bridge and snow galleries and include the scope in Schedule B. Please also provide the contours of the area through which approach roads to Western Portal and Eastern Portal are proposed | Concessionare has to do own survey for contours. General layout drawings are enclosed. (ref Annexure-3).
92 | Schedule B, Annex - I Cl. 1.9 Final Interior Finish |  | Request authority to provide the details final interior finish type for Egress Tunnel | As per concessionaire's detailed design to be approved by IE
93 | Schedule B, Annex - I Cl. 1.15 Site Installation | Four site installations are visualised . The site installation for the western portal is to be located in the area of Baltal. The site installation for the eastern portal is to be located in the area of Minamarg. Two additional installations will be located in the vicinity of the openings of the construction access shafts no 1 and no 2 near Km 106 and 110 of the NH. andGagangir close to the National Highway approx. 1.0 km from the western port. After making the assessment of requirement, the concessionaire has to ascertain the availability of the land with the local BRO authorities. | Are the four nos. of site installations the minimum to be provided or is it the number which are anticipated. Please clarify | It is the anticipated number
94 | Schedule B, Annex - I Cl. 1.16 Muck Dump Disposal | Muck dump disposal sites are available in the project area. Upto eight pockets have been proposed These disposal area are located between approx. km stone 90 and Km stone 120 on existing NH 1. | Please provide drawing showing the locations and tentative area and quantity of muck that can be disposed in each disposal area. In case the designated areas are not sufficient, the additional site locations in the vicinity of Project Site shall be made available by the Authority. | The drawings showing the tentative muck disposal areas are provided Ref Annexure-2. It is assessed that these areas have adequate capacity to accommodate the muck from the tunnels. Concessionaires are advised to verify the same on ground
95 | Schedule B, Annex - I Cl. 1.16 Muck Dump Disposal |  | It has been mentioned that permission shall be obtained from the Local authorities (Civil Administration/Wild life / Forest). We presume that all the permissions will be obtained by Authority. | Wildlife/Forest permission- Not required.
96 | Schedule B, Annex - I Cl. 1.16 Muck Dump Disposal |  | Authority also has to provide the access route for the Muck disposal Yard. | NOT true. Access route to muck disposal areas shall be concessionaire's responsibility.
97 | Schedule B, Annex - I Cl. 3 Alignment plan longitudinal section |  | Request authority to provide 1) Typical cross section for Two lane approach road (For Cut and Fill sections) 2) Plan and Profile for aproach roads and Junctions 3) Protection scheme for Tunnel approach roads 4) Vertical profile for Egress tunnel and 5) Plan showing dimensions (distance between axes of main and Egress tunnel) Main tunnel Portal elevations are not in line with the Clause 1.1.1 and Clause 1.1.2 of Annexure I of Schedule B in referred drawing. Please clarify | (1) (2) (3)-Details are enclosed at Annexure-3. By pass with 2-lane road and approach road with 2-lane with Paved shoulder. 4) Typical vertical profile of the Egress Tunnel has been given in the drawings provided. Ref drawing 8482B_II-ZOT_Gen-02-12-00(Layout plan View) provided in appendix B-1. Schedule B 5) Plan showing the dimensions and distances have been provided. Ref 'to the scale' drawing 8482B_II-ZOT_GEOM-05-12-00(TCS Egress) provided in appendix B-1. Schedule B West portal elevation at 2900m and East portal elevation at 3310 have been correctly mentioned in the clauses of schedule B and the drawings.
98 | Schedule B, Annex - I Cl. 5.3 | Proposed ROW for Approaches | Please provide: 1) Proposed ROW of Approach Roads 2) Proposed ROW at Junctions | Required ROW are available. (Ref-Annexure-3).
99 | Schedule - B | Proposed ROW for Approaches | Width of ROW is varying due to site condition. The Details of Proposed ROW to be ascertained from local BRO. | Required ROW are available. (Ref-Annexure-3).
100 | Schedule - B | Proposed ROW for Approaches | Authority shall be single point contract for Concessionaire. Authority has to coordinate with BRO & provide ROW details immediately to calculate the cost before bid. Please clarify. | Authority will facilitatae.
101 | Schedule - B, Cl. 1.16 | Site Installation | Connectivity from the project corridor to area proposed for site installation shall be provided by Authority. | Connectivity shall be concessionaire's responsibility
102 | Schedule - B, Cl. 1.16 | Site Installation | Proposed area for site installation shall be free from all encumbrances. | Project site area is available.
103 | Schedule B, Annex - I Cl. 5.4 At Grade Junctions |  | Request authority to provide proposed ROW details at Junctions. | Required ROW are available. (Ref-Annexure-3).
104 | Schedule B, Annex - I Cl. 5.6 Major Bridges | One bridge of 60 m will be required in this reach of the Project Highway, on the Eastern Portal approach. | It appears that the bridge is required on the Western Portal approach please confirm Request authority to provide the GAD of proposed bridge. | As per RFP. If required concessionare may provide.
105 | Schedule B, Annex - I Cl. 5.7 Culverts | One multi cell box culvert of 18 m span is visualised in this reach of the Project Highway | As the span of this structure is more than 6 m, can it be considered as a culvert? Request the Authority to provide the location and GAD of this structure. | No as per IRC codes culvert is upto 6m.
106 | Schedule B, Annex - I Cl. 5.11 Snow Galleries | Snow galleries are required on the western approach road as per detailed requirements to be spelt out by SASE. | Request the Authority to provide the locations where these galleries are to be provided, drawings and specifications, detailed requirements specified by SASE for the same. Also Clarify the length of Snow galleries as it is not mentioned in Schedule B, but same is mentioned as 700 m per ITB Cl. 1.1. | Details are Annexed. (Ref Annexure-3)
107 | Schedule B, Annex - I Cl. 5.12 Avalanche Protection Measures | Avalanche protection measures will be required in the project area as per detailed requirements spelt out by SASE. | Request the Authority to provide the locations and scope where these protection measures are to be provided. Request the Authority to provide typical drawings and specifications, requirements as specified by SASE for the same. | Details are Annexed. (Ref Annexure-3)
108 | Schedule B, Annex - I Cl. 5.11 Snow Galleries, Cl. 5.12 Avalanche Protection Measures |  | Request the Authority to provide the Specifications formulated by SASE. | Details are Annexed. (Ref Annexure-3)
109 | Schedule B, Annex - I Cl. 5.10 Entry and Exit ramps |  | As per Cl. 5.10, no entry and exit ramps are required. However, as per given drawings of Hydraulic Systems, Acceleration lanes (slip roads) are shown connecting to service buildings. Please clarify the same. Request authority to provide details (Length, P&P, Typical cross section and road protection scheme) of slip roads /ramp roads connecting to proposed Tunnel service building | No Entry Exit Ramps have been provisioned for the main traffic. Deceleration lanes have been provided for maintenance traffic only.
110 | Schedule - B, Cl. 1.1 | Bypasses for traffic. | It is well known that execution of tunnel along with approach road itself is big challenge therefore the scope of bypasses for traffic shall be omitted from the COD. | As per RFP.
111 | Schedule B, Annex - I Cl. 7 Note to schedule B "the minimum functionality to be achieved for Zoji La Tunnel, shall be as per DPR included in the tender document" |  | Request Authority to delete "the minimum functionality to be achieved for Zoji La Tunnel, shall be as per DPR included in the tender document" because it is already mentioned that detailed design must be done according to latest international standards and practices for highway tunnel. | Both essentially mean the same. Therefore RFP be adhered to.
112 | Schedule B clause 1.4.3 of schedule B |  | For Shaft 3 : For Shaft 3 : Excavation dia 6m needs to increased due to following reason: The diameter proposed for Shaft 3 is insufficient to allow correct ventilation. Shaft 3 has to ventilate sections VS6 and VS7 and according to Table 8 in document 8482B_II_ZOT_rep-08-12-00, fans in these sections have a flow of 150 and 132 m3/s, respectively. As they work in Normal Situation, both may do it simultaneously, so the total flow to extract through this shaft would be 150m3/s + 132m3/s = 282m3/s. If we consider the 10 m2 section indicated in the DPR, the speed in the shaft would be 282m3/s/10m2= 28,2 m/s. This value is unacceptable considering that the length of the shaft is 208m and there will be a very high pressure drop. Increasing the fan power as well as the number of fans could solve the problem, but an undersized section would require such ventilation systems that the power consumption during normal operation of the tunnel would be greatly penalized and could become unviable. It is reasonable to size the civil works to make the cost of the facilities is not disproportionate. Request Authority to kindly consider increasing the diameter of Shaft 3 or else provide necessary explanation how 6m dia proposed for Shaft 3 is justifiable. | The reasons for limiting the ventilation diameter of the Shaft No 3 (Ventilation Shaft) is as follows:- - The ventilation shaft has been recommended to be constructed by raise boring, in order to achieve speedier construction and thus its diameter is limited to the largest dia of raise borer generally available in the market. This way the construction cost has also been kept low. A larger dia as suggested is possible, however it will entail change in the construction methodology, which will have to be top down and construction cost will also go up. Keeping in mind the overall construction schedule of the tunnel this methodology has been suggested in the design. Higher speed in the shaft will be acceptable because it is not a traffic tube and no damage to the structures is visualised. There are other examples of traffic tunnels with similar configuration. Example of Tunel La Linea under construction in Columbia is quite similar to Zoji La tunnel and has a ventilation shaft only slightly larger to the one proposed for Zoji La tunnel and has a ventilation shaft only slightly large the civil works to make the cost of the facilities is not disproportionate.
113 | Schedule B clause 6 of schedule B |  | Request Authority to kindly clarify whether the Design speed given is only for the road passing from Tunnel ? or also for approach road. Please confim. Request Authority to provide the alignment of approach road with Design speed of 80 km/hr for Eastern and Western Portal Approach road It is understood that the Design speed shall not applicable for access and slip roads (service building connecting road). Kindly confirm. | The design speed shall be applicable to both the tunnel and the approach road Details are enclosed. (Ref-Annexure-3) It is confirmed that design speed is not applicable to the slip roads.
114 | Schedule B clause 5.11 & 5.12 |  | Please provide the following details : Avalanche Mapping: A number of highways and lateral road axes in J&K, for identification and registration of snow avalanche paths, snow drift deposition and ice formation sites; frequency and severity of avalanche activity; and the extent of highway affected. Avalanche Atlas: Published atlases comprising terrain data, frequency of occurrence of avalanches, magnitude of damage, proposed control measures etc. Automatic Weather Stations: The data of all the stations are received at RDC SASE, Chandigarh by a state of the art digital Earth Receiving Station. We would need to know if any Artificial Triggering of Avalanche Methods are going to be implemented or allowed in the avalanche area. Request Authority to please provide the details | The concessionaire is advised to conduct own studies or approach SASE to acquire the data. The responsibility lies with the concssionaire as per the ITB. (A report of SASE is at Annexure-3).
115 | Schedule B clause 1.5 Separate Parallel Egress Tunnel and Cross Passages |  | Request Authority to kindly confirm whether the given length (14.200 kms) of Egress tunnel includes the length of Cut & Cover length ? Please confirm | It includes the length of the cut and cover tunnel portion.
116 | Schedule B, Annex - I, Clause 1.14 | Construction Concept "The construction of the main and the egress tunnel to include the cross passages to be carried out preferably by NATM method." | It is understood that since the project is on DBFOT basis, use of NATM method is not mandatory for construction and the Concessionaire may adopt other internationally accepted method as per Concessionaire’s choice with prior approval of BRO in consultation with the Independent Engineer. Kindly Confirm. | Yes. The concessionaire has the liberty to adopt any method as long as the output parameters are attained. NATM has been recommended as the preferred on account of the geological conditions encountered.(Ref para 1.14 of annex -I of schedule B)
117 | Schedule B, Annex - I, Clause 1.14 | Construction Concept "The construction of the main and the egress tunnel to include the cross passages to be carried out preferably by NATM method." | Since the project is on DBFOT basis, the Concessionaire shall be given the freedom to decide upon the Construction methodology for the Project. Accordingly, the final choice of number of working faces/attack points rests with the Concessionaire only. The construction of Zozilla Tunnel from both tunnel portals and from the intermediate construction access shafts No 1 and 2 mentioned is only for guideline and Concessionaire shall be allowed to decide upon as to how many and which shaft may be used as access shaft(s) and whether any shaft may be used for construction or not. | In view of the clause 1.14 of annex-I of schedule B of the RFP, this query is irrelevant. It is clearly mentioned that the concessionaire is at liberty to decide upon the construction methodology.
118 | Schedule C, Annex -1 g. Bus-bays and Bus Shelter | Bus-bay and Bus Shelter shall be provided at as per requirement and as decided by local BRO authorities during construction. | Request the Authority to provide the numbers and locations of the facilities as the cost may vary as the project is in hilly terrain | These have to be as per the concessionaire's detailed design.
119 | Schedule D, Annex -1 , Note In case of any revisions of the above mentioned codes the latest revisions shall be followed. |  | We presume that the revision in use 60 days prior to be Bid Due date shall be applicable. | As per RFP
120 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment, 4.1.1.1 & 4.2.1 | Clause 4.1.1.1 States "Oil-filled transformers are not permitted for subsurface usage during Construction. Transformers shall be air-cooled and of dry type." However Clause 4.2.1 states "The transformers to lower the voltage from 11kV to 690V or 400V shall be situated in the OMCs, in the ventilation caverns and special power supply niches. The transformers have to be oil-filled." Please clarify | It is correct that air cooled transformers have been recommended during construction phase on account of technical/safety reasons. During Operation and Maintenance phase Oil filled transformers have been recommended.
121 | Phase II: Detailed Project Report - Preliminary Tunnel Design | Technical Specifications Fixed Operating Equipment 4.2.1 | Variation in "%" for Voltage & frequency may be given. | The variation in permitted is the voltages and frequencies of the high and low voltage electric supplies shall be guided by provisions contained in Indian Electricity Rules 1956(Chapter V)/ IE Rules 2005, The IS/CPWD codes on the subject or the state of the art in consonance with the Employers Rep(The Indep Engr) at the time of instalation.
122 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.2.1 | Please confirm whether it is mandatory that Ventilation System Voltage should be of 690 V AC. | It is the voltage as per the indicated design of the ventilation system. The final system voltage to be as per concessionaire's detailed design, duly approved by IE.
123 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.2.3.2 | Please confirm whether Dynamic UPS of 450 KVA is also to be provided in addition to other Battery UPS. | Yes. Confirmed
124 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment | Request you to provide "List of Approved Vendor for Electrical . Illumination & Ventilation system" if any. | NA
125 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.5.1.1 | Request you to provide technical specifications of the PTZ Camera | As per concessionaire's detailed design to be approved by IE
126 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.5.1.1 | Kindly confirm whether fixed CCTV Camera can be mounted in center of the tunnel (i.e. under the roof) instead of mounting on the wall to get better overall viewing as it’s a bi-directional tunnel? | As per concessionaire's detailed design to be approved by IE
127 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.5.1.1 | We feel that distance between the two fixed camera of 200 m and 250 m in main tunnel and egress tunnel respectively is very high and it is suggested to intall CCTV cameras as per their actual coverage or viewing distance. Kindly confirm | As per concessionaire's detailed design to be approved by IE
128 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.5.1.4 | Specifications of the Interface equipment are contracdictory i.e. of IP Camera as well as of Analog Camera. We presume that IP CCTV Cameras are to be provided (both fixed and PTZ). Kindly confirm. | As per concessionaire's detailed design to be approved by IE
129 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.5.2.1. | Kindly inform and specification of Large Video Display to be used in Video Wall i.e. Rear Projection Type or LED Display Type, its screen size, bizel thickness, etc. We presume that 8 Large Screen Display shall be installed in 4x2 matrix, kindly confirm? Kindly also inform specification of Video Monitors, i.e. size, type, etc.? | As per concessionaire's detailed design to be approved by IE
130 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.7.1.4 | Kindly inform for coverage for which Cellular Band has to be provided inside the tunnel? | As per concessionaire's detailed design to be approved by IE
131 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.7.3.2 | Kindly inform whether time delay functionality is required for the individual loud speaker inside the tunnel or not? | As per concessionaire's detailed design to be approved by IE
132 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.9.1 | Authoriy to confirm whether Entrance Lighting can be designed as per the lastest CIE-88 Stanards or not? | As per concessionaire's detailed design to be approved by IE
133 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.10 - Integrated Tunnel Control System (ITCS) - SCADA | Authority to confirm whether SCADA for individual sub-system of ITCS is required or not like Ventilation, Electrical, Lighting, Fire Fighting, etc.? Kindly also confirm whether a separate PLC Network for each ITCS sub-system is required or not? | As per concessionaire's detailed design to be approved by IE
134 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.10.1 | Authority to inform on which all sub-system of ITCS Redundancy is required and what level of Redundancy is required? | As per concessionaire's detailed design to be approved by IE
135 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.10.1.1 | Authority to clarify on what all parameter needs to be checked/measured for the "Damage to road infrastructure" and how shall the same be indentified by the SCADA? Autority to also specify what all shall cover in "Other Unsual or expected events? | As per concessionaire's detailed design to be approved by IE
136 | Schedule D, Appendix -D2 | Technical Specifications Fixed Operating Equipment 4.10.1.4 | We presume that Police and Fire Brigade shall be contacted through external PSTN line and Vehicle Drivers shall be contacted by means of automated announcement from Evacuative Broadcasting System (EBS) and FM break-in system. Kindly clarify. | As per concessionaire's detailed design to be approved by IE
137 | Schedule D, Appendix -D2 | Hydrants with fire-fighting water shall be installed on both portals and in the hydrant niches in the tunnel. | We presume that Water Supply including its piping up to tunnel entrance at Each portal for Fire fighting and other purposes shall be provided by Client. We also presume that scope for Constrution, Operation & Maintenance of the Water Resorvioir Building shall also be in the Scope of Authority. | These shall be in the scope of the concessionaire
138 | Schedule D, Appendix -D2 | - | We presume that Liasioning and its applicable fees for Power Supply / Radio Frequency / FM Radio, etc. shall be in Authority’s Scope. | These shall be in the scope of the concessionaire
139 | Schedule B | Ventilation | Traffic data included do not correspond to those specified in Table 3 of document 8482B_II- ZOT_rep-08/12/00 8482B II, HVD (AADT 7,500 veh/24h, 33,33% HVD). Moreover, the emissions standard considered for calculations are no clearly identified. On one side the report establishes that the most recent emission standard is EURO 4 for passenger cars and EURO 2 for heavy duty vehicles. However, table 5 indicates values more unfavourable. Specific traffic data are requested. | The data provided in Appendix A 3 is the physical traffic count during the census carried out during the road open period in the summer (June July year 2011). This data has been provided to depict the present day intensity of traffic on Baltal-Drass axis(traffic likey to pass through the Zoji la Tunnel.) However the Technical specification provided at Appendix D 2, Technical Specifications Fixed Operating Equipment, Addendum 1 Ventilation Equipment lay down as the design average daily traffic at 7500 counts per day of mixed traffic for the operation life of the tunnel. The technical specifications further lay down criteria for the ventilation design. The standards laid down in the Technical specifications are expected to be met. Any further detailing or enhancement may be carried out by the concessionnaire.
140 | Schedule B | Ventilation | Calculations of the ventilation system for the emergency operation are independent of the length of the sections designed. Why the volume flow rate for the emergency operation is different in each section? | The basic design criteria for both the normal and emergency operations are mentioned at para 1 of the Appx D 2 Technical Specifications. Concessionnaire are advised to adhere to these and other parameters mentioned in the Technical Specification documents. The DPR volumes are provided only as guidelines.
141 | Schedule B | Ventilation | The ventilation design for the Egress tunnel is not clearly explained. How the air quality is justified all over the Egress tunnel, considering its length, with two unique axial fans atthe portals? | It is hereby clarified that only the major elements having significant influence on the tunnel cost have been included in the RFP in order to bring all bidders on a common platform and for ease of bid evaluation. The leeway of detailing rests with concessionnaire.
142 | Schedule B | Ventilation | The ventilation design for pressurizing the cross passages is not clearly explained. Does the pressurization for the whole Egress tunnel have been provided? | It is hereby clarified that only the major elements having significant influence on the tunnel cost have been included in the RFP in order to bring all bidders on a common platform and for ease of bid evaluation. The leeway of detailing rests with concessionnaire.
143 | Schedule B | Fire Fighting System | The distribution of fire fighting equipment (hydrants, fire extinguisher) is not justified under any standard. What regulations have been considered for the design of this facility? | European/PIARC standards have been followed. However the concessionaire is at liberty to adopt any established standards on approval by IE.
144 | Schedule B | Fire Fighting System | Design conditions for hydrant pipe network are not indicated (flow rate, residual pressure, number of hydrants of simultaneous operation, etc.). What regulations have been considered for the design of the water supply network for hydrants? | European/PIARC standards have been followed. However the concessionaire is at liberty to adopt any established standards on approval by IE.
145 | Schedule G, Scheduled Project Completion Date |  | It is envisaged that the construction from the Eastern Portal will be possible round the year. In such case whether the Rohthang Pass tunnel will be available by the time Construction works of Zojila Tunnel commences? Request to confirm the same. The Western Portal, Shaft No. 1 & 2 work fronts cannot be accessed during winter. Whereas, the SPCD is depending on the Interim Milestones to be achieved from these work fronts. As such, request to review & revise the Interim Milestones and SPCD accordingly. | Availability of Rohtang Tunnel can not be ascertained at this juncture on account of the technical difficulties encountered there.. Concessionaire are advised to resort to winter stocking for round the year work at the Eastern Portal. Costs of effects of winter stocking have already been included in the TPC.
146 | Schedule-G Project Completion Schedule |  | Request Authority to kindly restrict the occurrence of milestones to the Percentage of the total capital cost set forth in Financial Package only. The details of activities and % shall be finalised after the signing of the Concession Agreement in consultation with the Authority/IE. | As per RFP
147 | Schedule G Scheduled Completion Date | Project Milestones | Request you to modify following Physical project Milestones, Financial Milestones shall be modified accordingly: | As per RFP
148 | Schedule G | Project Milestones | Project Milestone-I to be modified from 365th day to 1095th day | As per RFP
149 | Schedule G | Project Milestones | Project Milestone-II to be modified from 730th day to 1460th day | As per RFP
150 | Schedule G | Project Milestones | Project Milestone-III to be modified from 1095th day to 2190th day | As per RFP
151 | Schedule G | Project Milestones | Project Milestone-IV to be modified from 1460th day to 2555th day | As per RFP
152 | Schedule G | Project Milestones | Project Milestone-V to be modified from 1825th day to 2920th day | As per RFP
153 | Schedule G | Project Milestones | Project Milestone-VI to be modified from 2190th day to 3285th day | As per RFP
154 | Schedule G | Project Milestones | Scheduled Project Completion Date to be modified from 2555th day to 3650th day | As per RFP
155 | Schedule G | Project Milestones | Construction of Access shaft-1 to be modified to excavation of Access shaft-1 | As per RFP
156 | Schedule G | Project Milestones | Construction of Access shaft-2 to be modified to excavation of Access shaft-2 | As per RFP
157 | Geotechnical Report for Tunnel and Structure locations |  | Request the Authority to provide the Detailed Geotechnical Investigations report for the tunnel and the structure locaitons | Already provided in the RFP
158 | Schedule - B | Depth of Shaft & Portal Elevation. | Details of Portal Elevation, Shaft length are defined in Schedule “B”, Fixing of portal elevation & shaft depth is big challenge without Bore Lag Data, which is not available in Geotechnical investigation report. Kindly provide the bore log data of Portal & shaft Locations. If the Bore log data is not available please provide the method of deriving the invert level of Tunnel, Portal Elevation, & shaft length. | Bore log data Could be collected from MORT&H. High volume data could not be uploaded. . The portal (Including elevation) have been fixed after carrying out multi criteria analysis based on the field data gathered during site investigation. All the dimensions e.g depth of the shaft and the invert level have been arrived at using CAD with the overlay of the predicted geotechnical conditions, and thus are considered to be accurate. However, the concessionaire may ensure at their own cost also.
159 | General | Extention of Bid due date | Kindly provide Bore log data, details of RoW, access roads to site, accessibility to muck disposal area, details of approach roads, essential clearances & permissions. | Bore log data have been provided. ROW is available. Concessionaire are advised to visit the site to assess the details of access roads to the site and the accessibility of the muck disposal area. Output parameters of the approach roads have been indicated in schedule B. Concessionaire are required to verify the design requirements as per the ground situation.
160 |  |  | We request for a joint site visit along with the consultant to identify the shaft & Portal locations to carry out geotechnical study & to prepare the report. | Concessionare may have a site visit at thier own cost in consultation with PIU office of this Ministry at Srinagar.
161 | General | Maps | Concessionaire need to carry Geological mapping along with the Geotechnical investigation to minimize the risk in cost estimation. | Agreed
162 |  |  | Geological maps can be only obtained from Defence Research Development Organization (DRDO) office which Government officials may get the maps easily than any private body. We request you to kindly provide the same either through DRDO or BRO. | DRDO is not the right agency to porovide geological maps. These maps are available with the Geological Survey of India(GSI). As per GSI procedures any interested party can procure these maps from them as per certain terms and conditions. The concessionaire are advised to approach the GSI in this regard. Also refer to reply at para 26.
163 | General | Environmental Clearance | Please provide the status of Environmental clearances for Project, Environment Impact Assessment (EIA) & Rehabilitation & resettlement plan. | Not Required
164 | General | Utility Shifting | Please provide the status of utility shifting. | To be shifted, if any, before appointed date.
165 | General | Forest land and clearance | Kindly clarify whether any part of the project highway or any project facilities comes under the Forest Department / Wild life sanctuary / Reserve Forest / Protected forest & status of the clearance for the same. | Not required. However, the same, if any, to be done before appointed date.
166 | General | Details of Land acquisition. | As per Schedule “A” Existing ROW is varying in between 10 to 15M. Schedule “B” is silent on proposed ROW. Requesting you kindly provide the Details of Land acquisition. | Details enclosed. (Ref Annexure-3)
167 | General | Drawing | We presume that the proposed drawings are for guidelines and reference purpose only. Concessionaire may design & prepare the drawings based on project requirement. Please clarify. | Confirmed. The concessionaire are required to carry out their own design and good for construction drawings
168 | General | Material obtained from Tunnel Excavation. | We presume that materials obtained from tunnel excavation can be used in construction activities for free of cost. Please clarify. | Agreed, subject to approval from IE/ Authority based on quality of rock materials.
169 | General | Access to the site | We presume that after opening the tunnel face, contractor will be allowed for execution / construction of tunnel round the clock & round the year. Requisite permissions shall be provided by authority to access the site during winter season. | Access to site will be made by contractor. Work may go all around the year as per site conditions.
170 | General | Bore Log Data & Report | We request you to please provide us the Bore log data & related report for the project. | All the data have been provided. Detail report could not be uploaded due to very huge data, same could be personally collected from MoRT&H.
171 |  |  | Whether we must submit only our PQ documents on closing date . PPP proposal to be submitted only if our JV qualifies, at a future date to be specified by you. | As per RFP (RFQ and RFP has to be submitted together).
172 |  |  | In accordance with FIDIC conditions, we would request you to accept sharing of risks on Geo Technical Conditions at site between the Concessionaire and MoRTH. This can be discussed in detail during Pre Bid Meeting. | As per RFP
173 | General | Report/Documents/details Required | Following Documents are mising:- 1.Executive Summary, 2. Tunnel Design Report. 3. Portal Design report 4. Geotechnical Tunnel Design Report, 5.Primary lining Analysis Report 6. Analytical analysis result. Result structural analysis 7. Cost estimation & BOQ 8. Preliminary Ventilation Design Report 9. Guideline inner lining concrete, 10. Ventilation Equipment, 11. Drawings mentioned in the Volume X, Technical Specifications of Fixed Operating Equipment | Already provided as Amendments on tender portal. Please download all the Amendments. Borelog data could be collected from MORT&H. High volume data could not be uploaded.
174 | Cl. 14.3.2 | The Parties hereto expressly agree that a Provisional Certificate under this Clause 14.3 may,... ... ... be issued for operating part of the Project Highway, if at least 100% (hundred per cent) of the total length of the Project Highway has been completed... ... ... | It is mentioned that provisional completion certificate can be issueed only after completing 100% of the total length of Project Highway. We presume that: A) Egress tunnel will not be considered while considering 100% of the length of the Project Highway. B) All the protective works including the snow gallery etc. will not be the part of 100% of the length of the Project Highway C) If the above are the part of 100% of the length of the Project Highway, then please clarify the significance of Provisional completion certificate. | As per RFP documents
175 | Schedule -B Cl-6.1 | Design speed | Due to steep gredient & sharp kink, desired design speed may not be feasibile. We presume that it shall be designed based on gradient & sharp kinks | To de designed as per RFP.
176 | Schedule -B Cl-1.15,1.16 | Access road conncetividty to site instalation & muck Disppsal | We persume that connctivity from the project site for muck disposal & Site installation shall be provided by the Authority. Kindly clarify | Access route to muck disposal areas shall be concessionaire's responsibility.
177 | Clause 24.1.1 DCA | 180 Days for Financial Closure | Time period given for Financial Close is not enough considering the quantum of the project and keeping in mind the current economic scenario pertaining to lending for the Infrastructure Sector. In view of the same, we kindly request the Authority to provide minimu of 270 days for Financial Close. | As per RFP documents
178 |  | Bid Submision | In e-tendring procedure 2 (ii), A (g) it is written certificate of Undertaking as specified in Clause 2.25 of the RFQ. It should be Undertaking only, please clarify. | It is certificate of Undertaking.
179 |  | Schedule-B | In our opinion on wetern portal side instead of provision of approach road, bypass and snow galleries, it will be a better option to provide a raised and long viaduct structure through the valley and away from the hill side to avoid snow. In that case the snow will be slided under the viaduct structure without affecting the approach road usage. Secondly, it will help in avoiding large scale quantities of earth work involved in embankment. The arrangment of borrow area for huge quantities of earth work will create environmental issues. The muck excavated from tunnel cannot be used in road construction because of lagging time phase. please confirm. | As per RFP. However, the concessionaire may adopt the safety measures from the alternative design as per prevailing site condition considering adverse impact of avlanches etc.
180 | Schedule B | 1.3.2 | We presume that 14.083 m is typographical error, it have been 14.083 km. Please confirm. | The total length of the tunnel including the cut and cover portions is 14.150 km.
181 | Schedule B clause 1.4.3 |  | For shaft 3 the dia 6m needs to be increased for opening two more faces and similarly shaft 1 and shaft 2 dia can be decreased as it would not be necessary and also would achieve higher speed of construction, is it allowed? Please confirm. | As per RFP.
182 |  |  | At the eastern portal, the elevation of the portal can be lowered so that the existing road would not be disturbed and subsequently, the bypass could be avoided. Please confirm. | As per RFP.
183 | E-tender procedure Cl.I (vi) |  | Please confirm if the tender processing fee of Rs 1,295/- (Rupees one thousand two hundred and ninety five only) shall be paid online or though demand draft. If the payment is to be made throug DD, please confirm the details of the beneficiary. | The fees of Rs 1,295/- will be paid online and the fees for RFQ / RFP will be by demand draft.
184 | General |  | Please provide the encroachment details for Project Highway. | At present, land is available, if any encroachment, the same will be removed before Appointed Date.
185 |  |  | Please confirm if the single lane unidirectional twin tube instead of bidirectional single tube with egress tunnel can be proposed. | As per RFP.
186 |  |  | At the chainage 2+250 km, the overburden (cover of the tunnel) seems to be very less and this could be critical for tunnel construction and it is not shown in the L-section. The cover which was visible, it appeared to be glacier and not rock. Please confirm if the survey/investigation data for this location is available and provide the same. | All the data have been provided. Detail report could not be uploaded due to very huge data, same could be personally collected from MoRT&H.
187 |  |  | The scope of work includes construction of 14 Km tunnel; three Shafts and no Adit. The portal at Sonmarg is closed for at least 4-5 months a year. The construction period of 7 years is too optimistic and it is therefore requested increase the construction period to 9 years and thus the total concession period shall be modified to 24 years. For relevant comparision purpose, the critical details of Z-Morh tunnel which is under execution is given below: Z-Morh Tunnel-6.5 km tunnel, No shafts, Better approach roads, No closure of site, construction period of 5 years. | Construction schedule has been developed after incorporating all contingencies. As Per RFP.
188 | Clause 12.4.3. of DCA | Delay in Construction "In the event that Two-Laning is not completed within 270 (two hundred and seventy) days from the Scheduled Two-Laning Date, unless the delay is on account of reasons solely attributed to the Authority or due to Force Majeure, the Authority shall be entitlement to terminate this Agreement. | Considering the nature and technical complexities of the project, there is a possibility of technical challenges can occur during the construction period, whcih will be beyond the control of the concessionaire, this will lead to delay the construction period therefore, please change the clause to Ïn the event that Two-Laning is not completed within 730 (Seven Hundred Thirty) days from the Schedule Two-Laning Date, unless the delay is on account of reasons solely attributable to the Authority or due to Force Majure, the Authority shall be entitled to terminate this Agreement. | At present, the changes in the RFP are not possible. This will be taken up as per RFP clauses.
189 | Schedule-A Annex-1, 1.1 | The site: The Project Highway aims at construction of tunnels and approaches in general area between km 95 & km 119 of the Srinagar - Leh section of NH-1 as per following details: 14.150 km long two lane bidirectional single tube tunnel with a parallel 14.200 km long egress tunnel on new alignment between Baltal & Minamarg along the existing NH-1 in J&K. | Being DBFOT project, can the Concessionaire, without increase in cost and time, be allowed to follow the international practice and design and adopt alternative section like twin tube unidirectional layout instead of one bidrectional traffic tunnel and one egress tunnel, both tubes having same c/s ,i.e. a clear width of 6.5m and height of 5.5m in addition to the 1.0m wide maintenance walkways at both sides. this arrangement will be efficient in accident prevention, no chance of head on collission and allow smooth movement of traffic. The approach shall be modified accordingly with both roads converging at a small distance from portal face as per design requirements. | This change in the scope of work may lead to change in the cost of tunnel and ultimately it will affect the annuity. As the cost is already approved by the Cost Committee/ PPPAC/CCEA, so this may not be considered to allow any change in the scope at this stage. However, after the award of work, the selected Concessionaire may propose twin tube unidirectional layout instead of one bidirectional traffic tunnel and one egress tunnel, without any financial implication, which may be considered in consultation with Independent Engineer.
190 | General |  | The requirement of ventiliation systems shall be allowed to be provided based on design requirements. The number of ventilation shafts can be reduced to two, considering reduction of tunnel height. Whether it will be permitted if alternate design is adopted by the Concessionnaire. | The numbers for ventilation design & shafts are as per RFP.
192 | 2.8 |  | What are the possible deductions from annuity payments? Whether VAT/TDS will be deducted for the project at the earliest | As per RFP